PC-1 FORM

GOVERNMENT OF PAKISTAN

PLANNING COMMISSION

KHYBER PAKHTUNKHWA -RURAL ECONOMIC TRANSFORMATION PROJECT – RETP

TOTAL COST: PKR 29 BILLION

Financed by:

International Fund for Agriculture Development (IFAD)

And

Planning and Development Department

GOVERNMENT OF KHYBER PAKHTUNKHWA

15th July 2021

# Table of Contents

Table of Contents	i

Weights and measures	iii

Currency Conversion	iii

Abbreviations and Acronyms	iv

Explanatory Notes	vi

Name of the project	1

Location	1

Authorities responsible for sponsoring, execution, O&M and concerned federal ministry	1

Plan provision	1

Project objectives and its relationship with sector objectives	2

A.	Project Objective	2

B.	Relationship with Sector Objectives	2

C.	Partnership	3

Description, justification, technical parameters and technology transfer aspects	4

A.	CONTEXT, JUSTIFICATION AND RATIONALE	4

B.	PROJECT DESCRIPTION	5

C.	PROJECT COMPONENTS	7

1	Component 1: Agribusiness Development	7

1.1.	Sub-Component: Development of Professional Farmer Organizations (PFOs)	7

1.2.	Sub-Component: Development of Public-Private-Producers Partnerships (4Ps)	9

1.3.	Sub-Component: Reorganising Farm Service Centres as Farm Services Companies	11

1.4.	Sub-Component: Institutional support services	11

2	Component 2: Skills Development and Employment Promotion	12

2.1.  Sub-Component 2.1: Vocational and Technical Skills Development	14

2.2.	Start-up capital for self-employment/enterprise development	17

2.3.	Job placement/Induction	18

3	Component 3: Programme Management, Policy, and Institutional Support	19

Capital cost estimates	20

Annual operating and maintenance cost after completion of the Project	20

Demand and supply analysis	22

A.	Situation Analysis	22

B.	Opportunities	22

Financial plan and mode of financing	24

Project benefits and analysis	25

A.	Financial Analysis/Benefits	27

B.	Economic Analysis	27

C.	Social benefits with indicators:	28

D.	Employment generation (direct and indirect)	28

E.	Environmental impact	29

F.	Impact of delays on project cost and viability	30

Project Implementation	31

A.	Implementation schedule	31

B.	Result Based Monitoring (RBM) Indicators	31

Management structure and manpower requirements including specialized skills during construction and operational phases:	31

A.	Project Steering Committee (PSC)	31

B.	Project Management Unit (PMU)	32

C.	Regional Coordination Units (RCUs)	33

D.	Management and Operations	34

E.	Project Implementation Manual (PIM)	36

ANNEX I. DETAILED COST ESTIMATES BY COMPONENTS	38

ANNEX-2: RESULT BASED MONITORING (RBM) INDICATORS	43

ANNEX-3(A): MAP OF THE AGRIBUSINESS HUBS AND SUPPLY CHAIN CLUSTERS	47

ANNEX-3(B): AGRIBUSINESS HUBS AND SUPPLY CHAIN INTERVENTIONS AND TENTATIVE INVESTMENT OUTLAY	48

# Weights and measures

| 1 kilogram | = | 1000 g |
| --- | --- | --- |
| 1 000 kg | = | 2.204 lb. |
| 1 kilometre (km) | = | 0.62 mile |
| 1 metre | = | 1.09 yards |
| 1 square metre | = | 10.76 square feet |
| 1 acre | = | 0.405 hectare |
| 1 hectare | = | 2.47 acres |

# Currency Conversion

1 USD				=	162.81 PKR (last 6 months average of inter-bank exchange rate 						until 30th October 2021)

# Abbreviations and Acronyms

| ADB | Asian Development Bank |
| --- | --- |
| ADP | Annual Development Programme |
| AHITI | Animal Husbandry In-Service Training Institute |
| ATI | Agriculture Training Institute |
| AWPB | Annual Work plan and budget |
| BISP | Benazir Income Support Programme |
| BISP-PSC | Benazir Income Support Programme – Poverty Score Card |
| BRI | Belt and Road Initiative |
| CBN | Cost of Basic Needs |
| CDWP | Central Development Working Party |
| C&W | Communication and Works Department |
| CO | Community Organization |
| COSOP | Country Strategic Opportunities Programme |
| CPEC | China-Pakistan Economic Corridor |
| DFI | Development Finance Institution |
| DFID | Department of International Development |
| EAD | Economic Affairs Division |
| ECNEC | Executive Committee of National Economic Council |
| FA | Financing Agreement |
| FATA | Federally Administered Tribal Area |
| FY | Fiscal Year |
| GCC | Gulf Cooperation Council Countries |
| GII | Gender Inequality Index |
| GDP | Gross Domestic Product |
| GLLSP | Gawdar-Lasbel Livelihood Programme |
| GLOF | Glacial Lake Outburst Floods |
| GNI | Gross National Income |
| HHs | Households |
| IFAD | International Fund for Agriculture Development |
| IMF | International Monitory Fund |
| JICA | Japan International Cooperation Agency |
| KM | Knowledge Management |
| Km | Kilometre |
| LSO | Local Support Organization |
| M&E | Monitoring and Evaluation |
| MFB | Micro-finance Bank |
| MFI | Micro-finance Institution |
| MPI | Multidimensional Poverty Index |
| NAVTEC | National Vocational & Technical Education Commission |
| NMD | Newly Merged Districts |
| NGO | Non-Government Organisations |
| NER | National Economic Registry |
| NPGP | National Poverty Graduation Programme |
| NPGI | National Poverty Graduation Initiative |
| P&D | Planning and Development Department |
| PDR | Project Design Report |
| PKR | Pakistan Rupees |
| PC-I | Planning Commission Proforma-I |
| PCN | Project Concept Note |
| PMT | Proxy Mean Testing |
| PMU | Project Management Unit |
| PPAF | Pakistan Poverty Alleviation Fund |
| PSC | Project Steering Committee |
| RSP | Rural Support Programme |
| SDGs | Sustainable Development Goals |
| SECAP | Social, Environmental and Climate Assessment in Projects |
| SMP | Social Mobilization Partner |
| SSN | Social Safety Net |
| SSN-TUP | Social Safety Net – Targeting the Ultra Poor (an IFAD pilot) |
| TA | Technical Assistance |
| TEVTA | Technical Education & Vocational Training Authority |
| UCT | Unconditional Cash Transfer |
| UNDP | United Nations Development Programme |
| USD | United States Dollars |
| VO | Village Organization |
| WB | World Bank |

# Explanatory Notes

- The Rural Economic Transformation Project (RETP) is a flagship initiative of the Government of Khyber Pakhtunkhwa for the renascence of the rural economy of the province. The project will focus on the development and promotion of 5 high value agribusiness clusters. Following is the brief organisation of the agribusiness clusters (details of districts in each cluster are given in para 13.10);

  - The Southern Agribusiness Cluster: With a focus on development of halal and organic agribusiness industry with supply chains covering, halal meat, dairy (benefiting from the river Indus banks), cereals (bio-fortified wheat), grapes, citrus (seedless oranges, lime and lemons), rose/floriculture, nuts, coffee, and high value vegetables. The focus will be on promoting value addition/processing into a product mix with demand. Possible collaboration with foreign direct investment will be explored. The agribusiness zone will have the hub/free economic zones at DI Khan. Essential support will be leveraged for ensuring compliance notably certification related to Good Agricultural Practices (GAP), organic, Good Manufacturing Practices, Hazard Analysis and Critical Control Points (HACCP) and ensuring disease free status with respect to foot and mouth and other diseases relevant to compliance regimes.  Hub of this cluster will be DI Khan.

  - The Central Agribusiness Cluster: With a product mix of citrus (oranges), peaches, pears, lychees, vegetables using structured/vertical farming techniques, strawberries, organic brown sugar, dairy and other niche products, the supply chains will take advantage of the Rashakai economic zone. Capacity building for compliance will be supported as required. Hub of this cluster will be Mardan.

  - The Northern Agribusiness Cluster: The predominant focus shall include horticulture products pome fruits, peaches, off-season vegetables, buck wheat, saffron, medicinal and aromatic plants and aromatic rice. Hub of this cluster will be Mingora.

  - The Chitral Natural Products Agribusiness Cluster: With a unique low input agriculture the zone represent potential for organic, produce from nature and niche products such as buck wheat, saffron, medicinal and aromatic plants, potato, off-season vegetables and nutraceuticals. Hub of this cluster will be Chitral proper.

  - The Eastern Agribusiness Cluster: The zone has the potential for agribusiness activities with a mix of pome fruit, high value off-season vegetables, potato, maize corn and dairy production. The zone will take advantage of the CPEC route. Hub of this cluster will be Mansehra.

- This PC1 shall be read in conjunction with the following documents;

  - Project Implementation Manual (PIM)

  - Feasibility Studies/Business Plans for Professional Farmer Organization (PFO), Public Private Producer Partnership (4P) and Farm Services Company.

  - Economic and Financial Analysis (EFA)

  - Social, Environment and Climate Change Procedure (SECAP) and related assessment

  - Integrated Project Risk Matrix (IPRM)

  - Detailed Cost Tables

- The Project Implementation Manual (PIM). A standalone document which contains comprehensive guidelines to facilitate coherent, effective and efficient implementation of the project interventions. PIM describes the management actions, processes, systems and mechanisms involved in effective implementation of the project and will enable implanting units to achieve development objective in an efficient and timely manner. PIM also includes roles/responsibilities of staff and scope of work of potential service providers. It is pertinent to mention that PIM provides an initial guideline based on project design that would require updating and revision as the programme progresses. However, such updating, and revisions would stay within the overall project objectives and target groups and subject to approval by IFAD and PSC.

- Feasibility/Business Plans. At the project design stage, based on the field consultations, three indicative business plans have been developed. These include a business plan for a Professional Farmer Organisation (PFO), a Public-Private-Producers Partnership (4Ps) and a Farm Services Company (FSC). In addition, the viability of the intervention under component 2 are studied under the economic and financial analysis by working out enterprise models using the “with” and “without” project scenarios. The feasibility studies are provided as Appendix 2A, 2B and 2C.

- Engagement of Department/Service Providers. Based on the needs assessment of the PFOs/4Ps/FSCs, evolving implementation environment and knowledge gained, the project management unit will identify the need for performance-based partnerships to be developed with public, private and civil society organisations and seek approval of project steering committee (PSC).

- The cost estimates in the PC1 are rounded to one decimal level. The detailed component-wise costs estimates and unit costs are given in ANNEX-1.

GOVERNMENT OF PAKISTAN

PLANNING COMMISSION

PC-1 FORM

(SOCIAL SECTOR)

| 1 | # Name of the project | Rural Economic Transformation project ( RETP-KP) |  |
| --- | --- | --- | --- |
| 2 | # Location | All over the province – covering 35 Districts |  |
| 3 | # Authorities responsible for sponsoring, execution, O&M and concerned federal ministry - Sponsoring - Execution - Operation and maintenance - Concerned federal ministry | - Planning & Development (P&D) Department, Government of Khyber Pakhtunkhwa - Coordination and Management by Planning and Development Department, Government of Khyber Pakhtunkhwa through a dedicated and autonomous Project Management Unit (PMU) at Peshawar and 5 Regional Management Units (RCUs). - Implementation through Relevant line departments including but not limited to: - Agriculture, Livestock and Cooperatives - Industries, Commerce and Technical Education - Zakat, Usher, Social Welfare, Special Education and Women Empowerment - Technical Education and Vocational Training Authority - Halal and Food Safety Authority Note: Implementing partners to be engaged through performance-based MoU/agreements during project implementation based on the needs/roles identified. The existing project under ADP and PSDP will be leveraged under the project for building synergies, efficiency and fostering collaborations. - Relevant provincial line departments, Professional Farmer Organisations, Private Sector and Farm Services Centres - Not applicable |  |
| 4 | # Plan provision | The total cost of the Project is PKR 29 billion which includes financing of PKR 16.300 billion (USD 100.1 million) IFAD loan (56%), PKR 4.712 billion leveraged by provincial government (16%) and PKR 7.988 billion contributed by beneficiaries/private sector (28%). The scheme is reflected in ADP 2021-2022 at S.No. 1148 (Project Code-210257) and S.No. 07 under Appendix V: Donor-Wise Summary of Foreign Assistance. |  |
| - 5 | # Project objectives and its relationship with sector objectives |  |  |
|  | ## Project Objective - The overall goal of the project is to contribute to poverty reduction, and food and nutrition security of rural households. The development objective is improved rural income and employment through high value agriculture and off-farm/non-farm related activities in a sustainable and climate resilient manner. The project aims to addresses the main causes of rural poverty and food insecurity. These include low productivity and inefficient production system, wastages and low return from unorganized smallholders dominated farming, poor market orientation and weak linkages to supply chains, youth and women unemployment in rural areas as well as limited access to economic services, causing in turn income losses, food insecurity and malnutrition. - The specific objectives are; - Improve production and income of 700,000 small farmer through agribusiness development particularly for high value and niche crops tapping on the province’s comparative advantage and improved agriculture services. Agribusiness development will be pursued under the framework of Professional Farmers’ Organizations (PFOs), Public-Private Producer Partnerships (4Ps) and improved delivery of economic services. - Improved capacities of farmers and institutions to assess climate/environment risks; and plan and identify climate adaptation/mitigation measures concerning changing weather and climate conditions. - Address the critical challenges of 110,000 job market integration through; (i) market orientated and experiential skills development; (ii) market readiness for self-employment (start-up capital); and (iii) integration of young graduates in job market. - Employment promotion and agribusiness development components are complementary in terms of new rural services and employment development opportunities created by agribusiness and skills development to integrate trades related to agribusiness. ## Relationship with Sector Objectives - The project outcomes will contribute to the poverty reduction goals as outlined in the Vision 2025, 12th Five Year Plan, GoKP strategic development strategy 2019 – 2023, Poverty Reduction Strategy 2019, National Food Security Policy and Khyber Pakhtunkhwa Agriculture Policy. The project will also support youth development and empowerment and gender equality and women empowerment under the umbrella of National Youth Development Framework/Kamyab Jawan Programme, provincial Women Empowerment Policy 2017 and Youth Policy 2016. The project also contributes to balanced regional development objective of the 12th Five Year Plan - As a flagship initiative, the project aims at transformation of the rural economic and is specifically aligned to the following major strategies and sector objectives. - National Food Security Policy: The project will support the National Food Security Policy aims of achieving the reduction in poverty, malnutrition, and food insecurity by reaching an average growth of 4% for the agriculture sector. To enhance the agriculture and livestock sectors, the federal government launched a five-year PKR. 309 billion (about USD 2 billion) National Agriculture Emergency Programme in 2020. The programme focuses on emergency support (mainly subsidies on inputs) and is being executed with the coordination of the provinces to enhance productivity of major crops and improvement of water efficiency. - Vision 2025: The Program will directly contribute to attainment of targets under Government of Pakistan’s Vision 2025, including: Pillar I (Youth: channelize and streamline the energies of Pakistan’s large youth population and realize their immense economic potential, Gender Equality and Women’s Development: ending the discrimination faced by women, and providing an enabling environment for them to realize their full potential and make their contribution to the socio-economic growth of the country); Pillar II, (Reduce Poverty by half); Pillar IV (Food Security: Protect the most food-insecure segments of the population, Agriculture: Create a modern, efficient and diversified agricultural sector. Climate Change: Explicit recognition of the relevant risks (and associated economic and social costs and implementation of well-defined mitigation and adaptation strategies/measures). - 12th Five Year Plan: The Federal Government 12th Five Year Plan 2018-23, set the target of reducing Cost of Basic Needs based poverty from 24.3 percent to 19.0 percent by 2023 and reducing multidimensional poverty headcount from 38.8 percent in to 30.0 percent during the plan period. The 12th Five Year Plan is aligned to Sustainable Development Goals and articulates the government’s commitment to attain SDG goals in terms SDG 1 (No Poverty), SDG 2 (Zero Hunger), SDG 5 (Gender Equality) SDG 6 (Decent Work), and SDG 13 (Climate Action). - Agriculture Policy-Khyber Pakhtunkhwa - A 10 Year Perspective (2015-2025). The project will support the Agriculture Policy objectives of Enhance sector productivity and competitiveness; Address food security and incomes needs of the vulnerable sections of the population and targeted actions to improve food security, reduce poverty and enhance the role of women; and natural resource management, adaptation to climate change and disaster risk management. - Sustainable Development Strategy (SDS): The project’s objective and interventions are fully aligned with the overall objective and the thematic areas and sectoral objectives spelled out under Strategic Development Strategy 2019-2023 of the Government of Khyber Pakhtunkhwa. - THEMATIC AREA 3: Economic Growth and Employment Opportunities: Socio-economic development by creating employment opportunities in association with the private sector is a key objective under the thematic area. - THEMATIC AREA 6: Agriculture, Food Security and Safe Environment: Key objectives include Increased food production and trade; Use of climate-smart production technologies; Value-addition and reduced post-harvest losses; Public-private partnerships; Agricultural insurance and credit; and Institutional and policy reforms. - National Youth Development Framework/Kamyab Jawan: The Project is closely aligned to the National Youth Development Framework’s objectives of social and economic empowerment of youth women and men through promotion of vocational skills, financial inclusion, entrepreneurship and micro business support. - SDGs: The Program will contribute towards the achievement of at least six SDGs including Poverty (SDG 1), Zero Hunger (SDG 2), Gender Equality (SDG 5), Decent work and Economic Growth (SDG 8), Reduced Inequalities (SDG 10) and Climate Action (SDG 13). ## Partnership - The project will seek synergies and promote complementarities with Ehsaas/National Poverty Graduation Initiative of the Federal government (particularly with IFAD-funded National Poverty Graduation Programme already present in 10 of the 35 districts in KP), as well as with all other donor and Government of Khyber Pakhtunkhwa funded programmes particularly the ones under the departments of; Industries, Commerce & Technical Education/TEVTA; Agriculture, Livestock & Cooperatives (Farm Services Centres, agriculture extension and research for instance);, Zakar-Usher, Social Welfare, Special Education and Women Empowerment (particularly women centres in merged districts); Accelerated Implementation Programme and Agriculture Transformation Programme etc. Coordination will be established with the FAO and WFP to reinforce respective interventions, especially on climate resilience aspects, mainstreaming nutrition and policy support on food security, nutrition and women empowerment. |  |  |
| 6 | # Description, justification, technical parameters and technology transfer aspects |  |  |
|  | ## CONTEXT, JUSTIFICATION AND RATIONALE - Khyber Pakhtunkhwa province is the third largest province of Pakistan with a land mass of 101,741 km2 and population of 35.35 million (4.4 million households). Rural population is 81%. The province is administratively divided into 7 divisions and 35 districts including 7 merged districts of the erstwhile federally administered tribal areas (FATA). - Multidimensional poverty in the province is 49% against the national average of 39%. Rural poverty is nearly 58%. The multidimensional poverty in the MDs is close to 74%. The number of HH categorised as extremely and chronically poor (BISP PSC 0-16.7), in the province, is estimated at 1.6 million. - The economy is dominated by the services sector which contributes about 67% to provincial GDP followed by manufacturing (17%), and agriculture (14%). Despite the declining share of agriculture in the GDP, the sector accounts for employment of 32% of labour force and provides direct and indirect livelihood to 80% of the rural population. Small farmers constitute 95 percent of the total farms and mostly undertake subsistence farming and follow mixed farming system consisting of agriculture and livestock and supplementary income through off and non-farm labour. Rural poverty in the province is found to be strongly correlated with lack of productive assets, limited to no access to markets and services, insufficient private sector participation, lack of farm, off farm and non-farm employment; limited avenues for the youth in rural areas for market-responsive skills development for jobs, and; increased vulnerability of people and assets to climate induced disasters. - Low labour force participation rate, high unemployment rate particularly among youth, predominance of informal economy, low level of education and skills and very low participation by women are some of the features of labour market in the province. An inadequate skilled workforce has remained a major challenge over the past few decades particularly for agriculture value addition and the emerging manufacturing, hospitality, construction mining and services sectors. The unemployment rate in the province is 8% against the national average of 5.7%. The labour force participation rate is 43% with only 13% for women. Youth (age 15-24) employment to population ratio is 30% compared to the national average of 40%. The employment to population ratio for women age 15-24 year is a paltry 9.3%. While the unemployment rate in the province is 8 %, the quality of employment does not necessarily ensure gainful/productive employment. Among the employed people, 77% work in informal sectors, of which an estimated 38% are self-employed/own account workers and 24% are family workers; and only 12% are wage workers with a written contract. The youth face a three times higher unemployment rate and are more likely to work in informal sectors than older age groups. - The province however, because of its unique agro-climatic conditions, has enormous growth potential in the development of high value horticulture crops and floriculture, as well as in the development of livestock and fisheries sector. The farmers continue to face market, capacity, and credit constraints that deprive them to participate in high value markets and maximize their incomes while at the same time, kept agriculture development far less than the potential that the province offers in terms of its unique and diverse agro-climatic conditions. The current youth bulge can be gainfully employed and contribute to provincial economy through benefit from rejuvenating agriculture sector and skills developments for meeting the demand of the other emerging sectors of the economy. - Within the above context, Government of KP identified a strategic opportunity of engaging with IFAD in addressing the objective of transforming its rural economy to address the persistent issues of poverty reduction, youth unemployment and food insecurity in rural areas. The primary rationale for IFAD’s engagement for KP- RETP is its successful introduction and implementation of rural economic development mainly agribusiness promotion, value chain development and employment generation in Pakistan. The proposed project offers the province an opportunity to leverage IFAD’s experience to implement and scale up the evidence-based successful agribusiness models and employment generation approaches. Learning from the experiences of IFAD-funded projects, KP’s own initiatives and international best practices, the project will demonstrate and scale up in the areas of (i) promoting agribusiness development based on the comparative advantage of each of the agro-ecological zones/clusters having a focus on horticulture/livestock and dairy and high value crop production, value addition and marketing; (ii) skills development in line with the market demand and youth market readiness, (iii) through the agribusiness and skills development as a mean develop rural economic zones with the potential to not only national markets but also position private sector to enter into high end international markets. Climate resilience and nutrition outcomes would be achieved through a right mix of investments in community training and awareness combined with climate/environment proofing of new technologies. ## PROJECT DESCRIPTION - Project Objective: The overall goal of the project is to contribute to poverty reduction, food and nutrition security and strengthened resilience of rural households. The development objective is improved rural income and employment through high value agriculture and off-farm/non-farm related activities in a sustainable and climate resilient manner. - Geographic Area: The project will cover all 35 districts of the province to allow equitable coverage of the potential of all agro-ecological zones and exploit regional/district specific employment opportunities. However, project implementation will follow a phased approach whereby 3 districts per region will be rolled out per year with the aim of covering all the 35 districts by the Mid Term stage of the project (End of Year 3). RETP will integrate beneficiaries of IFAD financed National Poverty Graduation Programme (NPGP) in 10 districts of the province and of those projects/ADP schemes for which leveraging is confirmed by the Project Steering Committee. An equitable coverage of merged districts will be ensured in the phasing of project implementation keeping in view security situation, poverty/malnutrition and potential endowments with regards to agribusiness and youth employment. - Target Group: The KP- RETP target groups will fall under the category of smallholders (<12.5 acres or 5 ha), landless households (HH), rural youth and the poor. While participation in project activities will be demand driven, among the overall target population, priority will be given to the rural poor in BISP-PSC 0 – 34 range. Women and youth will be particularly targeted with specific interventions leading to their integration into economic activities. The target groups (small farmers, youth and women) will be pre-identified using selection criteria which include poverty, relevance and willingness. - Youth, Gender and Nutrition strategy. The project will target 50% youth and 25% women beneficiaries in all the project activities. Gender and women development will be mainstreamed in both agribusiness component as well as skills development. Women will also be especially targeted for maternal and child nutrition education. The project will build on the current initiatives and institutional arrangements flexibly to generate intended outcomes for youth, gender, and nutrition. In particular the following will be adhered in the project implementation; - The project, using the nutrition-sensitive value chain selection guidelines of IFAD, will select commodities with the highest impact on nutrition and dietary diversification. - The youth and the women headed households and landless in the BISP-PSC category of 0-11 (ultra-poor) will be given priority in selection criteria and will be exempted from community contribution like payment of FSC or PFOs fees and will be given priority access to wage earning opportunities under the employment generation programme (component II). - The project will in collaboration with WFP and FAO, assist the Government of Khyber Pakhtunkhwa in improving policy framework related to youth and women. - The M&E system would monitor youth, gender and nutrition dimensions in a disaggregated manner. - Project Beneficiaries: Around 785’000 households (4.35 million persons) will benefit directly and indirectly from RETP interventions through a range of agribusiness development, improved economic services delivery and skills development/employment [promotion interventions. - Agribusiness development interventions are expected to reach around 700,000 households through 550 PFOs, 20 4Ps, 35 Farm Service Companies and improved services of agriculture extension and research. This project supported PFOs will be established based on market studies, business plans, professional management teams, matching grant investments, partnerships, processing development, as well as clear break-even points and exit strategies. The necessary technical assistance as well as the coaching, mentoring, capacity building necessary to develop the business plan proposals, to register or to organize these institutions will be provided by RETP to ensure sustainability within 4 to 5 years. Performance based MoUs/partnerships/contracts will be developed with relevant departments/services providers for provision of support to the PFOs, 4Ps and FSCs. - Skills development and employment: A total of 110,000 youth (women and men) will benefit from a specific and dedicated skills enhancement for successful agribusiness development and rural employment promotion. These will be done through demand driven vocational and technical trainings; provision of start-up capital for self-employment and hands-on professional exposure for graduated trainees through induction programme in public, private and civil society institutions. - Project Period: The Project will be implemented over a period of seven years (2022-2028). - Project Design Parameters and Approach: The project design is based on a Government of Khyber Pakhtunkhwa and IFAD joint and in-depth assessment of the challenges and opportunities in terms of rural transformation, agribusiness and rural employment promotion. The rationale emanates from the approach of successful on-going and past IFAD-funded projects in Pakistan and globally as well as interventions of Government of Khyber Pakhtunkhwa. The project addresses the existing financial and technical gaps in the related sectors and will develop tested pathways to be upscaled and financed by the regular budget/ADP of the Government of Khyber Pakhtunkhwa. To this intent in view, the project will consolidate the investment made by the government through the establishment of fully autonomous and sustainable Farm Service Companies to make them complementary to the agribusiness development component. In addition, the project will be closely involved with the Technical Education and Vocational Training Authority (TEVTA) and Social Welfare Department to make its training programmes more responsive to labour market and potential employers. Also, TEVTA/Social Welfare Department will be assisted in addressing the testing/certification challenges as well as curricula development/improvement, training delivery and linkage of skills development to market demands. The approach will be fully compatible with the rural target groups, in particular the youth and women context. - The project approach further provides an integration and complementarities between the project components. The agribusiness development will create the necessary potential and institutional need (in the form of PFOs, 4Ps and FSCs) to absorb a significant number of youth to be trained with a purpose through the skills development component. The demand will be tied to the human resource capacities needed by PFOs, FSCs or 4Ps. The approach will also help improve development effectiveness for strong services market, through agribusinesses seeking services which in turn will help the agribusiness sector to thrive. The Project Management and Policy Support Component will provide: (i) effective management and implementation coordination; (ii) advocate and support policy reform to improve the rural poor’s livelihoods; and (iii) to facilitate and ensure the sustainability of project activities initiated through the project. This will allow the project to deliver results beyond the expected outcomes from the project investments. The approach of the project for agribusiness development is multi-pronged. While at the sector level major impetus will be on high value horticulture and livestock sub-sectors the investments will be made in such a manner that agribusiness cluster emerge as rural economic zones. ## PROJECT COMPONENTS - To achieve the objectives, the project interventions are grouped into: - Agribusiness Development (Professional Farmers Organizations, 4P Development, Farm Service Companies and Institutional Services), PKR 15.527 billion (USD 95.37 million) - Skills and Employment Promotion (Skills Development for agribusiness, employment, start-up capital for self-employment; Public –Private internship programme, support to TEVTA), PKR 11.098 billion (USD 68.17 million) - Project Management and Policy Support. (Management, implementation coordination and policy support, technical assistance), PKR 2.375 billion (USD 14.6 million) - The project investment will be distributed proportionately and equitably in the agribusiness clusters. Following is the description of project components and sub-components. ### Component 1: Agribusiness Development - The Agribusiness Component will have a focus on developing five economic zones including (i) Southern Agribusiness Cluster with its hub in Draban Agro-Halal Processing Zone; (ii) Central Agribusiness Cluster with its hub at Rashakai Economic Zone, Mardan; (iii) Northern Agribusiness Cluster with its hub in Mingora, Swat; (iv) Eastern Agribusiness Cluster with its hub in Mansehra; and, (v) Chitral Natural Food Products Cluster with its hub in Chitral city. The interventions are briefly summarised in the following sub-sections; - Southern Agribusiness Cluster. The cluster will have a focus on the promotion of niche products relevant to the agro-ecological conditions and to gradually establish certified organic pockets for production of high value produce. The cluster will consist of 11 districts i.e. DI Khan, Bannu, Laki Marwat, Hangu, Kohat, Karak, Orakzia, Kurram, Tank, North Waziristan and South Waziristan. The key interventions will include promotion of; (i) seedless citrus; (ii) dairy/halal meat; (iii) floriculture; (iv) grapes; (v) peanuts and, (vi) dates (vii) guava (viii) pine nut (ix) melons. Key interventions shall include; Intervention Areas; Activities; Institutional responsibilities. Dates value chain; - Transformation of dates production, harvesting and processing through introduction of modern technology – pollination, protection of produce, harvesting, dehydration, processing, branding/labelling etc. - Matching investment with farmers’ organizations and private sector for processing and cold storage/warehousing Quality certification of dates and its products; - Certification service providers - Agriculture Department Farmers’ organizations/ private sector. Offseason & high value vegetables; - Introduction of improved varieties and new technologies for OS/HV vegetable production. - Grant support to PFOs in establishment of aggregation centers. - Introduction of improved packaging. - Mobilizing private sector investment in vegetable processing i.e chips, paste, ketchup, frozen etc. - Support to farmers in market access and linkages. - Capacity building of FOs along the value chain.; - Agriculture Research station Swat - Agriculture Extension Department - Federal Seed Certification and Registration Department - Professional Farmers’ Organizations/nursery growers’ association. Medicinal and Aromatic Plants (including Saffron); - Capacity building of collectors in specie identification, harvest, postharvest management and marketing. - Establishment of linkages with potential markets/industry. - Supporting private sector investment in MAP nurseries. - Support to industry in system improvement, certification and branding.; - NTFP Directorate. - Certifying bodies, - PFOs - Private sector (processors, exporters etc.). Promotion of seedless citrus; - Strengthening germ plasm of seedless (preferably Valentia, Spain or any other origin) citrus in DI Khan – 20,000 disease free and true to type mother plants - Nursery persons/farmer organizations strengthened for multiplication of certified fruit plants - Capacity building through certified courses for farmers through academia/ extension department; - Agriculture University DI Khan - Agriculture Extension Department - Agriculture Research (Germ Plasm Unit) - Federal Seed Certification and Registration Department - Farmers’ Organizations. Dairy, meat & small ruminant; - Establishing FMD free zone - Organizing dairy farmers into PFOs. - Building their capacity in animal hygiene, nutrition, and management. - Support in establishment of milk collection and sale points. - Mobilizing SMEs for investment in milk processing, pasteurization, and value addition. - Breed improvement for milk and meat. - Support in fattening of animals. - Capacity building of farmers in raring small ruminants. - Support in breed improvement in small ruminant. - Mobilizing private sector in establishment of meat processing and value addition. - Capacity building of butchers in standardized meat cuts and establishment of meat shops. - Support in production of improved fodders. - Market access and linkages.; - Livestock Department - Private Sector - Farmers’ Organization - Youth (as AIT – 100). Mago value chain; - Support in establishment of mango nurseries in DI Khan and adjacent areas. - Support in establishment of commercial mangoes orchard. - Support in establishment of local mango processing industry. - Capacity building and market linkages.; Agriculture Department Private sector Farmer organisations. Honey (Jajuba Flavor); - Capacity building of honeybee keepers in beehives management and bee keeping. - Support in establishment of honeybee farms. - Technological innovation. - Establishment of common facility centers/processing units.; Agriculture Department Private sector Farmer organisations. Ground nut; - Supporting PFOs in introduction of improved varieties. - Introduction of improved technology in harvest and roasting, processing, capacity building and value addition (salting, peanut butters, packing etc.); Agriculture Department Private sector Farmer organisations. - Central Agribusiness Cluster. The cluster will have a focus on the promotion of high value agriculture and intensive production pockets of high value commodities. The cluster will comprise of 8 districts including Peshawar, Mardan, Khyber, Mohmand, Nowshera, Mardan, Swabi, Charsadda . The key interventions will include promotion of; (i) citrus; (ii) fruit (plum, peaches, pears, lychee, strawberries; melons etc.) (iii) high value vertical farming; and, (iv) commercial dairy. Key interventions shall include; Intervention Areas; Activities; Institutional responsibilities. Pome & stone fruits; - Establishment of germ plasm and screen houses. - Support to nursery growers associations/professional farmer organizations for establishment of screen houses, nurseries. - Support to nursery growers in registration and certification of plants and nurseries. - Technical assistance in Capacity building of their workers, technicians etc. - Support to PFOs in establishment of commercial orchards. - Support to farmers and organizations in value addition in fresh, processed, dried. - Mobilizing investment in fruits processing, packaging and export. - Support to farmers and FOs in commercial production of strawberry runners. - Mobilizing investors through grant support for strawberry processing, export.; - Agriculture Research station Swat - Agriculture Extension Department - Federal Seed Certification and Registration Department - Professional Farmers’ Organizations/nursery growers’ association. Citrus (sweet oranges); - Nursery persons/farmer organizations strengthened for multiplication of certified fruit plants already available with ARS Tarnab, Germ Plasm Unit in Sherkhana and Germ Plasm Unit Haripur - Capacity building through certified courses for farmers through academia/ extension department. - Support to PFOs in establishment of citrus orchards. - Support in certification (GlobalGAP, IFS, etc). - Mobilizing private sector investment in establishment of citrus processing units (washing, grading, waxing and pulping, storage etc.); - Agriculture Extension Department - Agriculture Research (Germ Plasm Units/ARS Tarnab) - Federal Seed Certification and Registration Department - Farmers’ Organizations. Dairy Clusters in Peri-Urban Areas; - Establishing FMD free zone - Promoting commercial feed production especially silage/concentrate feed - Promoting quality maize and other fodder including grasses (especially introduction of high quality seed) - Provision of certified training for AI technicians and AI kits and Liquid Nitrogen Container – Self/Employment grant model – linked with government department – 1 per Union Council - Dairy processing (pasteurization) through farmer owned companies/PPPs - Capacity building through certified courses for farmers through academia/ livestock department; - Livestock Department - Farmers’ Organization - Private Sector - Youth (as AIT – 80-100). Commercial fruit industry; - Introduction of adoptable germ plasm units - Adoptive research for seedless grapes - Development - Fruit nursery upgrading to certified and true to type planting material production systems; - Agriculture Research System - Farmers’ organizations and nursery producers. Others; - Identified based on the market studies and business planning exercise to be carried out in the first year of the project implementation.; - Relevant stakeholders. - Northern Agribusiness Cluster. This cluster will have a focus on the promotion of fruits, high value vegetable aromatic plants, fisheries and livestock. The cluster will consist of 7 districts i.e. Bajawar, Dir Upper, Dir Lower, Malakand, Buner, Swat & Shangla. The key interventions will include promotion of; (i) pome and stone fruits (ii) straw berry and straw berry runners (iii) citruses (iv) off season and high value vegetables (v) support and promotion of fruit nurseries (vi) medicinal and aromatic plants (vii) dairy and small ruminants. Key interventions shall include; Intervention Areas; Activities; Institutional responsibilities. Pome & stone fruits; - Strengthening the existing germ plasm units (GPU) and establishment of more GBUs and screen houses. - Support to Nursery persons/swat nursery growers’ associations/professional farmer organizations for establishment of screen houses, nurseries. - Support to nursery growers in registration and certification of plants and nurseries. - Technical assistance in Capacity building of their workers, technicians etc. - Support to PFOs in establishment of commercial orchards. - Support to farmers and organizations in value addition in fresh, processed, dried. - Mobilizing investment in fruits processing, packaging and export. - Support to farmers and FOs in commercial production of strawberry runners. - Mobilizing investors through grant support for strawberry processing, export.; - Agriculture Research station Swat - Agriculture Extension Department - Federal Seed Certification and Registration Department - Professional Farmers’ Organizations/nursery growers’ association. Citrus (sweet organges); - Nursery persons/farmer organizations strengthened for multiplication of certified fruit plants already available with ARS Tarnab, Germ Plasm Unit in Sherkhana and Germ Plasm Unit Haripur - Capacity building through certified courses for farmers through academia/ extension department. - Support to PFOs in establishment of citrus orchards. - Support in certification (GlobalGAP, IFS, etc). - Mobilizing private sector investment in establishment of citrus processing units (washing, grading, waxing and pulping, storage etc.); - Agriculture Extension Department - Agriculture Research (Germ Plasm Units/ARS Tarnab) - Federal Seed Certification and Registration Department - Farmers’ Organizations. Offseason & high value vegetables; - Introduction of improved varieties and new technologies for OS/HV vegetable production. - Grant support to PFOs in establishment of aggregation centers. - Introduction of improved packaging. - Mobilizing private sector investment in vegetable processing i.e chips, paste, ketchup, frozen etc. - Support to farmers in market access and linkages. - Capacity building of FOs along the value chain - Vegetable seed production under certification scheme; - Agriculture Research station Swat - Agriculture Extension Department - Federal Seed Certification and Registration Department - Professional Farmers’ Organizations/nursery growers’ association - FSC&RD. Medicinal and Aromatic Plants (including Saffron); - Capacity building of collectors in specie identification, harvest, postharvest management and marketing. - Establishment of linkages with potential markets/industry. - Supporting private sector investment in MAP nurseries. - Support to industry in system improvement, certification and branding.; - NTFP Directorate. - Certifying bodies, - PFOs - Private sector (processors, exporters etc.). Dairy, meat & small ruminant; - Establishing FMD free zone - Organizing dairy farmers into PFOs. - Building their capacity in animal hygiene, nutrition, and management. - Support in establishment of milk collection and sale points. - Mobilizing SMEs for investment in milk processing, pasteurization, and value addition. - Breed improvement for milk and meat. - Support in fattening of animals. - Capacity building of farmers in raring small ruminants. - Support in breed improvement in small ruminant. - Mobilizing private sector in establishment of meat processing and value addition. - Capacity building of butchers in standardized meat cuts and establishment of meat shops. - Support in production of improved fodders. - Market access and linkages.; - Livestock Department - Private Sector - Farmers’ Organization - Youth (as AIT – 100). Others; - Identified based on the market studies and business planning exercise to be carried out in the first year of the project.; - Relevant stakeholders. - Eastern Agribusiness Cluster. This cluster will have a focus on the promotion of fruits, high value vegetable, fisheries and livestock. The cluster will consist of 7 districts i.e. Haripur, Abbottabad, Mansehra, Battagram, Torghar, Kohistan, Lower Kohistan, Kolai Palas. The key interventions will include promotion of; (i) pome and stone fruits (ii) straw berry and straw berry runners (iii) citruses (iv) off season and high value vegetables (v) support and promotion of fruit nurseries (vi) dairy and small ruminants. Key interventions shall include; Intervention Areas; Activities; Institutional responsibilities. Pome & stone fruits; - Strengthening the existing germ plasm units (GPU) Haripur and establishment of more GBUs and screen houses in Mansehra, Battagram - Support to nursery growers’ of Haripur , Mansehra , professional farmer organizations for establishment of screen houses, nurseries. - Support to nursery growers in registration and certification of plants and nurseries. - Technical assistance in Capacity building of their workers, technicians etc. - Support to PFOs in establishment of commercial orchards. - Support to farmers and organizations in value addition in fresh, processed, dried. - Mobilizing investment in fruits processing, packaging and export. - Support to farmers and FOs in commercial production of strawberry runners. - Mobilizing investors through grant support for strawberry processing, export.; - Agriculture Research station Swat - Agriculture Extension Department - Federal Seed Certification and Registration Department - Professional Farmers’ Organizations/nursery growers’ association. Seedless citrus zone; - Nursery persons/farmer organizations strengthened for multiplication of certified fruit plants already available with ARS Tarnab, Germ Plasm Unit in Sherkhana and Germ Plasm Unit Haripur - Capacity building through certified courses for farmers through academia/ extension department. - Support to PFOs in establishment of citrus orchards. - Support in certification (GlobalGAP, IFS, etc). - Mobilizing private sector investment in establishment of citrus processing units (washing, grading, waxing and pulping, storage etc.); - Agriculture Extension Department - Agriculture Research (Germ Plasm Units/ARS Tarnab) - Federal Seed Certification and Registration Department - Farmers’ Organizations. Offseason & high value vegetables; - Introduction of improved varieties and new technologies for OS/HV vegetable production. - Grant support to PFOs in establishment of aggregation centers. - Introduction of improved packaging. - Mobilizing private sector investment in vegetable processing i.e chips, paste, ketchup, frozen etc. - Support to farmers in market access and linkages. - Capacity building of FOs along the value chain.; - Agriculture Research station Swat - Agriculture Extension Department - Federal Seed Certification and Registration Department - Professional Farmers’ Organizations/nursery growers’ association. Dairy, meat & small ruminant; - Establishing FMD free zone - Organizing dairy farmers into PFOs. - Building their capacity in animal hygiene, nutrition, and management. - Support in establishment of milk collection and sale points. - Mobilizing SMEs for investment in milk processing, pasteurization, and value addition. - Breed improvement for milk and meat. - Support in fattening of animals. - Capacity building of farmers in raring small ruminants. - Support in breed improvement in small ruminant. - Mobilizing private sector in establishment of meat processing and value addition. - Capacity building of butchers in standardized meat cuts and establishment of meat shops. - Support in production of improved fodders. - Market access and linkages.; - Livestock Department - Private Sector - Farmers’ Organization - Youth (as AIT – 100). Others; - Identified based on the market studies and business planning exercise to be carried out in the first year of the project implementation.; - Relevant stakeholders. - Chitral Natural Agribusiness Cluster. This cluster will have a focus on the promotion of fruits, high value vegetable aromatic plants, fisheries, and livestock. The cluster will consist of 2 districts Chitral upper and Chitral lower. The key interventions will include promotion of; (i) pome and stone fruits (ii) straw berry and straw berry runners (iii) citruses (iv) off season and high value vegetables (v) support and promotion of fruit nurseries (vi) medicinal and aromatic plants (vii) dairy and small ruminants. Key interventions shall include; Intervention Areas; Activities; Institutional responsibilities. Pome & stone fruits; - Support nursery growers’ professional farmer organizations for establishment of screen houses, nurseries. - Support to nursery growers in registration and certification of plants and nurseries. - Technical assistance in Capacity building of their workers, technicians etc. - Support to PFOs in establishment of commercial orchards. - Support to farmers and organizations in value addition in fresh, processed, dried. - Mobilizing investment in fruits processing, packaging and export. - Support to farmers and FOs in commercial production of strawberry runners. - Mobilizing investors through grant support for strawberry processing, export.; - Agriculture Research station Swat - Agriculture Extension Department - Federal Seed Certification and Registration Department - Professional Farmers’ Organizations/nursery growers’ association. Offseason & high value vegetables; - Introduction of improved varieties and new technologies for OS/HV vegetable production. - Grant support to PFOs in establishment of aggregation centers. - Introduction of improved packaging. - Mobilizing private sector investment in vegetable processing i.e chips, paste, ketchup, frozen etc. - Support to farmers in market access and linkages. - Capacity building of Fos along the value chain.; - Agriculture Research station Swat - Agriculture Extension Department - Federal Seed Certification and Registration Department - Professional Farmers’ Organizations/nursery growers’ association. Medicinal and Aromatic Plants; - Capacity building of collectors in specie identification, harvest, postharvest management, and marketing. - Establishment of linkages with potential markets/industry. - Supporting private sector investment in MAP nurseries. - Support to industry in system improvement, certification, and branding.; - NTFP Directorate. - Certifying bodies, - PFOs - Private sector (processors, exporters etc.). Wool and woollen products; - Training of farmers in sheering of sheep - Training of artisans in yarn making - Woolen shawls, sweaters, caps etc. production training - Supporting private sector investment in establishment of woolen products’ display centers - Support in developing market linkages; - Livestock Department - Private sector - Farmers’ organizations. Nuts; - Farmers’ training in harvest and post-harvest management of nuts including cracking, grading, packing, oil expelling etc. - Support in establishing processing facilities at PFO level - Introduction of improved packing - Establishing market linkages - Establishment of temperate fruit nurseries with PFOs; - Agriculture Department - Private Sector - Farmers’ organizations. Small ruminant; - Capacity building of farmers in raring small ruminants. - Support in breed improvement in small ruminant. - Mobilizing private sector in establishment of meat processing and value addition. - Capacity building of butchers in standardized meat cuts and establishment of meat shops. - Support in production of improved fodders. - Market access and linkages.; - Livestock Department - Private Sector - Farmers’ Organization - Youth (as AIT – 100). Others; - Identified based on the market studies and business planning exercise to be carried out in the first year of the project implementation.; - Relevant stakeholders. Note: Fisheries production (cold & warm water) will be strengthened in all regions wherever potential exist. - The activities of the project are organised into four mutually reinforcing sub-components: (i) Professional Farmer Organizations, (ii) Public-Private-Producers Partnerships - 4Ps, (iii) Farm Services Companies, and (iv) Institutional support services (performance-based engagement with departments and services providers). Note: Please refer to Section V. Technical Requirement/Guidelines for Implementing of Component 1 – Agri-business Promotion of PIM Volume II for details description, eligibility criteria, farmers mobilisation process, business planning and selection and roles and responsibilities of Business Mobilisation Partners (BMPs). #### Sub-Component: Development of Professional Farmer Organizations (PFOs) - One of the reasons that the agriculture sector’s performance is far below its potential is that small farmers, which are the backbone of the sector, are not organized as formal groups. The project will assist smallholders in formation of PFOs to promote agribusiness activities in rural areas, consolidate/aggregate production base for market/private sector demand, and leverage private investment in agribusiness value chains. Since the public extension services has traditionally focused on major crops and food security thus these institutions had remained under-capacitated regarding effective promotion of agribusiness, market development and engaging with private sector. It is therefore necessary to engage service providers/Business Mobilization Partners (BMP) which will be engaged for facilitating implementing component 1. The BMP will provide necessary technical assistance in the form of mobilization, incorporation, business planning, coaching, mentoring, capacity building, matchmaking, product development etc. necessary to develop the business model. The scope of work/role of BMP is detailed in the PIM. - Key activities under the sub-component include; (i) mobilisation of farmers; (ii) registration of PFOs; (iii) business development planning; and (iv) leveraging investment in PFO business proposal. A total of 550 professionally managed PFOs will be established and made sustainable by year 6 of the project to meet the demands of the markets. A typical PFOs will have an average of 400 farmers as members/shareholders. The PFOs will be involved in multi-purpose/multi-product businesses aligned with the local farming systems. The PFO will be open to growth/membership expansion and investment by farmers and non-farmers in the village. Villages/valleys/cluster will be identified by BMPs, in line with demand and potential of the farmers to meet the demand characteristics, availability/willingness of the required numbers of famers (400 farmers or more), and potential for nutrition-sensitive commodities. - The mobilization process undertaken by BMP in the identified cluster, will involve: (i) organizing farmers into PFO; (ii) diagnostic study to assess the potential for upgrading and gaps with regards to meeting demand and to identify potential interventions and understand contextual factors for project implementation etc.; iii) market appraisal, to plan development of agribusiness and establish the baseline for outcome indicators that can be measured to understand the anticipated changes; and (iv) prepare a business development plan with five (5) year projections on various aspects with clear breakeven-point expected preferably within 3 years’ time. The business development plan will include investments in technology/agribusiness development, skills development and cost of the professional management. The FPO business plan will be reviewed by the PMU through a panel of experts and will be subject to no objection provided by IFAD. - To be eligible for project support, a PFO will be supported by BMP to: (i) become a legally registered entity either under the Cooperative Societies Act, 1925 or the Companies Act, 2017 or the proposed Farm Services Act; (ii) have at least 70% of its membership comprising smallholders; (iii) comprise farmers that are producers of a commodity/commodities falling under the nutrient-rich sources of food, such as animal source foods, fruits, vegetables, beans and pulses; (iv) agree on leveraging investment and; (v) be jointly liable under contract signed with project; and, (v) agree to manage PFO through professional staff. - The FPO will facilitate upgrading farm practices and functions of members including input supply, production technology, packaging, marketing, handling etc. as well as bridge the services gaps related to insurance, technical skills, networking accessing services of government line departments, financial institutions and private sector. The PFOs will also be responsible to aggregate the products, and facilitate in grading, processing, packaging and to ensure the sale as per business plan and the establishment of contracts for this purpose. In addition, PFOs with support from relevant line departments (to be engaged through performance-based MoU) and shall strive to facilitate farmers in obtaining certification (Global GAP, HACCP, BRC, ISO 22000, FFS etc.) for the farmer produce particularly for exportable items to guarantee the best added value for the selected commodities. - The PFOs’ net profit will be limited to the operational cost and transfer most of the profit to member farmers. The project will channel project assistance to FPOs through formal banking sector, thus building credit history for both FPOs and their members. This will enable FPOs/smallholders to access credit through formal banking system to avail opportunities for business expansion in the future. - All value chains that support dietary diversity, nutrition and incomes will be eligible (e.g., livestock, crops, vegetables, fruits, etc..), with a prioritization of those with high nutrition impact, subject to the condition that the business plan demonstrates market demand, the profitability at individual and organizational levels, and sustainability. Based on need, line departments and FSCs may provide technical support to the PFOs. These PFOs will also be entry points for nutrition education especially for women producers and will use labelling/branding with nutritional content dissemination among consumers as well. In coordination with WFP/FAO and through other contracted service providers, nutrition education will be delivered through: (i) the women membership, especially on maternal and child nutrition; and (ii) to the male membership on good nutritional habits and dietary diversification. While curriculum will be overlapping, the two groups will be trained separately considering the requirements of the social context and cultural norms. - The PFO business plans will also include investment in climate action i.e., adaptation and mitigation as appropriate. All identified investments by PFOs, 4Ps and FSCs will be subject to environment and climate screening. Business plans for PFOs will include costed adaptation and mitigation measures as provided in ESMP to avoid or minimize any negative social, environmental and climate change impacts (see PIM). In general, interventions will have positive impacts. - Cost and Share for financing: Subject to fulfilment of eligibility criteria, the project will finance the PFOs (investment and working capital) in the range of PKR 10 – 15 million depending on the number of members in PFO. Beneficiaries will contribute 30% of the total cost of the business proposals. Depending on the ability of FPO, the contribution of beneficiaries could either be shared as lumpsum or as instalments aligned to milestones. This would be agreed in the terms of partnership for establishment of PFO. The project investment will be to finance the investment and working capital requirements determined in the PFO’s business plan. The project investment will be grant to the PFOs for in turn on-lending to members in the form of cash or in-kind of technology and inputs. A scheme for repayment will be necessary condition to be developed by the PFO as part of the business plan keeping in view the applicable regulatory framework. - Implementation Arrangements: Experienced Business Mobilisation Partners (BMPs) will be engaged for implementation following Quality and Cost Based Section (QCBS) method following Khyber Pakhtunkhwa Public Procurement Regulatory Authority (KP-PPRA) Rules, to the extent of their consistency with IFAD's Project Handbook & Procurement Guidelines, Financing Agreement and Letter to the Borrower (LTB). The BMPs will be responsible for mobilization of members (farmers), legal incorporation/registration, development of business plan, facilitate recruitment of professional staff and implementation of the business plan and capacity building. The BMP will provide coaching support in all the business and technical aspects of PFOs, ensure good governance practices and facilitate audit of each PFO for the first 2 years. Formal joint staff assessment will also be carried out every semester using international best practices using FO’s maturity index. - Beneficiaries: This sub-component will directly reach and provide decent revenue, employment and access to services and resources for 220,000 HHs. The sub-component will generate additional employment opportunities in services like PFO management, grading, processing, storage, transport and consolidation services. #### Sub-Component: Development of Public-Private-Producers Partnerships (4Ps) - The objective of the subcomponent is to promote value chain development particularly for high value crops, livestock and fisheries. The project will develop 20 Public, Private Producers Partnerships (4P), with an average of 2 000 producers per partnership. The project will make a call for proposals, open to local, national and multinational private firms/companies already in the business and having the financial capacity as well as demonstrated market share. - The 4P model involve cooperation and partnership between public private (promotors) and small-scale producers, who agree to work together to reach a common goal or carry out a specific task while jointly assuming risks and responsibilities and sharing benefits, resources and competencies. It is a holistic win-win platform where multiple partners could leverage their investment in selected value chains led by private companies facilitating access to markets, knowledge, technology and capital for smallholder rural poor farmers. In addition, such platforms could create employment opportunities in rural areas as such jobs would perform as value chain actors within the same business ecosystem. - The project will encourage; private agribusiness companies/SMEs who are already established in the province/country with prior experience of working with individual farmers/FOs/PFOs or with indirect/direct presence in the province through other means by sourcing, value addition and creating market linkages. These entities would act as “promoters” under 4Ps. The underlying principles of these partnerships should be to maximize the incremental income of farmers and integrate them in the selected value chains. PMU would act as the initiator to invite expressions of interest (Call for Proposals) to engage private agribusiness companies/SMEs in 4Ps, that will be short listed and selected based on a set of criteria and commitment and interest in pro-poor development. The selected partners will subsequently be requested to submit proposals in the form of Business Development Plans (BDP) which will include an investment plan and an implementation plan. The BMP will be responsible for preparing BDP working closely with the company’s/SME and farmers/PFOs (reassuring financial and economic benefits to farmers). BMPs will also be responsible for promoting, sensitizing and brokering match making/engagement and a first contact with the partners. As the process progresses, the BMP will continue its brokerage role, facilitate negotiations and fine-tuning of the proposals. - The investment needs assessed for each 4Ps is on average PKR 50-70 million, which will be contributed on a 50:50 basis between project and private sector, dedicated for the investment in the business model. Project investments will only be meant for small holder producers to enable them to better respond to the demand (mainly production in quantity/quality /regularity) of the private sector. A contract spread over five-years or more will be established between the private sector, the project and the farmers, which will establish the terms and conditions of the partnership. - The private company will ensure the extension and technical support, the collection of the product as well as marketing. Producers’ capacities will be built to meet the demand characteristics and requirements of the private company for which project investments will be identified and provided. The 4Ps model could/will also be developed as a link to the PFOs under contract farming modality. All payments will be gradually digitalized through formal banking sector institutions. The process of evaluation and approval of proposals will be done by an evaluation committee (appraisal panel) established by the PMU and consisting of at least 3 experts from private sector i.e., technical, financial and marketing based on approved criteria. The criteria against which the proposals will be reviewed shall include assurance of the market potential, benefits and income to the target group, nutrition/dietary diversity consideration, gender, sustainability of the proposed activities, climate resilience and impact, etc. To reduce the risks and impacts associated with climate change, the project will build farmers’ capacity to assess climate risks, plan and identify suitable climate adaptation/mitigation action –as appropriate (including technology, insurance etc.). The identified climate actions, once implemented, will help farmers to cope with extreme climatic events, notably drought and water shortages. - Beneficiaries: This sub-component would directly benefit 40,000 small-holder producers of agriculture and livestock products. - Cost and Share for financing: The project funding will support the implementation of the business or investment plan pertaining to small-holder farmers. This funding will be on a matching grant basis at approximately 50% of the total investment cost of the 4P’s projects contributed by the participating private sector and farmers. The capex (capital expenditure) grant support in the 4P’s is PKR 78,000 (USD 500) per farmer/beneficiary or with a maximum allocation of PKR 78 million (USD 500,000) per 4P. The project will make investments in smallholder farmers to meet the demand of the participating private company in terms of quantity, quality and national/international standards. - Implementation Arrangements: The Business Mobilisation Partners (BMPs) will be responsible for the development of business plans (BDP) closely working with the company’s/SME and farmers/PFOs to ensure financial and economic benefits for the farmers. BMP’s will also be responsible for promoting, sensitizing and brokering, scouting, matchmaking/engagement and ensuring contractual agreement among participating partners. The PMU will be responsible for appraisal of each 4Ps proposal and seeking no objection from IFAD. #### Sub-Component: Reorganising Farm Service Centres as Farm Services Companies - The Government of Khyber Pakhtunkhwa has been investing in the development of the Farm Service Centres (FSC) with the objective: (i) to safeguard farmers rights and interests; (ii) enhance farmers knowledge and skills; (iii) boost the modernization of agriculture; (iv) increase crop yields; (v) improve farmers livelihood; (vi) develop rural economy; (vii) provision of certified seed, fertilizers, animal husbandry services, quality veterinary health care services and medicines, farm machinery, expertise and technology for the provision to the members on affordable rates; (viii) provide or extend the facility of loan to the members; (ix) facilitate access to facilities of laboratories; and (x) marketing arrangements for all types of surplus produce at Centres. - The project, building on the experience from the Farm Service Centres (FSC), will reorganise these institutions to become farm services companies enabled to be more responsive to the needs of the farmers in terms of input supply (fertilizers, seeds, pesticides etc.) and services (mechanized labour, technical advises, certification and marketing etc.) and to complement and fully operationalise the subcomponents I. II (PFOs) and I.II (4Ps). The objective will be to restructure and reorganise selected existing model farm services into fully functional, autonomous and sustainable Farm Service Companies (FSCs) one each per district/valley, with PFOs and individual farmers as shareholders. The reorganised FSC will be registered under the companies act and managed as a private company. - The FSCs would act as hubs for knowledge and technology dissemination as well as marketing of the agricultural and livestock commodities in order to facilitate the members. The FSCs are envisaged to enhance agricultural productivity of PFOs and other farmers. - The FSCs will be strategically identified to cover all the geographical zones/regions of the project. In total 35 FSC will be supported with an average of 1000 – 2000 farmers as shareholders and an expected outreach/market to be serviced of 20,000 famers per FSC. FSC may establish branches/franchisee/agents’ network in their respective territories or beyond. - Cost and Share for financing: Based on business plan, each FSC will have 50% matching investment by the project of which not more than 5% could be utilised for the administrative and operational cost, whereas 95% will be used as a working capital. Of the initial investment 50% will be contributed by shareholders/member farmers. It is anticipated that based on the first year of operations, the FSC would be able to leverage commercial sources of financing from the second year of its operation. The FSCs are expected to become financially self-sufficient in the fourth year of operation and operational self-sufficiency by the third year. - Beneficiaries: In addition to the direct benefits to the members of the PFO and framers involved in 4Ps (285,000), the sub-component together with Institutional Support Services (subcomponent 1.4) will benefit additional 415,000 small farmer HH of the province through its services. - Implementation Arrangement: The business mobilisation partners (BMPs) will be responsible for the undertaking a market assessment/rapid market appraisal, develop business plan, suggest FSC management system, undertake registration of the FSCs as companies, assist in hiring of professional staff and support implementation of the business plans. In addition, the BMPs will also be responsible for hand holding, coaching, process improvement and ensure the good governance practices in terms of audit and statutory compliances. The formal joint staff assessment will also be carried out every year. #### Sub-Component: Institutional support services - The main objective of the sub-component is to provide demand driven institutional services to PFOs/4Ps/FSCs, to meet the market demand and buyers’ requirements. The PMU will enter into multiple results based MoUs with the relevant public/Government departments (academic, research and extension services) for different activities with clear responsibilities and deliverables. The scope of work will emerge from the aggregated needs of PFOs/4Ps/FSCs and will be translated into work plan, timeline and cost estimates. The engagement plan will be developed by PMU and approved by PSC as and when the need arises on a rolling out basis. Performance assessment will be done on an annual basis and presented for review to PSC. Below is not an exhaustive list of potential institutional services but are typical needs assessed during project design; - Directorate of Agriculture Extension: (DAE): Based on the need assessed, PMU will engage for provision of support regarding training and advisory services (using existing App), - Directorate of Agriculture Research (DAR): The project will engage Additional collaboration will be in the areas of reforms related to seed/planting material import and multiplication and other related policy domains. - Additional/Other Partnerships: Several other MoUs may be executed as per the need with different institutions. The terms of partnership will include investment in capacities of the institutions, delivery of the services and overheads. ### Component 2: Skills Development and Employment Promotion - The objective of the component is creation of productive employment and self-employment opportunities for 110,000 rural women and men in the farm, off farm and non-farm sectors. The component approach will focus on employability for employment and self-employment/entrepreneurship in agriculture and other emerging sectors in the province through a range of activities tailored to the needs and interests of different target groups. The project design recognizes that in order to effectively engage rural people, an innovative, dynamic and integrated investment approach is required to create the right incentives for productive engagement of rural people, to address their growth challenges. The project approach provides for competency-based training including opportunities for business development skills, managerial capacity building and promoting non-cognitive skill building; apprenticeship for on-the-job training; mechanism for public private partnership for job placement; and linkage for access to financial services for start-up for self-employment. - The Skills Development and Employment Promotion Component consists of three mutually supporting sub-components: (i) Skills Development for Agribusiness; (ii) Employment promotion and self-employment/enterprise development and (iii) Job placement of young unemployed graduates. The Subcomponent II.I: Skills Development, will ensure that all the skills required for achieving successful Agribusiness Development (component 1), particularly for establishment and operation of Professional Farmer Organisations, Public, private and producers Partnership (4P) and Farm Services Centres, are available locally and adopted to ensuring institutional and business sustainability. The sub component II.II Employment promotion and Enterprise Development, will complement the agribusiness initiatives of the project in terms of the opportunities for rural off farm and non-farm employment and services preparing for young women and men to engage in provision of such services through their own private business and services. Support will also be provided through vocational training and apprenticeship to respond to the labour supply gap for the emerging sectors of the province like hospitality/tourism, health technicians, construction, manufacturing and mining. Subcomponent II.III will support unemployed graduates for enhancing their employability through internship programme in public and private institutions which will allow them to gain hands-on training and benefit from the opportunities created under agribusiness Component and/or to respond to the existing job market or business gaps in their respective rural areas. The subcomponent II. I and II.II will be implemented by KP-TEVTA/UET PESHAWAR and its subordinate training institutions/facilities directly or through outsourcing in case of; (i) non availability of courses, (ii) lack of facilities and (iii) geographical areas with no outreach by TEVTA. Training services providers will be engaged through MoU with public sector or through competitive selection process as appropriate. - Target Group: The main target group of the component will be the poor household in BISP-PSC band of 0-34. Additionally, unemployed and fresh graduates from poor families will be provided support for job induction as an opportunity for enhancing their employability. BISP-PSC criteria will be the main instrument for selection of beneficiaries. However, since the updated BSIP-PSC data is not yet available, the selection of beneficiaries by the project will be validated by village/tehsil councils or through the village organisations (where registered and functional one exist). - Within the main groups, the small farmers and youth supported by the project will broadly fall into the following main categories: - Famers young women and men looking for opportunities for remunerative livelihoods through employment and self-employment/micro and small enterprises and services opportunities created as a result of agribusiness development and the emerging sectors of the province. The successful beneficiaries of vocational trainings desiring to pursue self-employment/enterprise development based on demonstrated interest and capacity, will be supported through start-up capital from project resources and/or through linkages with private banks for accessing the government interest free and soft loans for Youth Entrepreneurship Scheme (YES)/Kamyab Jawan. - Successful trainees pursuing employment will be offered apprenticeship opportunities in collaboration with private sector entities. - Graduate from local faculties who require further employment skills development through on the job training/internship in their education qualification related trades particularly agriculture and food sector to improve their employability skills. The graduates who after the internship, wish to set up businesses/enterprise development will be supported through facilitating access to inter free/low interest loans under the Kamyab Jawan youth enterprise development schemes. - A combination of vocational training, access to interest free/low interest loans, apprenticeship and internship packages will be offered for different sub target groups. The following table summarises the target groups, indicative types of interventions/training and implementation arrangements. Table 1: Target Group, Indicative Type of Training and Implementation Arrangements Target Group/ PSC Range; Sectors; Intervention Type; Implementation. 0-34 Professionals, Small farmer, with 30% each of youth and women; Farm, business development; (sub-component II.I). Technical, financial, managerial or business skills development required for enhancing crop quality and quantity, institutional development, sustainability and profitability of institutions under Component 1: Agribusiness Development – 25,000; KP-TEVTA or outsourcing to public sector institutions like ATI. AHITI, Universities (Agriculture/Engineering/Livestock) or by hiring relevant training providers (firms or qualified individuals as appropriate).. 0-34 Youth women and men with 50% women; Emerging sectors: (construction, hospitality, manufacturing, health, mining etc.); (Subcomponent II.II.a) Vocational skill including soft skills development (skills that run the entire range from life skills to workforce skills, applied skills, personal skills, interpersonal skills and non- cognitive skills)-18,000. Apprenticeship support in private organisations for skills training attractive for potential trainees and meeting the demands of the emerging sectors supply gap.; KP-TEVTA. Farm, off Farm and non-farm Services and enterprises; (sub-component II.II.b) Vocational skills training for self-employment and youth enterprise development. Start up support either in kind or capital as appropriate to the trade from project resources and linkages to interest free and low-cost loan under Kamyab Jawan youth enterprise development and business incubation etc.; KP-TEVTA & Service Providers. 0-40 (includes transitory non-poor); Graduates and above; (sub-component II.III) Employment skills required for agriculture and rural sector professional service or self-employment through internship for hands-on training. Could also include self-employment for services like processing, food manufacturing, logistics, trading, animal health and reproduction, nurseries, pruning and pesticide application etc. Also linked to Kamyab Jawan low interest loan schemes; Private Service Providers through public and private institutions and businesses.. Note: Sectors/sub-sector will be assessed through job market study and outlook to be undertaken by TEVTA with the support the project. #### 2.1. Sub-Component 2.1: Vocational and Technical Skills Development - The objective of the subcomponent is to create skills among 60,000 persons for employment and self-employment opportunities with a focus on ultra-poor and poor households with limited access to land with a specific focus on women (50%) and youth (50%). Preference, particularly for self-employment, will be given to youth women and men on their poverty score among the band of 0-34. The component will be implemented by KP-TEVTA/UET PESHAWAR, other public and private service provider(s)/partners. - A special partnership will be developed with KP-TEVTA/UET PESHAWAR, and support provided to ensure implementation of vocational training within the parameters of project design. TEVTA will be supported to assess and adapt to the most recent market requirements in terms of training and / or to add additional demand-based trainings to their existing trainings. TEVTA will also be supported to develop partnerships with local industry/entrepreneurs/businesses for assessing demand and developing apprenticeship for job placement. In addition, KP TEVTA shall be supported in establishing partnership with public and private service providers to design and deliver the trainings currently not available at TEVTA. - Within the framework of the project design and under the overall supervision of PMU, the implementation arrangements will include: - Training of 60,000 youth men and women and provision of apprenticeship support to 18,000 trainees will be the responsibility of KP-TEVTA/UET PESHAWAR through on-going ADP schemes. The PSC will provide necessary modifications and flexibility, if required, to align the existing ADP programmes with the project framework and approach. - In case of non-availability of the market demanded courses and training identified at KP-TEVTA/UET PESHAWAR own institutions, KP-TEVTA/UET PESHAWAR will organise such courses through outsourcing to public or private service providers or qualified individuals. - KP-TEVTA/UET PESHAWAR will also ensure organising training for women at local level where the women could conveniently commute on daily basis, either through its own institutions or by engaging suitable public and/or private service providers. - Based on institutional assessment, availability of necessary facilities and outreach, the Directorate of Social Welfare Merged Areas could be one such pre-identified public sector service provider for vocational training of young women and men for employment and self-employment in the Merged Districts. The Directorate of Social Welfare Merged Areas will be engaged by KP-TEVTA/UET through a MOU. KP-TEVTA/UET will provide financing for training of women through the leveraged ADP funding, while financing of start-up capital will be provided by PMU through service provider. The trainees shall be awarded certificates by KP-TEVTA/UET. The number of beneficiaries and financial requirements will be determined mutually by the Directorate of Social Welfare Merged Areas, KP-TEVTA/UET and PMU. The project will explore the possibility of linking women groups with end markets and possibly using 4Ps model for supporting trainees of the Zakat-Usher, Social Welfare, Special Education and Women Empowerment Department as well as initiating social enterprise in support of the training centres under the department. - An amount of PKR 0.468 (USD 3 million) shall be allocated by KP-TEVTA/UET from the leveraged ADP schemes for outsourcing specialized trainings currently not offered by KP-TEVTA/UET and local level trainings for women where KP-TEVTA/UET has no outreach. - Institutional Services and Technical Support Provider(s): The key technical support areas identified are; (i) market assessment and release of job market outlook on a continual basis to enable adoption of training programme; (ii) updating curricula relevant to project needs and most demanded skills (at least 5); (iii) capacity building of instructors in delivery of training; (iv) establishing training hubs (3 hubs linked to economic zones, product clusters and emerging sectors); and, (v) policy reforms related to testing and certification. The technical support needs will be assessed once the job market assessment is completed. The PMU will develop scope of work and will engage one or several technical service providers for training mainly for thematic and geographical areas which are not currently covered by TEVTA. Selection of service providers will be undertaken following competitive process while public sector institutions may be engaged through a performance-based MoU. - Implementation of start-up capital and business development support/business incubation for self-employment (subcomponent II.I.b) and implementation of Job Placement for Graduates (subcomponent II.II) will be undertaken though technical service providers. - The identification of trainees will have three approaches; (i) demand driven regular intake by TEVTA; (ii) intake through the Social Welfare Department - women empowerment linked to women centres in merged districts; (iii) needs identified by service providers in areas not covered by TEVETA to enhance outreach. The service provider(s) will particularly assist KP-TEVTA/UET PESHAWAR in implementation of training of women at local level who have cultural constraints of mobility. The overall coordination and oversight will be provided by PMU. The PMU will also facilitate the linkages between the service provider and private banks for provision of interest free and low-cost financial services of the federal and provincial government. In this regard formal MOUs will be signed between the PMU/service provider and private banks. - The service provider will work closely with Village/Tehsil Council to facilitate identification of trainees using BISP-PSC (band of 0-34 on priority). The service providers will also develop partnership (with public, private and civil society organisations) for the job induction programme. - Each service provider and MoU partners will have a 3-year framework contract/result-based MoU renewable based on performance assessment undertaken every year. The service provider(s)/partner(s) will handle aspects related to both employment / self-employment and job induction. In areas where the service providers will not be able to obtain the GoP NOC to intervene, the PMU through its regional office will directly intervene using its own staff and line departments. - The beneficiaries pre-identified (using PSC data obtained from BISP) by the service provider(s)/partners will be validated by Village/Tehsil Councils and PMU after necessary due diligence. - The KP- RETP M&E staff as well as periodic external evaluations will inform adjustment in the approach. - Skills Development for Agribusiness. The overall objective is to provide purpose based training to 25,000 persons (professionals and farmers with focus on youth and women from rural areas - 30% at minimum) to ensure availability of staff and workforce required for achieving successful Agribusiness Development (component 1), particularly for establishment and operation of Professional Farmer Organisations, Public, private and producers Partnership (4P) and Farm Services Centres, are available locally and adopted to ensuring institutional and business sustainability. - The trained workforce will particularly assist the establishment and successful operationalization of: (i) the 550 Professional Farmers Organizations; (ii) the 20Public-private-producer partnerships; and (iii) the 35 Farm Service Companies. The implementation of the Subcomponent will follow the business development and capacity building plans for each FPO and FSCs in progressive and phased manner under component I. Training curricula will include a general orientation on nutrition, social, environmental and climate change in addition to technical theme. - Implementation Arrangement/Training Providers for Agribusiness Training: KP-TEVTA/UET PESHAWAR will be responsible for implementation of the subcomponent either in its own public sector institutions or in case of non-availability of courses, through outsourcing to public sector institutions like Animal Husbandry In-Service Training Institute (AHITI), Agriculture Training Institute (ATI), Universities (Agriculture/Engineering/Livestock) or by hiring relevant training providers (firms or qualified individuals as appropriate). Based on the training type and need, several performance based MoUs may be signed with training providers. The trainees will be tested and certified through these partnerships. The BMPs will be responsible for skills need assessments and selection of trainees as part of the business development planning process and will ensure that assessment is based on (i) needs identified and requested by PFOs, participants of 4Ps and FSCs after their establishment; (ii) the BMP own needs assessment for PFOs, 4Ps or FSCs; (iii) the guidance and needs identified for capacity enhancement of small farmers/members of PFOs/4Ps by participating private business partners/companies; and, (iv) need for skilled service providers. The maximum (all-inclusive) cost of training per individual is estimated at PKR 17,000 (USD 100). - Financing: The subcomponent will be financed from Component 1: Agribusiness Development - The KP- RETP M&E staff as well as periodic external evaluations will inform adjustment in the approach. - Following is the summary of the estimated workforce to be trained for agribusiness related interventions in RETP; Table 2: Estimated Number of Potential Workforce Type; PFOs; 4Ps; FSCs; Service Providers; Total. Staffing Need; 2 750; 400; 280; 3 430. Workforce Need; 19 250; 1 200; 875; 260; 21 585. Total; 22 000; 1 600; - 155; 260; 25,015. - Employment Promotion. Out of the trained 60,000 persons, employability of 18,000 youth trained by KP-TEVTA/UET PESHAWAR will be improved through apprenticeship programme for responding better to the supply gap in emerging sector in the provincial, national or international markets. The emerging sector include, in the context of KP, hospitality/tourism, construction, manufacturing, health care, mining etc. as well as demand for rural trading and other community services. - To address the key current challenges in terms of the quality of trainings, demand and supply gaps in labour market, and improved employability skills to meet the requirements of the employers in public and private sectors, the project provides for an approach consisting of: - Respond to market demand through competency based vocational training (CBT) - a learning approach that is based on trainee’s demonstration of interest and the knowledge and the skills that they are expected to learn. The project will assist KP-TEVTA/UET PESHAWAR for adopting CBT models for project beneficiaries, and for institutionalization and scaling up this methodology for trainings within KP TEVTA. As part of the identification and selection process, the potential trainees, will be assessed and assisted by the service providers/VOETOs engaged under the subcomponent, in selection of training courses based on willingness, qualifications and potential. - The vocational training curriculum will include soft skills development that run the entire range from life skills to workforce skills, applied skills, personal skills, interpersonal skills and non- cognitive skills. - Apprenticeship support for successful trainees will be provided by enhancing the current NAVTTC and KP-TEVTA/UET PESHAWAR apprenticeship programmes in public and private sectors institutions/enterprises for on-job training. KP-TEVTA/UET PESHAWAR in collaboration with private sector forums like chamber of commerce and trade, enterprises and businesses will put in place a system for consultations on demand-based trainings and job placement of the trainees. The selected VOETOs will also be supported for job placement initiatives at local rural areas. - Trainings for women will be organised at local level due to restricted mobility and cultural constraints. - Training and apprenticeship for employment (18,000 trainees) will be financed through leveraging existing Public Sector Development Programme/Annual Development Programme under KP-TEVTA/UET PESHAWAR. In line with the on-going TVET programme of KP-TEVTA/UET PESHAWAR an amount of PKR 10,000 (USD 64) will be paid per month for three to six months apprenticeship. - The type of skills to be acquired will vary and could cover different sectors depending on the gender, specific demands in each district, and its business/labour comparative advantage/demand with focus on emerging sectors of hospitality/tourism, health sector technicians, construction including heavy machinery operators, manufacturing and mining. #### Start-up capital for self-employment/enterprise development - Vocational and Entrepreneurial trainings will aim at developing sustainable and profitable businesses for rural youth. It is expected that 42 000 youth women and men with demonstrated interest, willingness and capacity will be supported to become self-entrepreneurs in fam, off farm and non-farm sectors with the support of a start-up package and coaching, in addition to vocational skills development under Subcomponent II.I a. The start-up package will include provision of in kind or capital resources whichever is deemed essential for the trade and coaching/mentoring support. The coaching support will include business development and planning, financial education, financial management, market access and access to existing financial services and business incubation in the form of hand holding during the initial period of enterprise/business establishment. Based on recent experience an estimated average start-up support amounting to USD 300 per person is required for an expected average income of USD 180 to USD 200 per month. - The type of skills to be offered and acquired will vary and could range between different sectors depending on the gender, district specific demand and its business/labour comparative advantage / demand. Vocational and Entrepreneurial training will be provided in order to develop sustainable and profitable business. The trades for self-employment/enterprise development could include but not limited to, mechanics, tailoring, shoe or handicraft production, beauty shop, mobile or solar panel repair, masonry, carpentry, hostelry, cloth design, electricity, steel fixing, plumbing, etc.) – see list of the 49 activities proposed in PIM. - The start-up support will also be augmented through linkages with banks for accessing the federal government interest free and low-cost loans for youth enterprise development under the Kanya Jawan programme. The project will particularly provide assistance for ensuring financial inclusion of the poor HH in BISP-PSC category 0-34 who are considered non bankable either because of collateral requirements or they do not meet the “ability to repay” criteria, through (i) brokering with the federal government Kamyab Jawan programme, GoKP and banks for attractive loan conditions the target group and (ii) in consultation with the banks devise a mechanism for institutional collateral by the project and/or social collateral by the existing registered community/village organisations. The province is among the pioneers in participatory and community level development approaches where a number of NGOs/RSPs are covering almost all the districts of the province through a network of more than 50,000 community organisations, which could service as social collateral for access to formal financial services. - Training for all the 42,000 trainees will be provided by KP-TEVTA/UET PESHAWAR through leveraging on-going ADP programme. The private service providers engaged by the project will be responsible for selection and assessment of trainees against the target (42,000), provision of start-up capital, and business incubation support trainees for self-employment. - IFAD financing for the start up support will be used in the initial 2-3 years of the project to generate evidence of sustainable job creation under the project. In the meantime, KP-TEVTA/UET PESHAWAR with support from PMU and approval of PSC, will prepare and approve an ADP scheme containing a mechanism for providing start-up capital to trainees who require it for self-employment by way of wider replication of this successful approach. #### Job placement/Induction - Pakistan produces around 450 000 new graduates each year including 70 000 annually in Khyber Pakhtunkhwa and yet the market cannot productively absorb this supply. This has led to graduate’s unemployment and the graduate unemployment rate is estimated at 16.5% - 7.3% for male and 41.1 for female. - The project will support about 25,000 graduates of universities through a public private partnership to enhance their employability skills and potential. The graduates will be engaged for up to one year as interns in both private and public sector and within the project for different functions based on the demand. Priority will be given to those coming from the poorest family. Women graduates will constitute 50% of the target. The initiative will provide opportunities for young fresh graduates to get experience as well as develop their skills in the respective domain which will improve their employment opportunity within the agriculture and rural development sector. The initiative will also provide exposure to the graduates to understand the requirements of the receiving organisations. - Amongst the numerous tasks that will be allocated to the young graduates, could include assisting government line departments and Service Providers in the implementation of their respective activities and/or could strengthen the M&E capacities of the PMU. - Each graduate will have the possibility to do 2 internships of 6 months each. The recruiting public sector institution and enterprise will be allowed to keep the same student for a second period of 6 months only if it provides a formal offer of employment to the student. In case of non-compliance, the enterprise will no longer be eligible to participate in the programme. Each enterprise will have a maximum of 2 students at the same time. Around 145 interns per district and per year will be eligible to this programme. Annual assessments of this activity will be conducted and the approach will be adjusted if needed. It is expected that 30% of the interns will remain employed in the enterprises after completing their internship period, 50% will find a job after their second internship (in a different enterprise) based on the experience acquired and 20% will set up their own business or still be looking for a job after 6 months. - Service provider(s) through call for proposal (twice a year), will identify interested public and private institutions in consultation with PMU, for placement of induction of skilled youth for a period of 6 months. An induction contract will be signed between all the parties - with the confirmation by the participating institution a minimum of 3 years job contact. The remuneration during the induction period is estimated to be PKR 15 000 PKR per month of which PKR 12,000 will be provided by the programme and PKR 3,000 by the institutions/enterprise. Project contribution will remain the same while contribution from participating institutions may be more depending on the skill demanded in the market. A joint assessment but objective assessment will be done of the incumbents at the end of the induction period for confirmation of successful completion of the induction/probation period. ### Component 3: Programme Management, Policy, and Institutional Support - The project will be placed under the Planning and Development Department. An autonomous Project Management Unit (PMU) will be established at Peshawar and 5 additional regional offices will be set up to efficiently manage the distance / geographic coverage / diversity of the project area. The PMU will report to the Project Steering Committee (PSC). The cost of the component includes USD 1 million for policy support. - The PMU will be headed by a Project Director, selected through a competitive process. The selection criteria shall include relevant qualifications, demonstrated experience and expertise approved by the Project Steering Committee (PSC). Till the appointment of Project Director, a Project Director on deputation or on acting charge basis may be appointed to provide leadership for ensuring timely project implementation readiness. For effective implementation, coordination and monitoring five (5) Regional Coordination Units (RCUs) will be established headed by Regional Manager selected through a competitive process. Each RCU shall have a small complement of management and technical staff. An allocation for hiring junior field consultants (mostly local) is foreseen to ensure implementation in remote and marginalised areas. The detailed TORs are provided in the PIM. - Hiring of additional specialized services like Business Development Specialist, Agri-Business Policy Specialist, Institutional Development specialist etc. and hiring field implementation consultants (mostly local) to ensure implementation in remote and marginalised areas will be engaged on as and when needed basis through the provision of Technical Assistance under the components. - PMU shall have a dedicated FM Section headed by Finance Manager for the management of project budgets and finances. A Budget and Finance Coordinator (B&F) staff shall also be provided in each RCU to support implementing partners especially PFOs in compliance with applicable compliance requirements. - Nutrition and Food Security Policy and Action Plan: Building on existing studies carried out on the current nutrition and food security situation in the province, KP- RETP will engage 6 person-months of national technical assistance in collaboration with WFP and FAO to assist the GoKP in the development of a comprehensive nutrition and food security policy and action plan. This will foster sound policy formulation and changes beyond the project immediate results. - The project will assist in integrating ICT4D specifically on online business plan development for PFOs (AgriPlan developed by IFAD or similar other options - to formulate, edit, evaluate, approve, and monitor business plans for producers’ organisations), e-commerce, digital money and e-advisory, etc. Digital systems may also be used to develop credit history and scoring of farmers under the PFOs. Institutional support will be provided in these respects on a cost-recovery basis and in a sustainable manner. |
| 7 | # Capital cost estimates |  |  |
|  | - The project cost is estimated at PKR. 29 billion (USD178.12 million) with IFAD loan financing of PKR 16.300 billion (USD100.1 million) representing 56%; Government of Khyber Pakhtunkhwa contribution of PKR 4.712 billion (USD 28.94 million) representing 16%, in the form of leveraged financing of ADP schemes mostly under KP-TEVTA/UET PESHAWAR/Agriculture Department and taxes and duties for good and services; and PKR 7.988 billion (USD49.1 million) representing 28%, contributed by private sector and beneficiaries. The project investment by component include; (i) agribusiness development PKR billion 15.527 (USD95.37 million); (ii) capacity building for employment/jobs PKR 11.098 billion (USD 68.17 million) and (iii) project management and policy support PKR 2.375 billion (USD 14.59 million). Financing for youth represents PKR 14.5 billion (USD89.06 million) which is 30% of total project cost while investment in women development is estimated at PKR 7.25 (USD44.53 million) at 25% of the total project investment. - Out of the PKR 4.712 billion GoKP contribution, incremental contribution is estimated at PKR 0.83 billion (USD 5.0) million on account of taxes and project management related expenditures while PKR 3.882 billion (USD23.38 million) will be leveraged mainly through ongoing ADP support to TEVTA and agriculture department (under farmer service centres support). The project beneficiaries’ contribution of PKR. 7.988 billion includes; (i) PKR 5.456 billion (USD33.51 million), which would finance about 35% of Component 1; and (ii) PKR 2.532 billion (USD15.55 million), which would finance about 23% of component 2 (mainly on account of job placement contribution). Beneficiaries will be contributing mainly in cash with various ratios depending on the type of activities. (Detailed cost tables for components and sub-components are at Annex I.) |  |  |
| 8 | # Annual operating and maintenance cost after completion of the Project |  |  |
|  | - Government Line Department/Public Sector Intuitions: Existing staff of the Department of Agriculture and KP-TEVTA/UET PESHAWAR will be assigned for implementation of the project and no incremental staff is envisaged. Therefore, there will be no post project operational costs. - Private Service Providers and Implementation Partners. Private service providers/companies and implementation partners will be engaged for implementation of project components under an output-based contract only in the case where public sector line department do not posses the capacity. On completion of the project, the staff and facilities of the service providers and implementation partners will be their own responsibility with no cost implication for the government. - Farm Services Companies: The Farm Services Companies will be fully functional, autonomous and sustainable entities providing demand-based services with PFOs and individual farmers as shareholders. These companies will be managed as private entities offering services on market rates to the PFO and in open market. FSCs are expected to become financially self-sufficient in its fourth year of operation and achieve operational self-sufficiency by the third year. - Professional Farmers Organisations: The business plan of Professional Farmers organisations is expected to achieve a breakeven point in year 3 of operationalization, leading to become self-sustaining institutions. The PFOs’ will finance its operational cost including the costs of professional management staff, out of the coat recovery contributions of members farmers whose average estimated net incremental income generated is expected in the range of USD 1000 – 2,000 per year, per farmer. - Skill Development and Employment Promotion: Eligible trained farmers and youth will be facilitated to find remunerative employment through vocational training, apprenticeship on public private partnership basis or start their own enterprise with one time grant support fund and/or interest free/low-cost loan through the Kamyab Jawan and provincial government programme. The post apprenticeship employment responsibility will be a matter between the trainee and employer. The provision of interest free/low-cost loans for self-employment/microenterprise will be facilitated directly from financial institutions and the borrowers will be responsible for repayment of loan with no cost implication for the project/government. - Physical Infrastructure, Equipment and Machinery. The operation and maintenance of any infrastructure like storage and/or machinery purchased by PFOs out of project financing, will be the responsibility of the concerned PFOs and Partners under 4Ps/FSCs. - Project Management: The Project Management Unit and Regional Coordination Units are project specific institutions which will wind up at the completion of the project. Offices will be established in government premises wherever available or rented premises will be maintained through project provided operational costs. The premises will be handed back to concerned government entity/landlords at the end of the project. The equipment/vehicles purchased for implementation of the project will be transferred to P&D Department for subsequent allocation. All staff will be competitively selected from public and private sector and public sector staff will revert to parent departments on completion of project while private sector staff will be contracted for the duration of the Project only. - Private Service Providers: Services of service providers will be engaged for the duration of the project with no post project liability to the government. No assets will be purchased under the contract with service providers. - Revolving Funds: The financing under component 1 provided to PFOs, PPPPs and FSCs will be treated as revolving fund in the form of debt equity of the Government of KP. Similarly under the component 2, the start-up capital will be managed as revolving fund on the basis of low/interest free loans. Nevertheless project investment on households having poverty score of 0-18 will be in the shape of grants. This group is estimated to be around 10% of the total project target. The cumulative growth in the revolving fund with a 10% growth per year will be around US$105 million over a period of 7 years. During the second last year of the project an exit strategy will be devised for the revolving funds. - Provincial Agribusiness Forum/Holding Company: The network of PFOs, PPPP and FSCs will be consolidated into a provincial agribusiness forum at provincial level which shall be a registered holding company owned by farmers. The network will provide economic services such is branding, labelling, compliance to standards, quality certification, joint access to input and output markets and product development etc. |  |  |
| 9 | # Demand and supply analysis |  |  |
|  | ## Situation Analysis - The demand and supply analysis of the project is contextualized to the specific socio-economic development challenges of the province and the country. The province, because of its geography and socio-economic conditions, is highly vulnerable to the impacts of climate change, conflicts and economic disruption owing to natural disasters. The provincial economy is dominated by the services sector which contributes about 67% to provincial GDP followed by manufacturing 17%, and agriculture 14%. Remittances from migrant workers, mostly as unskilled workers in GCC countries, are an important source of supplementary livelihood for about 0.3 million households . - Multidimensional poverty in the province is 49% against the national average of 39%. Rural poverty is nearly 58%. The number of HH categorised as extremely and chronically poor (BISP PSC 0-16.7), in the province, is estimated at 1.6 million. The multidimensional poverty in the merged districts is close to 74%. Because of the federally administered semi-autonomous nature and the proxy system of governance till 2018, MDs were not entitled to a formula-based federal fiscal allocation and generally remained outside the scope of political, economic and social development of the country. - Despite its declining share in the GDP, the agriculture sector continues to be considered a key driver of growth for the province. It accounts for employment of 32% of the labour force and provides direct and indirect livelihood to 80% of the rural population. Small farmers who constitute 95 percent of the total, mostly undertake subsistence farming and follow a mixed farming system consisting of agriculture and livestock and make supplementary income through off and non-farm labour. - Livestock is an integral part of a smallholders' household economy and a key element in the mixed farming system. The province possesses an estimated 13 million Cattell and buffalos, 20 million sheep and goats and 27 million poultry. The share of the livestock sector in the total agriculture income is 30% and it complements the agricultural incomes of small and landless households. In the southern part of the province, livestock is a more important source of livelihood than crops. The production and distribution system of livestock and livestock products are traditional and poorly developed. - Low labour force participation rate, high unemployment rate particularly among youth, predominance of informal economy, low level of education and skills and very low participation by females are some of the features of the labour market in the province. An inadequate skilled workforce has remained a major challenge over the past few decades particularly for agriculture value addition development and the emerging manufacturing, hospitality, construction mining and services sectors. The onset of the China-Pakistan Economic Corridor (CPEC) has further widened the gap in demand and supply for the skilled labour force. ## Opportunities - In line with the priorities of the provincial government and based on need assessment, the transformation potential of agriculture for enhanced incomes and employment will be pursued by addressing the critical issues in the farm, off-farm and non-farm sectors. - The province because of its unique agro-climatic conditions, has enormous growth potential in the development of high value crops such as horticulture crops and floriculture, as well as the development of the livestock sector. However, despite the existence of provincial and national market opportunities, farmers’ profitability and employment generation potential remain untapped. - Diversification to horticulture and the livestock/dairy sub-sectors offers the highest potential value generation and income enhancement for smallholders. The project will particularly focus on addressing the high transaction cost/lack of economies of scale (high cost of aggregation) due to fragmented production base; low productivity owing to low adoption of technology and techniques; limited access to finance limiting potential of investment; high risk associated with investment in agriculture sector; poor linkage of small-holders with markets and non-integration in major supply chains; high post-harvest losses due to absence of essential infrastructure; weak compliance capacities and complex quality standards regimes. - The youth bulge calls for equipping the youth with the skills that are in demand in the labour market and facilitating them in finding decent livelihood. The agribusiness approach of the project under component I and skill gap between demand and supply for the emerging sectors of the province provides an opportunity for the project for skilling the young women and men for employment, self-employment/micro enterprises leading to growth and development of the province. According to a study, there is an annual incremental potential of about 100,000 skilled workforce for the evolving sectors like tourism, construction, mining, health care technicians etc. The agribusiness development component of the project is expected to generate about 25,000 employment/enterprise development opportunities for value addition in the agriculture sector including productivity enhancement, harvesting and post harvesting technologies, fruits and vegetables, processing, trade, storing, and transporting. - The project will provide about 110,000 employment and self-employment/enterprise development opportunities for realizing the dividends of the “youth bulge” by addressing critical challenges related to human capital development, jobs market readiness (skills and self-employment), integration of young graduates to the job market and access to finance. A major challenge to increase the labour force participation rate and provide productive employment to the youth is the lack of appropriate skills relevant to job market needs. There is a growing gap between the skills that the job market expects from their entry level employees and the skills that the young people possess. Women's work force participation is partially hindered due to cultural norms, mobility issues, a lack of co-working spaces and skills, and perceptions that limit opportunities for women. - Since a large proportion of the youth have poor educational attainment, vocational skill development is the most important pathway for human capital accumulation for the youth in view of the limited livelihoods opportunities. In the case of the target district this pathway will be fundamental in restoring livelihoods and generating employment. - Climate Change: Pakistan is one of the 10 most affected countries in terms of climate change and variability, ranking 5th in the Long-Term Climate Index. To reduce the risks and impacts associated with changing weather and climate conditions, the project will strengthen the capacity of farmers to assess climate risks, plan and identify suitable adaptation/mitigation actions. The identified actions, once implemented, will significantly improve the agriculture sector’s resilience to climate change. - Nutrition: The project, under the agribusiness development component, focuses on value chains that support dietary diversity, high nutrition impact and incomes (e.g., livestock, crops, vegetables, fruits, etc.). The project will supplement investments in livelihood enhancement, with nutrition information services to women and men, to ensure that decisions at household level are well informed. Considering the conservative social context in the project area, the 25% of targeted women will be provided with this information through separate trainings, especially on maternal and early childhood nutrition, while men will be trained separately on good nutritional behaviours and dietary diversity. It is also expected that enhancing smallholder production and productivity will have a positive impact on the nutrition status of targeted households. - Overall, around 750,000 households will benefit directly and indirectly from KP- RETP interventions. The project agribusiness development initiative involving 700,000 HH, relates to aggregation of the production based on three simultaneous pathways. These include (i) mobilizing small farmers into professional farmer organisations; (ii) integrating small farmers into public-private-producers partnership; and (iii) strengthening the delivery of inputs and services to the PFOs and farmers participating under 4Ps. The employment and enterprise development will position 85,000 farmers and rural youth to avail jobs and self-employment for remunerative engagement. Investment in skills (vocational and entrepreneurship) will increase wage/salary rates while self-employment (combining training and start up) will create economic activities in the rural areas. In addition, job placement facilitation will provide the entry point for youth training graduates. |  |  |
| 10 | # Financial plan and mode of financing |  | (Detailed cost Tables are at Annex – 1) |
|  | - The total project cost is estimated at PKR. 29 billion (USD185.8 million) and will be financed through: - IFAD loan of PKR 16.300 billion (USD100.1 million) on blend terms (56%). A financing of US$84.19 is available from the current financing cycle (2019-2021) by IFAD while the remaining $16.91 million will be allocated in the next financing cycle (2022-2024). Negotiation are also underway with European Union for a possible grant financing for an amount of US$16.91 million. - Government of Khyber Pakhtunkhwa contribution of PKR 4.712 billion (USD28.94 million) representing 16% of the total cost. - Beneficiaries’ contribution is estimated at PKR.7.988 billion (USD 49.06 million) including (i) an estimated PKR 5.456 billion, which would finance about 35% of Component 1; and (ii) an estimated PKR 2.532 billion, which would finance about 23% of component 2 (mainly on account of job placement contribution). Beneficiaries will be contributing mainly in cash with various ratios depending on the type of activity. |  |  |

|  | Table 3: Programme Cost by component (and sub-components) and financier (PKR. Million) Table 4: Programme Cost expenditure account and financier (PKR. Million) Table 5: Programme/project costs by component and year (PKR. Million) |
| --- | --- |
| 11 | # Project benefits and analysis |
|  | - The Economic and Financial Analysis (EFA) takes into account benefits from the two project components; (i) agribusiness development; and (ii) Skills Development and Employment Promotion. The incremental financial returns for all the sub-components have been worked out keeping in view the initial situation vis-a-vis projected benefits resulting from the project interventions. The financial modelling covers a period of 20 years. The economic analysis takes into account investments and recurrent costs of the proposed project against the incremental economic benefits over a period of 20 years. The economic values of cost and corresponding benefits of the project have been used in the economic analysis. - The intervention logic and theory of change of the project is based on two mutually reinforcing pathways. The agribusiness development pathway will reorient the traditional agriculture to a market-driven industry which integrates smallholder farmers into commercially viable supply chains. The project assistance will facilitate operationalization of; (i) professional, profitable and sustainable farmers organizations responding to the market demand; (ii) 4Ps business model integrating small farmers into commercial supply chains; and (iii) strengthening service delivery that improve market access (mainly inputs and technology). The aggregation of farmers will initiate policy advocacy for creating a favourable policy and regulatory environment. The skills for employment and entrepreneurship pathway – poorer households (PSC 0-34), and especially women and youth who do not have access to land, will be economically integrated in job market and rural economic activities through skills, start-up capital and job placement support. This combination allow them to; (i) access a decent and remunerative employment; (ii) to develop, alone or in association, own business; or, (iii) integrate into job market through an apprenticeship programme. The youth / women trained will be able to get jobs and income opportunities created through Component 1. - The project’s investments will be nutrition sensitive. Commodities/crops and its related products that have high nutritional value will be prioritized. Smallholder farmers, skilled persons and entrepreneurs assisted under the KP- RETP will facilitate recognizing the nutrition issue and will include awareness and activities directly linked to nutrition for the benefit of the entire HHs and in particular for the children and youth. The project will sustainably increase income of small farmers, landless and women, which in turn will improve their livelihood and dietary diversity/nutrition. Recognizing that improved productivity and incomes do not automatically lead to better nutrition outcomes, the project will pursue behaviour change, awareness/education campaigns primarily through farmer’s organisations and revision/extension in training curricula. - Total cost is estimated to be approximately 93% investment expenditures and 7% recurrent expenditures. Investment cost includes Vehicles, Equipment and Material; Technical Assistance, Training and Studies; and Grants to Beneficiaries. Recurring expenditure is composed of salaries and operating expenses. The project is designed to contribute to the attainment of Sustainable Development Goals (SDGs) and assist in realization of the priorities of poverty reduction, food security, and access to services. - Summary of benefits and economic analysis. The KP- RETP provides the necessary incentive to all stakeholders as evident from its financial and economic rate of returns. The net cash flows resulting from the project provides incentive for beneficiaries (producers and participating private sector) in the shape of improved income and profitability. For the Government of Khyber Pakhtunkhwa, there are significant economic gains in terms of socio-economic development of rural households. The intervention will leverage private sector investment and will catalyse horizontal and vertical expansion of economic activities in the rural areas. - The benefits: The project benefits are anticipated in the two project components including; i) agribusiness development; and (ii) employment and jobs promotion while the third component i.e., project management, institutional and policy support will facilitate the two. - Benefits of agribusiness development. The project interventions related to aggregation of the production based on three simultaneous pathways. These include (i) mobilizing small farmers into professional farmer organisations; (ii) integrating small farmers into public-private-producers partnership; and (iii) strengthening the delivery of inputs and services to the PFOs and farmers participating under 4Ps. The project logic is to reduce transaction cost (production, handling and marketing), accessibility to quality inputs, reduce cost of capital and eventually improve quality compliance. The net effect is in the form of increased income stream resulting from increased production and higher prices realised. The farm services centres having shares of PFOs (its members) will generate additional income and will provide inputs and services to both members and non-members. - Benefits of employment and jobs promotion: The project component will position rural youth to avail jobs and self-employment for remunerative engagement. Investment in skills (vocational and entrepreneurship) for the job market will increase wage/salary rates while self-employment (combining training and start up) will create economic activities in the rural areas. In addition, job placement facilitation will provide the entry point for youth training graduates. - The income after the project intervention of small farmers is estimated to be PKR. 379,000 (US$2500) on an annual basis, around 3-15% higher over the baseline. It has been estimated that 4Ps will enable increase to PKR. 124,000 (US$818) per small farmer 18-24% up from baseline. Additional income from farm services centres is estimated is PKR. 8 000 (US$50) per annum. Investment in vocational and entrepreneurship training help the beneficiaries enhance income and wage return. Annual increase is estimated at Rs. 237 000 (US$1 550) per year. |
|  | ## Financial Analysis/Benefits - The KP- RETP investment is viable as evident from its overall Financial Internal Rate of Return (FIRR) of 22.3%. The Net Present Value (NPV) of the proposed project over 20 years’ period is noted to be PKR 18.6 billion (USD119.2) million. The discounted benefit cost (B:C) ratio is noted to be 1.56. ## Economic Analysis - The economic analysis of the proposed project was worked out taking into account the economic cost of the proposed project and the resultant economic benefits to the target beneficiary households. The economic cost was worked out by converting the financial value using the standard conversion factor whereas economic value of benefits have been worked out using conversion factors of outputs and inputs. The standard conversion factor used in the economic analysis was derived to be 0.874 while the conversion factors for output and inputs were noted to be 1.10 and 0.95 respectively. The economic analyses takes into account the total economic investment and economic recurrent cost of the project during the project period i.e., incurred between 2022 and 2042. Price contingencies and taxes are excluded from the economic analysis. For the capital items, no residual values have been considered in the economic analysis. - The overall economic internal rate of return (EIRR) of the project is estimated at 26.7%. The economic net present value (NPV) of the project net benefit stream, discounted at 9.76%, was calculated to be PKR 18.4 billion (USD118.0 million while benefit-cost ratio is noted to be 1.34. - The results of the financial and economic analysis suggest that the proposed project is financially and economically viable, will result in the increased income and represent significant incentive for the participating beneficiaries thus recommended for investment. - For detailed EFA kindly refer to Appendix 4. ## Social benefits with indicators: - In line with the overall goal, the project interventions will contribute to poverty reduction, food and nutrition security and strengthened resilience of rural households. The social benefits can be summarized as following: - The project benefits are expected to reach 522,500 households adjusted for an estimated 50% household receiving multiple benefits. - About 60% of project target group will belong to Extremely poor households (families with a large number of dependents, often these are women headed, are illiterate, do not own a house and living standards in terms of housing condition, water, sanitation is very low); Chronically poor households (large households with a large number of dependents; own basic one room house and one odd head of livestock or other productive asset; largely illiterate and dependent on daily wage labour or other casual work for others. Seasonal indebtedness during periods of low employment or prior to wheat harvest times or due to illness of wage earner; lack of access to social services and sources of knowledge and capital. Have one or two able-bodied adults who can be equipped with skills and/or productive assets to generate a sustainable income stream and get out of poverty); and Transitory poor households (The per capita per month income of the household is more than or equal to 75 percent of the poverty line but less than the poverty line. These are fluctuating poor, who are poor in some periods but not in others and have a mean poverty score around the poverty line. These households are likely to have fewer livestock and less land and other physical capital.) - Significant change of provincial poverty status and SDGs contribution at national level by economic and social graduation of an estimated 300,00 extremely, chronically and transitory poor households - Contribution to social and economic empowerment of youth through benefits of agribusiness development and skills and employment for about 261,250 youth - The project will purse gender mainstreaming and women economic and social empowerment by ensuring a minimum of 25% (about 175,000 HH) women participation in all project activities and by the development of women centred value chains, and 4Ps. |
|  | ## Employment generation (direct and indirect) - The project will generate employment at different levels. At the beneficiary level, employment will be generated under the following interventions: - The project is expected to generate 110,000 employment and self-employment opportunities directly. The focus of the project Skills development and Employment Promotion component will be youth (50%) and women (25%). Following is the detail of employment opportunities under various activities of the project: - Capacity building and employment opportunities for 25,000 small farmers and youth in technical, financial, managerial, and business skills needed to ensure the successful operation and management, profitability, and sustainability of agribusiness development component and related services. - Rural employment and self-employment for 60,000 persons through demand based vocational training. This includes job market readiness for 18,000 youth through skills development training and public private apprenticeship for employment in new emerging sectors like tourism, construction, mining, health care technicians and CPEC related infrastructure activities and provision of start-up capital for self-employment/micro enterprises for 42,000 youth. Beneficiaries will consist of 25% women and 50% youth. - Employability enhancement and job placement of 25,000 graduates from faculties through public private internship programme. It is expected that 80% of the interns will remain employed in the enterprises after completion of internship and 20% will engage in self-employment/micro enterprises. About 50% of the total internship will be offered to woman graduates. - Additionally, the agribusiness development is expected to generate additional employment in fruits and vegetables picking, packing, processing, trade, storing, and transporting. - Employment will be generated for the professional and support staff deployed at PMU, RCUs as well as incremental staff recruited for private service providers responsible for implementation of their respective interventions of the project. |
|  | ## Environmental impact - An environmental, social and climate risk screening under the IFAD Social, Environmental and Climate Assessment Procedures (SECAP) was carried out for the project. The project was rated as category B and a mandatory Environmental and Social Management Plan (ESMP) has been prepared. IFAD classifies all projects into one of three environmental and social categories (A, B or C) and one of three climate risk classifications (high, moderate and low). Determination of the category and classification also depend on the national requirements and the existing national capacity to promote and implement environmental and social mitigation measures. - The SECAP outlines how to mainstream and addresses the social, environmental and climate impacts associated with IFAD projects and programmes and for category B projects, a mandatory Environmental and Social Management Plan (ESMP) is prepared at the design stage. The identified social and environmental risks and opportunities management measures are reflected in the project design and the project design report. The ESMP provides guidelines for the management of potential environmental and social impacts together with climate change aspects of the project interventions. - The project mostly involves soft activities like social mobilization, agribusiness development and vocational trainings and skills development for the target group employability and income increase. It does not involve infrastructure development or other civil works, land acquisition or displacement and resettlement of people. However, there are chances that the FPOs might go for establishing fruit, vegetable or dairy processing units at local level. - The project anticipates positive environmental impact in terms of increased mitigation measures including (i) improved and efficient water usage; (ii) sustainable natural resource management particularly climate smart technologies and judicious usage of agro-chemicals; and (iii) promoting plantation of fruit trees and vegetables. - Interventions with small farmers and livestock holders will follow climate smart agriculture technologies, water conservation and a value chain approach that would have positive impact on income of farmers and environment. Household level interventions are aimed at building capacity and skills of the small households to generate more sustainable and environmentally responsible incomes for themselves through skill development for enterprises and remunerative jobs or services. The Environment and Social Management Framework (ESMF) is compiled as Appendix 3. |
|  | ## Impact of delays on project cost and viability - The project start up delays, financial management capacity, climate risks and uncertain security situation in some areas may cause underperformance with regards to achievement of full scale benefits, delay in realization of benefits and reduced effectiveness. Under various risk scenarios, the analysis reveals acceptable values of both NPV and EIRR, and thus the proposed investment is feasible under these adverse scenarios with the project viability more sensitive to extended time lag. Table 6: Sensitivity Analysis of Proposed Project Scenarios; A%; Link with the risk matrix; IRR; NPV (USDM). Normal Scenario; Normal; No Adverse Risks; 26.7%; 118.0. Project benefits; -10%; Poor Security Situation affecting project benefits adversely; 23.6%; 95.1. Project benefits; -20%; 20.5%; 72.1. Project costs; 10%; Weak financial capacity result in cost overrun and delayed implementation; 23.9%; 106.9. Project costs; 20%; 21.5%; 95.7. Time lag in benefits (Year); 1; 16.1%; 49.9. Time lag in benefits (Year); 2; 21.1%; 93.1. Success Rates; -10%; Security and climate change risk affecting success rate negatively; 23.6%; 95.1. Success Rates; -20%; 22.8%; 93.7. Note: Three major risks have been identified which include; (i) security; (ii) financial management capacity, and (iii) climate-risks. These risks may cause underperformance concerning achievement of full-scale benefits, delay in realization of benefits and reduced effectiveness. |

| 12 | # Project Implementation |  |
| --- | --- | --- |
|  | ## Implementation schedule - The project will be implemented over a period of 7 years (2022-2028) and will cover all the 35 districts of the province. However, project implementation will follow a phased approach starting in 10 districts initially and subsequently 3 districts per region will be rolled out per year with the aim of covering the entire province reached out by the mid-term stage of the project (End of Year 3). |  |
|  | ## Result Based Monitoring (RBM) Indicators - A result-based monitoring system will be in place based on the project logframe - see Annex-2 for RBM indicators. The indicators will be updated through a baseline study and will be evaluated through a mid-line and end-line studies undertaken by independent third party. |  |
| 13 | # Management structure and manpower requirements including specialized skills during construction and operational phases: |  |
|  | - The Economic Affairs Division, Government of Pakistan, will be the overall coordinating agency at the federal level for IFAD financing while project steering committee will provide the overall strategic direction and oversight. ## Project Steering Committee (PSC) - A Project Steering Committee headed by the Additional Chief Secretary of the P & D Department, shall be constituted to provide policy level guidance, oversight, and coordination. The composition of the PSC shall be as follows: - Additional Chief Secretary (ACS) Development; Chairperson. - Secretary Finance Department; Member. - Secretary Agriculture, Livestock, & Cooperatives Department; Member. - Secretary, Industries, Commerce and Tech. Education Department; Member. - Managing Director TEVTA; Member. - Secretary Zakat-Usher, Social Welfare, Special Education and Women Empowerment Department; Member. - Secretary Sports, Tourism and Youth Affairs Department; Member. - Secretary Local Government and Rural Development Department; Member. - Co-opted Member ( as and when required); Member. - Project Director; Secretary. - The PSC shall co-opt a member or expand membership by including additional members—as the case may be subject to the need of project implementation. The PSC shall examine the need for such additions to the existing membership in its meetings and take a formal decision thereon. The PSC will convene bi-annually (more often if necessary) on the basis of the agenda items prepared by PMU. - The specific responsibilities of the PSC include: - Provide overall guidance and oversight to enable the project to reach its development objective in line with the financing agreement; - Take timely decisions and issue necessary direction to create enabling policy/regulatory environment for project implementation; - Ensure fair allocation of funds to the districts/regions by considering population, poverty profile, and value chain potential in each district/region. In cases where a region/district is not able to achieve performance targets established in the AWPB persistently, divert funds to the districts/regions that are performing as per established targets with. - Examine proposals for partnerships with government departments/agencies and approve MOUs for execution of such partnerships; - Identify and approve ADP projects that shall be implemented under the project as part of the government’s financing stream; - Approval of Annual Work Plans, Budgets and Procurement Plans; - Review performance of PMU/Service Providers/ line departments under MOUs, against established targets and take remedial actions to keep implementation on track; progress against the work plans/budgets and take remedial actions where needed; - Approve the PIM as a guideline for project implementation and its periodic updating as needed; - Ensuring timely provision of counterpart funds (cash) and sufficient allocations for provincial ADP-funded projects that have been selected for leveraging under the project. - To resolve implementation bottlenecks promptly, the PSC shall constitute a smaller but empowered a small Sub-Committee under the PSC—to be called the Executive Committee. The Sub-Committee/Executive Committee shall be headed by Secretary P&D and include representatives of Finance Department, line department (s) relevant to the implementation issue(s), Chief RD P&DD, Chief IDS P&DD, Chief Agriculture P&DD, Chief Industries P&DD, Head/CEOs of service providers and Project Director. The Sub-Committee/Executive Committee shall be responsible to: - Provide operational level direction and suggest viable options or any pertinent issues faced during project implementation; - Review and finalization of the project implementation as and when required; - Identify and expeditiously resolve implementation constraints/bottlenecks in coordination with the stakeholders concerned which otherwise would await PSC meeting; - As delegated by the PSC, engage with IFAD and other financiers on matters requiring their decision to ensure smooth implementation of project activities; - Carry out any task/follow up at the direction of PSC; and, - Obtain anticipatory approval of any urgent action pertaining to the mandate of PSC. - The Sub-Committee/Executive Committee shall meet quarterly or as may be required by PSC to review implementation progress and take quick decisions after consultation with relevant members of the PSC—as appropriate. - During the meetings of the PSC, the decisions taken by the Executive Committee shall be validated. ## Project Management Unit (PMU) - The Planning and Development Department will be the lead implementing agency/administrative department for the project. A Project Management Unit (PMU) at Peshawar and five (5) Regional Programme Management Units (PMUs) will be established under the P&DD for project implementation. PMU shall be headed by a Project Director who will preferably be a civil servant of appropriate seniority posted or selected through a competitive process on terms and conditions acceptable to IFAD. Once the Project Director resumes the charge, he/she will serve for at least three years. - PMU will be responsible for all aspects including operations, finance, procurement, human resource, M&E related to the implementation of the project. PMU will be administratively linked to the P & D Department but accountable for its work and performance to the PSC. Following are the major responsibilities of PMU; - Project planning, implementation, monitoring and coordination with the participation of all implementing partners and stakeholders; - Preparation of the consolidated AWPB and the associated procurement plan (PP); once the AWPB and PP is approved by PSC and cleared by IFAD, the PMU will ensure its efficient implementation; - Quarterly and monthly plans for project implementation; - Conduct of financial, accounting, external auditing, procurement and administrative management—including robust oversight of the FM processes at partner organizations/service providers etc; - Development of comprehensive M&E Plan and conduct of monitoring and evaluation activities including impact assessments; - Preparation of detailed quarterly and annual physical and financial progress reports for submission to Government and IFAD as per prescribed timelines; - PMU staff and partner implementing agencies staff capacity building training in project approach, processes and outputs and outcomes; - Promotion and development of team building among all partners and ensuring discipline within PMU and among implementing partners; - Establishing systems for transparent operations, prevention of corruption and achieving value for money through efficiencies and competitiveness; - Preparation of the Project’s communication strategy and dissemination of information about the project rationale, concept and detailed content to the stakeholders and all interested parties; - Establishment and maintenance of linkages with government departments and agencies, donors, private sector partner organizations, social mobilization partners, and the community organizations; and - Maintain an efficient management/accounting software to support effective decision making and financing reporting to IFAD and other stakeholders. ## Regional Coordination Units (RCUs) - Given the degree of homogeneous production systems/characteristics, agro-ecological features and proximity to Peshawar, PMU shall have five (5) RCUs as stipulated hereunder: - The Central Agribusiness Zone: covering Peshawar, Charsada, Mardan, Swabi, Nowshera, Khyber and Mohmand Districts. The regional office will be at Peshawar. - The Northern Agribusiness Zone: Lower Dir, Upper Dir, Malakand, Buner, Swat, Bajaur and Shangla. The regional office will be at Mingora, Swat. - The Chitral Organic Agribusiness Zone: covering Lower Chitral and Upper Chital with office in lower Chitral. - The Eastern Agribusiness Zone: covering Haripur, Abbottabad, Mansehra, Torghar, Batagram, Kolai Pallas, Upper Kohistan and Lower Kohistan. The regional office will be in Mansehra. - The Southern Agribusiness Zone: covering Bannu, Lakki Marwat, D.I. Khan South Waziristan, North Waziristan, Kohat, Hangu, Kurram, Orakzai, and Karak and Tank. The regional office will be at DI Khan. - Each RCU will be headed by a Regional Coordinator who shall be selected through a competitive process. The RCUs shall provide field level coordination and monitoring. Each RCU shall have a small complement of management and technical staff. RCU shall facilitate continuous and effective coordination between the project and agro-business partners, farms service centres, farmers’ organizations, and the relevant staff of agriculture extension/research in the field. ## Management and Operations - Financial Management. PMU will have a dedicated FM Section headed by a well-qualified and experienced Finance Manager (FM) who will be selected through a competitive process on terms and conditions acceptable to IFAD. The FM shall have adequate and suitably qualified support staff—both in PMU and each RCU. The financial management shall be subject to applicable rules and regulations, PIM, and provisions contained in the Financing Agreements. In cases where there is conflict between the government rules and regulations and IFAD’s requirements, PMU shall follow IFAD’s guidelines. - Annual Work Plan and Budget (AWPB). The PMU will prepare AWPB subject to IFAD’s guidelines and procedures and submit it to IFAD by the end of April after the approval of the PSC for the next financial year starting from July. PMU shall ensure that the government’s share in terms of (a) “cash” for taxes and project management; and (b) ADP funds under the ongoing/new projects that shall be leveraged under the project are clearly estimated and indicated in the AWPB in addition to the share of IFAD Loan. It will be the main instrument for financial management, expenditure control, reporting and fund releases. PMU shall follow a participatory process in formulating the AWPB. - Flow of Funds. PMU shall have one designated account each for the IFAD’s Loan and the Government Counterpart Funds. PMU shall obtain from IFAD an initial advance to meet expenditure for the first six month of implementation. This will be replenished subject to submission of financial statements as referred to below. The project shall maintain liaise with P&DD/Finance Department for timely release of funds. - Accounting. A full set of accounts will be maintained by PMU as per the requirement of the provincial government and IFAD. The project shall follow IPSAS-Cash Basis in accounting. An appropriate accounting software shall be used to capture all sources and uses of funds and generate financial statements acceptable to the Auditor General of Pakistan and IFAD. - Internal Controls. Robust internal controls shall be established to protect project funds against any financial impropriety. Access conditions shall be established for all Implementing Partners in contracts/MOUs with them. FM team shall conduct monthly analysis of budget vs actual expenditures, bank reconciliations, random inspection of Implementing Partners’ field work, to prevent, detect and rectify compliance gaps in implementation. - Reporting. The project will submit to IFAD detailed financial statements for each financial year within four (4) months of the end of each financial year (by the end of October). In addition, the project will submit an Interim Financial Report indicating progress against components/categories vis-à-vis AWP/B. All Implementing Partners (IPs) shall be required to submit quarterly reports on their technical and financial progress vis- a- vis approved AWPB. - Internal Audit. An Internal audit function—reporting directly to Project Director, shall be established. Internal audit shall—in addition to normal auditing, ensure compliance with the recommendations of the supervision missions, external audit, and other direction issued by the government etc. An Internal Auditor/Chartered Accountant firm shall be engaged for this purpose. The TORs of the IA are provided as part of PIM. - Audit. Audit of Project Accounts will be carried out by the Auditor General of Pakistan (AGP). PMU shall submit to the AGP the Annual Financial Statements (AFS) within two (2) months of the close of a financial year and closely coordinate with relevant field audit office of AGP for timely audit, reporting, and resolution of audit observations. Report of each Audit—along with the Management Letter shall be submitted to IFAD within six months of the close of the financial year (by 31 December) to which the audit relates. - Procurement Management. Project procurement will be carried out in accordance with the Khyber Pakhtunkhwa Public Procurement Regulatory Authority (KP-PPRA) Rules, to the extent of their consistency with IFAD's Project Handbook & Procurement Guidelines, Financing Agreement and Letter to the Borrowers (LTB). - PMU will have a highly qualified procurement team comprising a Procurement Specialist (PS) and a Contract Management Officer (CMO) reporting to the Project Director. The procurement team will be responsible for undertaking all procurement activities within the defined thresholds and shall prepare procurement document for the processes. All procurement activities shall have to be consistent with the Annual Work Plan and Budget (AWPB) provisions. IFAD’s prior review and No Objection requirements to the procurement transactions—where established under the FA, shall be complied with. - IFAD Standard Bidding Documents (SBD)/templates will be used for all procurement for goods, works and services. PMU shall include provisions in the SBDs requiring suppliers, contractors and consultants to comply with IFAD’s Policy on Preventing Fraud and Corruption, IFAD’s Policy to Preventing and Responding to Sexual Harassment, Sexual Exploitation and Abuse, IFAD’s Anti-Money Laundering and Countering the Financing of Terrorism Policy. The SBDs/contract shall also include provisions allowing PMU/IFAD to inspect/audit transactions’ record/documentation maintained by suppliers, contractors, and consultants etc. to ensure that all applicable compliance requirements emanating from these policies are being complied with in project activities. - PMU and RCUs shall be adequately staffed with suitably qualified and experienced staff that shall be selected through a transparent and competitive process. The positions provided in the project are given in the table below. The organizational structure of PMU and Job Descriptions of key positions at PMU and RCUs are provided in PIM. The government employees will be hired through negotiable package. Project Management Unit. Position; BPS; Number. Project Director; 19 or MPS; 1. Project Coordinator; 19 or MPS; 1. Agribusiness and Agri Skills Manager; 18; 1. Employment and Jobs Placement Manager; 18; 1. Finance Manager; 18; 1. Gender/Nutrition/Climate Change Specialist; 18; 1. M&E and Knowledge Management Manager; 18; 1. Institutional Development Officer; 18; 1. KM/Communication Officer; 17; 1. Accounts Officer; 17; 1. Budget and Finance Officer; 17; 1. Procurement Officer; 17; 1. Contract Management Officer; 17; 1. M&E Officers; 17; 2. Admin and HR Officer; 17; 1. Labour Market Specialist (Consultant); 1. Skills Development Specialist (Consultant); 1. Employment Policy Specialist (Consultant); 1. IT Officer; 16. Support Staff. Account Assistants; 16; 8. Office Assistants; 16; 4. M&E Assistants; 16; 4. Drivers; 05; 5. Peon; 04; 4. Guards; 04; 4. Gardeners; 04; 4. Sweepers; 04; 4. Note: The positions of Project Director may be hired following MP scale with salary to be negotiated based on applicable rates. Regional Coordination Units. Position; BPS; Number. Regional Coordinator; 18; 5. Regional M&E Officer; 17; 10. Agribusiness/4P officer; 17; 5. Gender and Youth Mainstreaming Officer; 17; 5. Budget and Finance Coordinators; 17; 5. Support Staff (RCU). Office Assistant; 16; 5. Drivers; 05; 20. Peon; 04; 10. Guards; 0]4; 10. Sweepers; 04; 5. ## Project Implementation Manual (PIM) 13.17. The project staff shall follow the direction/guidance provided in the PIM in planning, planning, coordination, financial management and reporting requirements covering PSC, PMU and all implementing partners. The PIM includes workable/simple templates for consistent application of required guidance in engagements for PFOs, FSCs, 4Ps, KP TEVTA, and other service providers. The PIM (Appendix 1) is an integral part of this PC-1. PIM will be approved by Project Steering Committee and will be updated as and when required. |
| 14 | Additional projects/decisions required to maximize socio-economic benefits from the proposed project |  |

15.	Certified that the project proposal has been prepared on the basis of

Instructions provided by the Planning Commission for the preparation of PC-I for social sector projects.

Prepared by:			Assistant Chief RDS

Planning & Development Department, 				    Government of Khyber Pakhtunkhwa

Checked by:		Chief of Section, Rural Development (RD)

Planning & Development Department, 		    Government of Khyber Pakhtunkhwa

Recommended by: 			Secretary

Planning & Development Department, 			 	     Government of Khyber Pakhtunkhwa

Additional Chief Secretary

Government of Khyber Pakhtunkhwa

# ANNEX I. DETAILED COST ESTIMATES BY COMPONENTS

\a One FO on average having 400 shareholders mobilised and will be registered under the relevant regulatory framework.

\b One 4P shall integrate a minimum of 2000 farmers on average. Farmers joining 4Ps may also be organised into registered FOs.

\c Support to Agriculture and Industries Department for policy consultations and updating regulatory framework related to Farm Services Companies, Cooperatives/Farmer Organisations, contract farming, quality control of inputs and Marketing/Markets

\d On the basis of project need result based and MoUs will be signed with government line departments/training institutions

\e AMP may be one or several service providers which will be responsible for mobilization and business development planning for PFOs and 4Ps, registration of PFOs, 4Ps and FSCs.

Table 2. Component 2: Skills Development and Employment Promotion

\a Start-up capital will be linked to entrepreneurship and vocational training. Priority will be given to those graduated under KP- RETP component 2, whose loans are approved under Kamyab Jawan Programme.

\b Gradual phase out of remuneration in collaboration with public and private institutions. This activity is linked to job placement support services.

\c Technical assistance for training programme adoption, curricula improvement, training of trainers and improvement to training facilities. To be approved by project steering committee as part of Annual Work Plan & Budget.

\d The service provider will be selected on competitive basis and must be having necessary expertise and demonstrated capacities to extend outreach of TEVTA skills development in marginalised areas/indigenous communities.

\e Facilitate MoU with employers/industries for job placement of youth (graduates of educational institutions and vocational training). Output based contract with service provider.

\f Investment in systems (M&E/database), institutional framework for skill development fund and improvement in training facilities as well as creation of 3 skills hubs/centre of excellence (at Rashakai economic zone, in Swat for hospitality and a multipurpose

\g Strengthening facilities and establishing 3 hubs/centre of excellence (economic zones)

\h Technical assistance for training programme adoption, curricula improvement, training of trainers and improvement to training facilities. To be approved by project steering committee as part of Annual Work Plan & Budget.

\i The TA will strengthen system within TEVTA for undertaking a job market study and releasing annual job market outlook.

\j The training need assessment will form the basis for training of instructors of the institutes linked to TEVTA and may also include selected private sector institutions offering training related to agribusiness.

\k Training of Trainers event organised for instructors on pedagogy and experiential learnings - each batch having 20 instructors from vocational/technical skills training institutes.

Table 3. Component 3: Project Management and Policy Support

\a Workshops, webinars, publications, documentaries and media engagement

\b Consultant(s) to be hired according to policy themes and needs identified during project implementation as and when required.

\c As per the need identified as and when required to be hired as consultant(s).

\d Multiple Specialists to be hired as per need and will be responsible for labour market assessment and development of framework for labour market outlook preparation, supporting TEVTA.

\e To be hired during project implementation to support TEVTA, Agribusiness Component and Social Welfare Department in curricula development/revision, training needs assessment of instructors, need identification for missing facilities and development CBT and certification mechanism

\f To be hired as per need identified in association with Department of Industries, Commerce and Technical Education/TEVTA.

\g Field consultants to be hired for direct implementation in specific areas, the need for which will be identified by PMU and approved by PSC with No Objection from IFAD.

# ANNEX-2: RESULT BASED MONITORING (RBM) INDICATORS

| Results Hierarchy | Indicators |  |  |  | Means of Verification |  |  |  | Assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Name | Baseline | Mid-Term | End Target | Source | Frequency | Responsibility |  |  |
| Outreach | 1 Persons receiving services promoted or supported by the project |  |  |  | surveys, service providers' records, MIS system | baseline, mid term and completion, yearly | PMU | A baseline survey is conducted; Project approach and timelines are adhered to; An efficient M&E system is developed and implemented |  |
|  | Females - Females |  | 87,500 | 196,250 |  |  |  |  |  |
|  | Males - Males |  | 262,500 | 588,750 |  |  |  |  |  |
|  | Young - Young people |  | 175,000 | 392,000 |  |  |  |  |  |
|  | Not Young - Number |  |  |  |  |  |  |  |  |
|  | Total number of persons receiving services - Number of people |  | 350,000 | 785,000 |  |  |  |  |  |
|  | 1.a Corresponding number of households reached |  |  |  | surveys, service providers' records, MIS system | baseline, mid term and completion, yearly | PMU |  |  |
|  | Women-headed households - Households |  | 87,500 | 196,250 |  |  |  |  |  |
|  | Non-women-headed households - Households |  | 262,500 | 588,750 |  |  |  |  |  |
|  | Households - Households |  | 350,000 | 785,000 |  |  |  |  |  |
|  | 1.b Estimated corresponding total number of households members |  |  |  | surveys, service providers' records, MIS system | baseline, mid term and completion, yearly | PMU |  |  |
|  | Household members - Number of people |  | 1,440,000 | 4,350,000 |  |  |  |  |  |
| Project Goal To contribute to poverty reduction, nutrition and food security of rural households in the Khyber Pakhtunkhwa Province | Beneficiary households reporting improved income |  |  |  | survey | completion | PMU | Security situation remains stable and allows implementation of project |  |
|  | Households - Number |  | 262,500 | 588,750 |  |  |  |  |  |
|  | Beneficiary households reporting to have improved their nutrition |  |  |  | survey | completion | PMU |  |  |
|  | Households - Percentage (%) |  | 20 | 60 |  |  |  |  |  |
| Development Objective Income of rural households enhanced in a sustainable manner | SF.2.1 Households satisfied with project-supported services |  |  |  | survey | completion | PMU | A baseline survey is conducted; Project approach and timelines are adhered to; an efficient M&E system is developed and implemented |  |
|  | Household members - Number of people |  | 1,740,000 | 3,480,000 |  |  |  |  |  |
|  | Women-headed households - Households |  | 78,500 | 157,000 |  |  |  |  |  |
|  | Households (%) - Percentage (%) |  | 40 | 80 |  |  |  |  |  |
|  | Households (number) - Households |  | 314,000 | 628,000 |  |  |  |  |  |
|  | SF.2.2 Households reporting they can influence decision-making of local authorities and project-supported service providers |  |  |  | survey | completion | PMU |  |  |
|  | Household members - Number of people |  | 1,650,000 | 3,850,000 |  |  |  |  |  |
|  | Women-headed households - Households |  | 15,000 | 30,000 |  |  |  |  |  |
|  | Households (%) - Percentage (%) |  | 38 | 89 |  |  |  |  |  |
|  | Households (number) - Households |  | 300,000 | 700,000 |  |  |  |  |  |
| Outcome 1. Enhanced capacity of smallholder farmers for increased market access (Professional Farmer Organizations and Farm Service Centres) | 2.2.2 Supported rural enterprises reporting an increase in profit |  |  |  | MIS system, service providers' records | baseline, yearly after mid-term and completion | PMU | Baseline established, farmers are willing to participate in PFO and FSC |  |
|  | Number of enterprises - Enterprises |  | 200 | 550 |  |  |  |  |  |
| Output 1.1 Support provided to Professional Farmers Organizations, Farm Service Centres and 4Ps and their members | 2.1.3 Rural producers’ organizations supported |  |  |  | MIS system, service providers' records | baseline, yearly and completion | PMU | farmers are interested to participate, and targeting guidelines developed |  |
|  | Rural POs supported - Organizations |  | 280 | 550 |  |  |  |  |  |
|  | Total size of POs - Organizations |  | 112,000 | 220,000 |  |  |  |  |  |
|  | Males - Males |  | 84,000 | 165,000 |  |  |  |  |  |
|  | Females - Females |  | 28,000 | 55,000 |  |  |  |  |  |
|  | Young - Young people |  | 56,000 | 110,000 |  |  |  |  |  |
| Output 1.2 Coaching of producers for increased capacity on business planning, production practices and market advice | 1.1.4 Persons trained in production practices and/or technologies |  |  |  | MIS system, service providers' records | baseline, yearly and completion | PMU | Updated BISP data on poverty available and targeting guidelines developed, nothing is hindering the participation of any of the categories of persons |  |
|  | Total number of persons trained by the project - Number of people |  |  |  |  |  |  |  |  |
|  | Men trained in crop - Males |  |  |  |  |  |  |  |  |
|  | Women trained in crop - Females |  |  |  |  |  |  |  |  |
|  | Young people trained in crop - Young people |  |  |  |  |  |  |  |  |
|  | Men trained in livestock - Males |  |  |  |  |  |  |  |  |
|  | Women trained in livestock - Females |  |  |  |  |  |  |  |  |
|  | Young people trained in livestock - Young people |  |  |  |  |  |  |  |  |
|  | Total persons trained in crop - Number of people |  | 110,000 | 320,000 |  |  |  |  |  |
|  | Total persons trained in livestock - Number of people |  |  |  |  |  |  |  |  |
| Output 1.3 Producer-Public-Private-Partnerships (4Ps) established | Producers engaged in 4P collaborations |  |  |  | MIS system, service providers' records | baseline, yearly and completion | PMU | Availability of farmers willing and interested in entering into 4Ps |  |
|  | Males - Number |  | 3,500 | 14,000 |  |  |  |  |  |
|  | Females - Number |  | 1,500 | 6,000 |  |  |  |  |  |
|  | total producers - Number of people |  | 5,000 | 20,000 |  |  |  |  |  |
|  | Young - Number |  | 2,500 | 20,000 |  |  |  |  |  |
|  | partnerships - Number |  | 5 | 20 |  |  |  |  |  |
| Outcome 2. Improved capacity for obtaining jobs and engage in entrepreneurship | 2.2.1 New jobs created |  |  |  | surveys, MIS system, service providers' records | baseline, yearly after mid-term and completion | PMU | Updated BISP data on poverty available and targeting guidelines available |  |
|  | Job owner - men - Males |  | 30,000 | 63,000 |  |  |  |  |  |
|  | New jobs - Jobs |  | 40,000 | 85,000 |  |  |  |  |  |
|  | Job owner - women - Females |  | 10,000 | 22,000 |  |  |  |  |  |
|  | Job owner - young - Young people |  | 20,000 | 45,000 |  |  |  |  |  |
| Output 2.1 Vocational, technical and entrepreneurial skills trainings provided | 2.1.2 Persons trained in income-generating activities or business management |  |  |  | MIS system, service providers' records | baseline, yearly and completion | PMU | all categories are interested and nothing is hindering their participation in the trainings |  |
|  | Females - Females |  | 9,000 | 18,000 |  |  |  |  |  |
|  | Males - Males |  | 6,000 | 12,000 |  |  |  |  |  |
|  | Young - Young people |  | 15,000 | 30,000 |  |  |  |  |  |
|  | Persons trained in IGAs or BM (total) - Number of people |  | 30,000 | 60,000 |  |  |  |  |  |
| Output 2.2 Provision of start-up capital for establishing business and self-employment | Start up provided for self-employment |  |  |  | MIS system, service providers' records | baseline, yearly and completion | PMU | Careful assessment of each households potential and endowments |  |
|  | Males - Number |  | 4,000 | 8,400 |  |  |  |  |  |
|  | Females - Number |  | 6,000 | 12,600 |  |  |  |  |  |
|  | Young - Number |  | 10,000 | 21,000 |  |  |  |  |  |
|  | total number of persons - Number |  | 20,000 | 42,000 |  |  |  |  |  |
| Output 2.3 Support to individuals entering the job market for the first employment | persons receiving support |  |  |  | MIS system, service providers' records | baseline, yearly and completion | PMU | Careful assessment of each households potential and endowments |  |
|  | Males - Number |  | 7,000 | 17,500 |  |  |  |  |  |
|  | Females - Number |  | 3,000 | 7,500 |  |  |  |  |  |
|  | young - Number |  | 10,000 | 25,000 |  |  |  |  |  |
|  | total persons - Number |  | 10,000 | 25,000 |  |  |  |  |  |
| Outcome 3. Increased availability of nutritious food and awareness | 1.2.8 Women reporting minimum dietary diversity (MDDW) |  |  |  | pro-WEA survey and MIS system | baseline, yearly after mid-term and completion | PMU | Persons trained do apply what communicated in the trainings. Value chains are nutrition sensitive |  |
|  | Women (%) - Percentage (%) |  | 20 | 40 |  |  |  |  |  |
|  | Women (number) - Females |  |  |  |  |  |  |  |  |
|  | Households (%) - Percentage (%) |  |  |  |  |  |  |  |  |
|  | Households (number) - Households |  | 150,000 | 500,000 |  |  |  |  |  |
|  | Household members - Number of people |  | 825,000 | 2,750,000 |  |  |  |  |  |
|  | Women-headed households - Households |  |  |  |  |  |  |  |  |
|  | Non-women-headed households - Households |  |  |  |  |  |  |  |  |
| Output 3.1 Households provided with nutrition education | 1.1.8 Households provided with targeted support to improve their nutrition |  |  |  | COI survey and MIS system | baseline, yearly and completion | PMU | Noting (security / customary laws) is hindering the participation of anyone (especially women) to attend the trainings. Trainings are suitably scheduled |  |
|  | Total persons participating - Number of people |  | 300,000 | 700,000 |  |  |  |  |  |
|  | Males - Males |  | 85,000 | 175,000 |  |  |  |  |  |
|  | Females - Females |  | 215,000 | 525,000 |  |  |  |  |  |
|  | Households - Households |  | 300,000 | 700,000 |  |  |  |  |  |
|  | Household members benefitted - Number of people |  | 1,650,000 | 3,850,000 |  |  |  |  |  |
|  | Young - Young people |  | 150,000 | 300,000 |  |  |  |  |  |
| Outcome 4. Capacity for policy dialogue/reform strengthened (Farmer Services Centre Act, cooperatives act, seed act amended) | Policy 3 Existing/new laws, regulations, policies or strategies proposed to policy makers for approval, ratification or amendment |  |  |  |  | baseline, yearly after mid-term and completion |  | Willingness of policy makers and other key stakeholders to provide enabling environment |  |
|  | Number - Number |  | 2 | 5 |  |  |  |  |  |
| Output 4.1 Policy development and reform supported | Policy 1 Policy-relevant knowledge products completed |  |  |  |  | baseline, yearly and completion |  |  |  |
|  | Number - Knowledge Products |  | 2 | 5 |  |  |  |  |  |
|  | Policy 2 Functioning multi-stakeholder platforms supported |  |  |  |  | baseline, yearly and completion |  |  |  |
|  | Number - Platforms |  | 0 | 1 |  |  |  |  |  |

# ANNEX-3(A): MAP OF THE AGRIBUSINESS HUBS AND SUPPLY CHAIN CLUSTERS

# ANNEX-3(B): AGRIBUSINESS HUBS AND SUPPLY CHAIN INTERVENTIONS AND TENTATIVE INVESTMENT OUTLAY

| Cluster | Interventions | Outputs | Allocation |
| --- | --- | --- | --- |
| The Southern Agribusiness Cluster: | - Prioritization of supply chains covering, halal meat, dairy (benefiting from the river Indus banks), cereals (bio-fortified wheat), grapes, citrus (seedless oranges, lime and lemons), rose/floriculture, nuts, coffee, and high value vegetables - Matching investment in the upgrading of supply chains through PFO/PPPPs/FSCs and value addition/processing promotion - Capacity building for quality certification - Good Agricultural Practices (GAP), organic, Good Manufacturing Practices, Hazard Analysis and Critical Control Points (HACCP), FMD free zone for livestock | - Hub/free economic zones at DI Khan creating employment and income opportunities - - 150 PFOs; 4 PPPs and 8 FSCs - 10,000 Self-employment in all sectors; 6000 youth job market integration in all sectors; and, 6000 youth employment in agribusiness | PKR. 6940 million |
| The Central Agribusiness Cluster | - Prioritization of value chains with focus on citrus (oranges), peaches, pears, lychees, vegetables, strawberries, organic brown sugar, dairy and other products - Supply chain development taking advantage of the Rashakai economic zone for agribusiness and employment creation of youth - Capacity building and matching investments in the upgrading of supply chains - Structured/vertical farming and high value production | - Hub of this cluster will be Mardan - 125 PFOs; 4 PPPs; and, 8 FSCs - 10,000 Self-employment; 6000 youth job market integration in all sectors and, 6000 youth employment in agribusiness | PKR. 6932 million |
| The Northern Agribusiness Cluster | - Promotion of Horticulture - Supply chain development taking advantage of the tourism/agro tourism promote pome and stone fruits, peaches, off-season vegetables, buck wheat, saffron, medicinal and aromatic plants, aromatic rice and dairy/livestock | - Hub of this cluster will be Mingora - 125 PFOs; 4 PPPs and, 8 FSCs - 10,000 Self-employment; 6000 youth job market integration in all sectors; and, 6000 youth employment in agribusiness | PKR. 6932 million |
| The Eastern Agribusiness Cluster | - Diversified agribusiness development - Production of high value off-season vegetables and pome fruit, potato, maize corn - Development and organization of dairy production | - Hub of this cluster will be Mansehra - 100 PFOs; 4 PPPs; and, 8 FSCs - 10,000 Self-employment; 6000 youth job market integration in all sectors; and, 6000 youth employment in agribusiness | PKR. 6925 million |
| The Chitral Natural Products Agribusiness Cluster | - Organic and natural farming zone - Agri-product development such ad buck wheat, saffron, medicinal and aromatic plants, potato, off-season vegetables and nutraceuticals industry development. | - Hub of this cluster will be Chitral proper - 50 PFOs; 4 PPPs; and, 3 FSCs - 2000 Self-employment; 1000 youth job market integration in all sectors; and, 1000 youth employment in agribusiness | PKR. 1270 million |

http://extwprlegs1.fao.org/docs/pdf/pak173417.pdf

Batagram, D.I. Khan, Kohistan Kolai Palas, Kohistan Upper, Kohistan Lower, North Waziristan, South Waziristan, Shangla, Tank and Tor Garh.

Employment Trends, 2018, Ministry of Statistics, Government of Pakistan

World Bank, Khyber Pakhtunkhwa Irrigated Agriculture Improvement Project, 2018

https://pssp.ifpri.info/2020/05/28/blog-post-will-remittances-be-the-same/

Sector Study on Demand Driven Competency Based Training in Potential Sectors  of Khyber Pakhtunkhwa 2016-17, NAVTTC

Global Climate Risk Index 2020, www.germanwatch.org/en/cri