## Summary
KHYBER PAKHTUNKHWA RURAL ECONOMIC TRANSFORMISSION PROJECT (KP-RETP)
PLANNING & DEVELOPMENT DEPARTMENT
DRAFT ANNUAL WORK PLAN / BUDGET FOR FY 2023-24 & 2024-25
SUMMARY
(In Million)
Results # | Objectives/Expected Results | Total Project Cost (as per PC-1) |  | Planned Cost (2023-24 & 2024-25) |  | Financial Ratio |  |  | Annual Expenditure (2023-24) | % | Progressive Expenditure | % | Comments
[6 empty] | IFAD | GoKP | Benef./ Private Sector
|  | PKR | USD | PKR | USD | PKR | PKR | PKR | PKR |  | PKR
1. Agribusiness Development
A | Professional Farmers Organisations (PFOs) Development | 8667.803 | 50.9871 | 698.9481 | 4.1115 | 489.2637 | 0 | 209.6844 | 0 | 0% | 0 | 0%
B | Strengthening Public-Private Partnerships | 1402.45 | 8.2497 | 69.0314 | 0.40607 | 34.5157 | 0 | 34.5157 | 0 | 0% | 0 | 0%
C | Farm Services Companies | 4501.665 | 26.4804 | 272.6723 | 1.604 | 136.3361 | 0 | 136.3361 | 0 | 0% | 0 | 0%
D | Strengthening Institutional Services | 816.099 | 4.8006 | 110.487 | 0.64992 | 77.3409 | 33.1461 | 0 | 0 | 0% | 0 | 0%
E | Agribusiness Mobilization Partner /f | 613.466 | 3.6086 | 116.4908 | 0.68524 | 88.533 | 27.9578 | 0 |  | 0% |  | 0%
Sub-Total |  | 16001.483 | 94.1264 | 1267.6296 | 7.4566 | 825.9894 | 61.1039 | 380.5363 | 0 | 0% | 0 | 0%
2. Skill Development & Employment Promotion
A | Vocational and Entrepreneurship Training | 3175.398 | 18.6788 | 31.0368 | 0.18257 | 26.3813 | 4.6555 | 0 | 0 | 0% | 0 | 0%
B | Start-up Capital for Self-Employment | 2191.889 | 12.8935 | 15.5184 | 0.091285 | 6.5177 | 9.0007 | 0 | 0 | 0% | 0 | 0%
C | Job Market Integration/Internship | 5250.158 | 30.8833 | 51.675 | 0.30397 | 25.8375 | 25.8375 | 0 | 0 | 0% | 0 | 0%
D | Institutional support services | 694.701 | 4.0865 | 113.8527 | 0.66972 | 79.6969 | 34.1558 | 0 | 0 | 0% | 0 | 0%
E | Institutional Strengthening | 134.554 | 0.79149 | 37.8103 | 0.22241 | 26.4672 | 11.3431 | 0 | 0 | 0% | 0 | 0%
Sub-Total |  | 11446.7 | 67.3335 | 249.8932 | 1.47 | 164.9006 | 84.9926 | 0 | 0 | 0% | 0 | 0%
3. Project Management & Policy Support
I | CAPITAL COST
| A) Project Management Unit (PMU) | 67.573 | 0.39749 | 125.735 | 0.73962 | 94.0728 | 30.6004 | 1.0619 | 0 | 0% | 0 | 0%
| B) Regional Coordination Units (RCU's) | 143.662 | 0.84507 | 254.25 | 1.4956 | 195.7725 | 58.4775 | 0 | 0 | 0% | 0 | 0%
II | ESTABLISHMENT RECURING COST
| A) Project Management Unit (PMU) | 60.7365 | 0.35727 | 187.1889 | 1.1011 | 136.8596 | 50.3293 | 0
| B) Regional Coordination Units (RCU's) | 71.73 | 0.42194 | 268.51 | 1.5795 | 210.4984 | 58.0116 | 0
II | Un-allocated | 2473.87 | 14.5522
Sub-Total |  | 2817.5714 | 16.5739 | 835.6839 | 4.9158 | 637.2033 | 197.4187 | 1.0619 | 0 | 0% | 0 | 0%
GRAND TOTAL |  | 30265.7544 | 178.0338 | 2353.2067 | 13.8424 | 1628.0933 | 343.5152 | 381.5982 | 0 | 0% | 0 | 0%

## 1. Agribusiness Development
KHYBER PAKHTUNKHWA RURAL ECONOMIC TRANSFORMISSION PROJECT (KP-RETP)
PLANNING & DEVELOPMENT DEPARTMENT
ANNUAL WORK PLAN / BUDGET FOR FY 2023-24 & 2024-25
1. AGRIBUSINESS DEVELOPMENT
(Rs.in Million)
S.NO | DETAILED COST |  |  | Approved PC-1 |  |  | 2023-24 |  | 2024-25 |  |  |  | Planned Physical | Financial Ratio |  |  |  | REMARKS
|  |  |  | Unit Cost | Physical Targets | Total Project Cost | Qtr 3 | Qtr 4 | Qtr 1 | Qtr 2 | Qtr 3 | Qtr 3 |  | IFAD | GoKP | Benef./ Private Sector | TOTAL
I | INVESTMENT COST
| A | Professional Farmers Organisations (PFOs) Development
|  | 1 | Mobilisation and Registration of FOs /a |  | 550 | [7 empty] | 45
|  | 2 | Business Development Planning |  | 550 | [7 empty] | 45
|  | 3 | Leveraging FOs Investment
|  |  | Sothern Agribusiness Cluster | 14.653 | 150 | 2368.5587 | [6 empty] | 10 | 108.7253 |  | 46.5965 | 155.3218 | 6% annual increased as per PC-1 (70% IFAD & 30% Beneficiary)
|  |  | Northern Agribusiness Cluster | 14.653 | 125 | 1968.2401 | [6 empty] | 10 | 108.7253 |  | 46.5965 | 155.3218
|  |  | Central Agribusiness Cluster | 14.653 | 125 | 1971.2222 | [6 empty] | 10 | 108.7253 |  | 46.5965 | 155.3218
|  |  | Eastern Agribusiness Cluster | 14.653 | 100 | 1570.9036 | [6 empty] | 10 | 108.7253 |  | 46.5965 | 155.3218
|  |  | Chitral Agribusiness Cluster | 14.653 | 50 | 788.8784 | [6 empty] | 5 | 54.3626 |  | 23.2983 | 77.6609
| Sub Total |  |  |  |  | 8667.803 | [7 empty] | 489.2637 | 0 | 209.6844 | 698.9481
| B | Strengthening Public-Private Partnerships
|  | 1 | Mobilisation and Match Making /b |  | 20 | [7 empty] | 1
|  | 2 | Business Development Planning |  | 20 | [7 empty] | 1
|  | 3 | Leveraging Private Sector Investment /c | 65.124 | 20 | 1402.45 | [6 empty] | 1 | 34.5157 |  | 34.5157 | 69.0314 | 6% annual increased as per PC-1 (50% IFAD & 50% Beneficiary)
| Sub Total |  |  |  |  | 1402.45 | [7 empty] | 34.5157 | 0 | 34.5157 | 69.0314
| C | Farm Services Companies
|  | 1 | Mobilisation and Registration |  | 35
|  | 2 | Business Development Planning |  | 35
|  | 3 | Leveraging Investment in FSC
|  |  | Leveraging Investment in FSC | 128.619 | 35 | 4501.665 | [6 empty] | 2 | 136.3361 |  | 136.3361 | 272.6723 | 6% annual increased as per PC-1 (50% IFAD & 50% Beneficiary)
| Sub Total |  |  |  |  | 4501.665 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 136.3361 | 0 | 136.3361 | 272.6723
| D | Strengthening Institutional Services
|  | 1 | Policy Reforms /d | 17.944 | 6 | 137.481 | [6 empty] | 1 | 13.3144 | 5.7062 |  | 19.0206 | IFAD = 70% GoKP = 30%
|  | 2 | Agriculture/Livestock Research Support Services /e | 86.289 | 7 | 678.618 | [6 empty] | 1 | 64.0264 | 27.4399 |  | 91.4663
| Sub Total |  |  |  |  | 816.099 | [7 empty] | 77.3409 | 33.1461 | 0 | 110.487
| E | Agribusiness Mobilization Partner /f |  | 109.897 | 5 | 613.466 | [6 empty] | 1 | 88.533 | 27.9578 |  | 116.4908 | 5% annual increased as per PC-1 (70% IFAD & 30% Beneficiary)
| Sub Total |  |  |  |  | 613.466 | [7 empty] | 88.533 | 27.9578 | 0 | 116.4908
Grand Total | [5 empty] | 16001.483 | [6 empty] | 2 | 825.9894 | 61.1039 | 380.5363 | 1267.6296

## 2. Skill Development and Employ
KHYBER PAKHTUNKHWA RURAL ECONOMIC TRANSFORMISSION PROJECT (KP-RETP)
PLANNING & DEVELOPMENT DEPARTMENT
ANNUAL WORK PLAN / BUDGET FOR FY 2023-24 & 2024-25
2. SKILLS DEVELOPMENT AND EMPLOYMENT PROMOTION
(Rs.in Million)
S.NO | DETAILED COST |  |  | Unit | Approved PC-1 |  |  | 2023-24 |  | 2024-25 |  |  |  | Planned Physical | Financial Ratio |  |  |  | REMARKS
[5 empty] | Unit Cost | Physical Targets | Total Project Cost | Qtr 3 | Qtr 4 | Qtr 1 | Qtr 2 | Qtr 3 | Qtr 3 |  | IFAD | GoKP | Benef./ Private Sector | TOTAL
I | INVESTMENT COST
| A | Vocational and Entrepreneurship Training
|  | 1 | Vocational/Technical& Enterpreneurship Training | Trainee | 0.0488 | 60000 | 3175.398 | [6 empty] | 600 | 26.3813 | 4.6555 |  | 31.0368 | IFAD = 85% GoKP = 15%
| B | Start-up Capital for Self-Employment |  | Trainee | 0.0488 | 42000 | 2191.889 | [6 empty] | 300 | 6.5177 | 9.0007 |  | 15.5184 | IFAD = 42% GoKP = 58%
| C | Job Market Integration/Internship |  | Youth | 0.195 | 25000 | 5250.158 | [6 empty] | 250 | 25.8375 | 25.8375 |  | 51.675 | IFAD = 50% GoKP = 50%
| D | Institutional support services
|  | 1 | Policy Reforms /d | lumsum | 102.57 | 6 | 694.701 | [6 empty] | 1 | 79.6969 | 34.1558 |  | 113.8527 | IFAD = 70% GoKP = 30%
|  | 2 | Engagement for Job Placement /e | Placement |  | 25000 | [7 empty] | 0
| Sub Total | [5 empty] | 11312.146 | [7 empty] | 138.4334 | 73.6495 | 0 | 212.0829
| E | Institutional Strengthening
|  | 1 | Institutional strengthening for skills /g | lumsum | 27.678 | 5 | 116.99 | [6 empty] | 1 | 21.1183 | 9.0507 |  | 30.169 | IFAD = 70% GoKP = 30%
|  | 2 | Technical assistance for skills development /h | [12 empty] | 0
|  | a | Job Market Study and Outlook /i | Study | 4.884 | 2 | 10.632 | [6 empty] | 1 | 3.7949 | 1.6264 |  | 5.4212 | IFAD = 70% GoKP = 30%
|  | b | Training Need Assessment of Instructors /j | TNA | 1.628 | 2 | 3.544 | [6 empty] | 1 | 1.265 | 0.54212 |  | 1.8071
|  | c | Training of Instructors /k | Event | 0.372 | 8 | 3.388 | [6 empty] | 1 | 0.28904 | 0.12388 |  | 0.41292
|  |  | Sub Total |  |  |  | 17.564 | [7 empty] | 5.3489 | 2.2924 | 0 | 7.6412
| Sub Total | [5 empty] | 134.554 | [7 empty] | 26.4672 | 11.3431 | 0 | 37.8103
Grand Total | [6 empty] | 11446.7 | [7 empty] | 164.9006 | 84.9926 | 0 | 249.8932

## 3.Proj Management Unit
KHYBER PAKHTUNKHWA RURAL ECONOMIC TRANSFORMISSION PROJECT (KP-RETP)
PLANNING & DEVELOPMENT DEPARTMENT
ANNUAL WORK PLAN / BUDGET FOR FY 2023-24 & 2024-25
3. PROJECT MANAGEMENT UNIT
S.NO |  |  | ACTIVITY | Approved PC-1 |  | 2023-24 |  | 2024-25 |  |  |  | Planned Physical | Financial Ratio |  |  |  | REMARKS
|  |  |  | Unit Cost | Physical Targets | Qtr 3 | Qtr 4 | Qtr 1 | Qtr 2 | Qtr 3 | Qtr 3 |  | IFAD | GoKP | Benef./ Private Sector | TOTAL
I | INVESTMENT COST
| A | Project Management Unit
|  | 1 | Office Establishment and Equipment
|  |  | Computers/laptops | 350000 | 20 | [6 empty] | 20 | 5.39 | 1.61 |  | 7 | IFAD Share 77 percent and GoKP Share 23 percent
|  |  | Printers 3 in 1 | 200000 | 4 | [6 empty] | 4 | 0.616 | 0.184 |  | 0.8
|  |  | UPS/Internet Connectivity | 200000 | 1 | [6 empty] | 1 | 0.154 | 0.046 |  | 0.2
|  |  | Power Generator/ Solar System | 3000000 | 1 | [6 empty] | 1 | 2.31 | 0.69 |  | 3
|  |  | Photocopier | 700000 | 1 | [6 empty] | 1 | 0.539 | 0.161 |  | 0.7
|  |  | Mobile Phone | 150000 | 15 | [6 empty] | 15 | 1.7325 | 0.5175 |  | 2.25
|  |  | Furniture and Fixtures | 250000 | 20 | [6 empty] | 20 | 3.85 | 1.15 |  | 5
|  |  | Air Conditioners (DC Inverter) | 275000 | 15 | [6 empty] | 15 | 3.1763 | 0.94875 |  | 4.125
|  |  | Overhead Projector/ multimedia | 450000 | 1 | [6 empty] | 1 | 0.3465 | 0.1035 |  | 0.45
|  |  | Refrigerator & Water Dispensor | 300000 | 1 | [6 empty] | 1 | 0.231 | 0.069 |  | 0.3
|  |  | Conference Room equipment and Furniture | 1500000 | 1 | [6 empty] | 1 | 1.155 | 0.345 |  | 1.5
|  |  | LCD/LED | 350000 | 2 | [6 empty] | 2 | 0.539 | 0.161 |  | 0.7
|  |  | Heaters | 61000 | 1 | [6 empty] | 1 | 0.04697 | 0.01403 |  | 0.061
|  |  | Telephone Exchange | 500000 | 1 | [6 empty] | 1 | 0.385 | 0.115 |  | 0.5
|  |  | Miscellaneous | 5000000 | 1 | [6 empty] | 1 | 3.85 | 1.15 |  | 5
|  | Sub Total | [10 empty] | 24.3212 | 7.2648 | 0 | 31.586
|  | 2 | Vehicles for PMU | [12 empty] | 0
|  |  | Vehicles - DC Pickups | 14000000 | 5 | [6 empty] | 5 | 53.9 | 16.1 | 0 | 70 | IFAD Share 77 percent and GoKP Share 23 percent
|  |  | Vehicles - Sedan Car | 5000000 | 3 | [6 empty] | 3 | 11.55 | 3.45 | 0 | 15
|  |  | Motorcycles | 150000 | 2 | [6 empty] | 2 | 0.231 | 0.069 | 0 | 0.3
|  | Sub Total | [10 empty] | 65.681 | 19.619 | 0 | 85.3
|  | 3 | Monitoirng and Evaluation
|  |  | Baseline studies | 5000000 | 5 | [6 empty] | 1 | 2.4155 | 2.2054 | 0.63012 | 5.251 | IFAD Share 46 percent and GoKP Share 42 & Beneficiary Share 12 percent
|  |  | Nutrition Sensitive Commodity Chains Prioritization | 3426038 | 1 | [6 empty] | 1 | 1.6551 | 1.5112 | 0.43176 | 3.598
|  |  | Knowledge Management and Communication /a | 2000000 | 5 | [6 empty] | 0 | 0 | 0 | 0 | 0
|  |  | Evlauation and Technical Sutdies | 2000000 | 2 | [6 empty] | 0 | 0 | 0 | 0 | 0
|  |  | Impact Evaluation and Project Completion Report | 5000000 | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0
|  | Sub Total | [10 empty] | 4.0705 | 3.7166 | 1.0619 | 8.849
| Sub Total (A) | [11 empty] | 94.0728 | 30.6004 | 1.0619 | 125.735
| B | Regional Coordination Units
|  | 1 | Equipment
|  |  | Laptops | 350000 | 25 | [6 empty] | 16 | 6.7375 | 2.0125 | 0 | 8.75 | IFAD Share 77 percent and GoKP Share 23 percent
|  |  | Desktop Computers | 300000 | 10 | [6 empty] | 8 | 2.31 | 0.69 | 0 | 3
|  |  | 3 in 1 Printers | 200000 | 8 | [6 empty] | 8 | 1.232 | 0.368 | 0 | 1.6
|  |  | Photocopier | 700000 | 4 | [6 empty] | 4 | 2.156 | 0.644 | 0 | 2.8
|  |  | Overhead Projector/ multimedia | 450000 | 4 | [6 empty] | 4 | 1.386 | 0.414 | 0 | 1.8
|  |  | LCD/LED | 350000 | 4 | [6 empty] | 4 | 1.078 | 0.322 | 0 | 1.4
|  |  | Air Conditioners | 275000 | 12 | [6 empty] | 12 | 2.541 | 0.759 | 0 | 3.3
|  |  | Generators/ solar systems | 2000000 | 4 | [6 empty] | 4 | 6.16 | 1.84 | 0 | 8
|  |  | Furniture & Fixture | 1750000 | 4 | [6 empty] | 4 | 5.39 | 1.61 | 0 | 7
|  |  | Refrigerator & Water Dispensor | 300000 | 4 | [6 empty] | 4 |  |  |  | 1.2
|  |  | Miscellaneous | 2000000 | 4 | [6 empty] | 4 | 6.16 | 1.84 | 0 | 8
|  | Sub Total | [10 empty] | 35.1505 | 10.4995 | 0 | 46.85
|  | 2 | Vehicles | [12 empty] | 0
|  |  | Vehicles - DC Pickups | 14000000 | 12 | [6 empty] | 12 | 129.36 | 38.64 | 0 | 168 | IFAD Share 77 percent and GoKP Share 23 percent
|  |  | Vehicles - Sedan Cars | 5000000 | 8 | [6 empty] | 8 | 30.8 | 9.2 | 0 | 40
|  |  | Motorcycles | 150000 | 4 | [6 empty] | 4 | 0.462 | 0.138 | 0 | 0.6
|  | Sub Total | [10 empty] | 160.622 | 47.978 | 0 | 208.6
| Sub Total (B) | [11 empty] | 195.7725 | 58.4775 | 0 | 255.45
Total Investment Cost (A+B) | [12 empty] | 289.8453 | 89.0779 | 1.0619 | 381.185
II | RECURRENT COST
| A | Project Management Unit
|  | 1 | Project Management Staff
|  | a | Project Director | 500000 | 84 | [6 empty] | 18 | 6.3 | 2.7 | 0 | 9 | IFAD Share 70 percent and GoKP Share 30 percent
|  | b | Project Coodinator | 500000 | 84 | [6 empty] | 24 | 8.4 | 3.6 | 0 | 12
|  | c | Manager Agribusiness Development | 300000 | 84 | [6 empty] | 18 | 3.78 | 1.62 | 0 | 5.4
|  | d | Manager Skills and Employment | 300000 | 84 | [6 empty] | 18 | 3.78 | 1.62 | 0 | 5.4
|  | e | Manager Finance & Administration | 500000 | 84 | [6 empty] | 24 | 8.4 | 3.6 | 0 | 12
|  | f | Manager M&E, KM and Communication | 300000 | 84 | [6 empty] | 18 | 3.78 | 1.62 | 0 | 5.4
|  | g | Manager Procurement | 300000 | 84 | [6 empty] | 18 | 3.78 | 1.62 | 0 | 5.4
|  | h | Manager Gender/Nutrition/Environment & Climate Change | 300000 | 84 | [6 empty] | 18 | 3.78 | 1.62 | 0 | 5.4
|  | i | Knowledge Management/Communication Officer | 200000 | 84 | [6 empty] | 18 | 2.52 | 1.08 | 0 | 3.6
|  | j | M&E Officer (2) | 200000 | 168 | [6 empty] | 36 | 5.04 | 2.16 | 0 | 7.2
|  | k | Contract Management Officer | 200000 | 84 | [6 empty] | 18 | 2.52 | 1.08 | 0 | 3.6
|  | l | Agribusiness Policy Specialists/ Consultants | 300000 | 84 | [7 empty] | 0 | 0 | 0 | 0
|  | m | Institutional Development Officer | 200000 | 84 | [6 empty] | 18 | 2.52 | 1.08 | 0 | 3.6
|  | n | Admin & HR Officer | 200000 | 84 | [6 empty] | 18 | 2.52 | 1.08 | 0 | 3.6
|  | o | Labour Market Specialist(s)/Consultant | 300000 | 84 | [7 empty] | 0 | 0 | 0 | 0
|  | p | Skill Development Specilist(s)/Consultant | 300000 | 84 | [7 empty] | 0 | 0 | 0 | 0
|  | q | Employment Policy Specialsit(s)/ Consultant | 300000 | 84 | [7 empty] | 0 | 0 | 0 | 0
|  | r | Accounts Officer | 200000 | 84 | [6 empty] | 18 | 2.52 | 1.08 | 0 | 3.6
|  | s | Budget & Finance Officer | 200000 | 84 | [6 empty] | 18 | 2.52 | 1.08 | 0 | 3.6
|  | t | Procurement Officer | 200000 | 84 | [6 empty] | 18 | 2.52 | 1.08 | 0 | 3.6
|  | u | IT Officer | 200000 | 84 | [6 empty] | 18 | 2.52 | 1.08 | 0 | 3.6
|  | v | Support Staff (PMU)
|  |  | Accounts Assistant (3) | 100000 | 252 | [6 empty] | 54 | 3.78 | 1.62 | 0 | 5.4 | IFAD Share 70 percent and GoKP Share 30 percent
|  |  | Admin Assistant | 100000 | 84 | [6 empty] | 18 | 1.26 | 0.54 | 0 | 1.8
|  |  | M&E Assistants (2) | 100000 | 168 | [6 empty] | 36 | 2.52 | 1.08 | 0 | 3.6
|  |  | Office Assistant (2) | 100000 | 168 | [6 empty] | 36 | 2.52 | 1.08 | 0 | 3.6
|  |  | Drivers (8) | 45000 | 672 | [6 empty] | 144 | 6.48 | 1.944 | 0 | 8.424 | IFAD Share 100%
|  |  | Peon (4) | 35000 | 336 | [6 empty] | 72 | 2.52 | 0.756 | 0 | 3.276
|  |  | Guards (4) | 35000 | 336 | [6 empty] | 72 | 2.52 | 0.756 | 0 | 3.276
|  |  | Gardeners (2) | 35000 | 168 | [6 empty] | 36 | 1.26 | 0.378 | 0 | 1.638
|  |  | Sweepers (2) | 35000 | 168 | [6 empty] | 36 | 1.26 | 0.378 | 0 | 1.638
|  | Sub Total | [10 empty] | 91.32 | 37.332 | 0 | 128.652
|  | 2 | Office Running Costs (PMU)
|  |  | Rent PMU | 550000 | 84 | [6 empty] | 18 | 6.93 | 2.97 | 0 | 9.9 | IFAD Share 70% GoKP Share 30%
|  |  | Utilities | 200000 | 84 | [6 empty] | 18 | 3.6 |  | 0 | 3.6
|  |  | Stationery and Supplies | 100000 | 84 | [6 empty] | 18 | 1.386 | 0.414 | 0 | 1.8 | IFAD Share 77% GoKP Share 23%
|  |  | POL | 80000 | 672 | [6 empty] | 18 | 1.44 |  | 0 | 1.44
|  |  | Vehicle O&M costs | 40000 | 672 | [6 empty] | 18 | 0.5544 | 0.1656 | 0 | 0.72 | IFAD Share 77% GoKP Share 23%
|  |  | Communication, postage, email, internet | 50000 | 84 | [6 empty] | 18 | 0.693 | 0.207 | 0 | 0.9
|  |  | Seminars, Workshops & Meetings | 200000 | 84 | [6 empty] | 18 | 2.772 | 0.828 | 0 | 3.6
|  |  | Office maintenance | 100000 | 84 | [6 empty] | 18 | 1.386 | 0.414 | 0 | 1.8
|  | Sub Total | [10 empty] | 18.7614 | 4.9986 | 0 | 23.76
|  | 3 | Travel Cost
|  |  | TA/DA (day) | 1095000 | 84 | [6 empty] | 18 | 15.1767 | 4.5333 | 0 | 19.71 | IFAD Share 77% GoKP Share 23%
|  |  | Rental Vehicles | 814050 | 84 | [6 empty] | 18 | 11.2827 | 3.3702 | 0 | 14.6529
|  |  | Air Tickets | 23000 | 245 | [6 empty] | 18 | 0.31878 | 0.09522 | 0 | 0.414
|  | Sub Total | [10 empty] | 26.7782 | 7.9987 | 0 | 34.7769
| Sub Total (A) | [11 empty] | 136.8596 | 50.3293 | 0 | 187.1889
| B | Regional Coordination Units
|  | 1 | Regional Coordination Office Staff
|  | a | Regional Coordinator (5) | 300000 | 420 | [6 empty] | 90 | 18.9 | 8.1 | 0 | 27 | IFAD Share 70 percent and GoKP Share 30 percent
|  | b | Regional M&E Officer (5) | 200000 | 420 | [6 empty] | 90 | 12.6 | 5.4 | 0 | 18
|  | c | Agribusiness/Public Private Producers Partnership (4P) Officer (5) | 200000 | 420 | [6 empty] | 90 | 12.6 | 5.4 | 0 | 18
|  | d | Gender & youth mainstreaming Officer | 200000 | 84 | [6 empty] | 90 | 12.6 | 5.4 | 0 | 18
|  | e | Budget/Finance Coordinator (5) | 200000 | 420 | [6 empty] | 90 | 12.6 | 5.4 | 0 | 18
|  | f | Support Staff
|  |  | Office Assistant (5) | 100000 | 420 | [6 empty] | 90 | 6.3 | 2.7 | 0 | 9 | IFAD Share 70 percent and GoKP Share 30 percent
|  |  | Drivers (20) | 45000 | 1680 | [6 empty] | 360 | 16.2 |  | 0 | 16.2
|  |  | Peon (10) | 35000 | 840 | [6 empty] | 180 | 6.3 |  | 0 | 6.3
|  |  | Guards (10) | 35000 | 840 | [6 empty] | 180 | 6.3 |  | 0 | 6.3
|  |  | Sweepers (5) | 35000 | 420 | [6 empty] | 90 | 3.15 |  | 0 | 3.15
|  | Sub Total | [10 empty] | 107.55 | 32.4 | 0 | 139.95
|  | g | Field Consultants | 20200000 | 7 | [6 empty] | 1 | 14.14 | 6.06 | 0 | 20.2 | IFAD Share 70 percent and GoKP Share 30 percent
|  | Sub Total | [10 empty] | 14.14 | 6.06 | 0 | 20.2
|  | 2 | Office Running Costs
|  |  | Rent RCU (4) | 150000 | 336 | [6 empty] | 72 | 7.56 | 3.24 | 0 | 10.8 | IFAD Share 70 percent and GoKP Share 30 percent
|  |  | Utilities (4) | 120000 | 336 | [6 empty] | 72 | 8.64 |  | 0 | 8.64
|  |  | Stationery and Supplies (4) | 100000 | 336 | [6 empty] | 72 | 5.544 | 1.656 | 0 | 7.2 | IFAD Share 77% GoKP Share 23%
|  |  | POL (4) | 50000 | 1680 | [6 empty] | 360 | 18 |  | 0 | 18
|  |  | Vehicle O&M costs | 35000 | 1680 | [6 empty] | 360 | 9.702 | 2.898 | 0 | 12.6 | IFAD Share 77% GoKP Share 23%
|  |  | Communication, postage, email, internet | 30000 | 336 | [6 empty] | 72 | 1.6632 | 0.4968 | 0 | 2.16
|  |  | Seminars, Workshops, Meetings | 150000 | 336 | [6 empty] | 72 | 8.316 | 2.484 | 0 | 10.8
|  |  | Office maintenance | 30000 | 336 | [6 empty] | 72 | 1.6632 | 0.4968 | 0 | 2.16
|  |  | Travelling and Daily Allowance | 2000000 | 84 | [6 empty] | 18 | 27.72 | 8.28 | 0 | 36
|  | Sub Total | [10 empty] | 88.8084 | 19.5516 | 0 | 108.36
| Sub Total (B) | [11 empty] | 210.4984 | 58.0116 | 0 | 268.51
Total Recurrent Cost (A+B) | [12 empty] | 347.358 | 108.3409 | 0 | 455.6989
Un-allocated |  |  |  | 2473.87 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0
G. TOTAL (Project Management Unit Cost) (Investment + Recurrent) | [12 empty] | 637.2033 | 197.4187 | 1.0619 | 836.8839

## Proj Management (2) (hidden)
S.NO |  |  | ACTIVITY | Approved PC-1 |  | Planned Physical (2023-24) | Financial Ratio |  |  |  | REMARKS
|  |  |  | Unit Cost | Physical Targets |  | IFAD | GoKP | Benef./ Private Sector | TOTAL
I | INVESTMENT COST
| A | Project Management Unit
|  | 1 | Office Establishment and Equipment
|  |  | Computers/laptops | 120000 | 10 | 10 | 0.9702 | 0.2898 |  | 1.26 | IFAD Share 77 percent and GoKP Share 23 percent
|  |  | Printers | 50000 | 4 | 4 | 0.1617 | 0.0483 |  | 0.21
|  |  | UPS/Internet Connectivity | 10000 | 1 | 1 | 0.00847 | 0.00253 |  | 0.011
|  |  | Power Generator | 1000000 | 1 | 1 | 0.8085 | 0.2415 |  | 1.05
|  |  | Photocopier | 35000 | 1 | 1 | 0.28336 | 0.08464 |  | 0.368
|  |  | Mobile Phone | 50000 | 15 | 15 | 0.60676 | 0.18124 |  | 0.788
|  |  | Furniture and Fixtures | 100000 | 10 | 10 | 0.8085 | 0.2415 |  | 1.05
|  |  | Air Conditioners (DC Inverter) | 90000 | 5 | 5 | 0.36421 | 0.10879 |  | 0.473
|  |  | Heaters | 61000 | 1 | 1 | 0.04697 | 0.01403 |  | 0.061
|  |  | Miscellaneous | 251000 | 1 | 1 | 0.19327 | 0.05773 |  | 0.251
|  | Sub Total |  |  |  |  | 4.2519 | 1.2701 | 0 | 5.522
|  | 2 | Vehicles for PMU
|  |  | Vehicles - DC Pickups | 8000000 | 5 | 5 | 32.3454 | 9.6616 | 0 | 42.007 | IFAD Share 77 percent and GoKP Share 23 percent
|  |  | Vehicles - Sedan Car | 3500000 | 3 | 3 | 8.4908 | 2.5362 | 0 | 11.027
|  |  | Motorcycles | 80000 | 2 | 2 | 0.12936 | 0.03864 | 0 | 0.168
|  | Sub Total |  |  |  |  | 40.9655 | 12.2365 | 0 | 53.202
|  | 3 | Monitoirng and Evaluation
|  |  | Baseline studies | 5000000 | 5 | 1 | 2.4155 | 2.2054 | 0.63012 | 5.251 | IFAD Share 46 percent and GoKP Share 42 & Beneficiary Share 12 percent
|  |  | Nutrition Sensitive Commodity Chains Prioritization | 3426038 | 1 | 1 | 1.6551 | 1.5112 | 0.43176 | 3.598
|  |  | Knowledge Management and Communication /a | 2000000 | 5 | 0 | 0 | 0 | 0 | 0
|  |  | Evlauation and Technical Sutdies | 2000000 | 2 | 0 | 0 | 0 | 0 | 0
|  |  | Impact Evaluation and Project Completion Report | 5000000 | 1 | 0 | 0 | 0 | 0 | 0
|  | Sub Total |  |  |  |  | 4.0705 | 3.7166 | 1.0619 | 8.849
| Sub Total (A) | [5 empty] | 49.288 | 17.2231 | 1.0619 | 67.573
| B | Regional Coordination Units
|  | 1 | Equipment
|  |  | Laptops | 120000 | 16 | 16 | 1.5523 | 0.46368 | 0 | 2.016 | IFAD Share 77 percent and GoKP Share 23 percent
|  |  | Desktop Computers | 80000 | 8 | 8 | 0.51744 | 0.15456 | 0 | 0.672
|  |  | 3 in 1 Printers | 55000 | 8 | 8 | 0.35574 | 0.10626 | 0 | 0.462
|  |  | Photocopier | 250000 | 4 | 4 | 0.8085 | 0.2415 | 0 | 1.05
|  |  | Overhead Projector | 150000 | 4 | 4 | 0.4851 | 0.1449 | 0 | 0.63
|  |  | LCD | 160000 | 4 | 4 | 0.51744 | 0.15456 | 0 | 0.672
|  |  | Air Conditioners | 90000 | 12 | 12 | 0.87318 | 0.26082 | 0 | 1.134
|  |  | Generators | 300000 | 4 | 4 | 0.9702 | 0.2898 | 0 | 1.26
|  |  | Furniture | 1000000 | 4 | 4 | 3.2348 | 0.96623 | 0 | 4.201
|  |  | Miscellaneous | 240000 | 4 | 4 | 0.77616 | 0.23184 | 0 | 1.008
|  | Sub Total |  |  |  |  | 10.0909 | 3.0142 | 0 | 13.105
|  | 2 | Vehicles
|  |  | Vehicles - DC Pickups | 8000000 | 12 | 12 | 77.6283 | 23.1877 | 0 | 100.816 | IFAD Share 77 percent and GoKP Share 23 percent
|  |  | Vehicles - Sedan Cars | 3500000 | 8 | 8 | 22.6419 | 6.7632 | 0 | 29.405
|  |  | Motorcycles | 80000 | 4 | 4 | 0.25872 | 0.07728 | 0 | 0.336
|  | Sub Total |  |  |  |  | 100.5289 | 30.0281 | 0 | 130.557
| Sub Total (B) | [5 empty] | 110.6197 | 33.0423 | 0 | 143.662
Total Investment Cost (A+B) | [6 empty] | 159.9078 | 50.2654 | 1.0619 | 211.235
II | RECURRENT COST
| A | Project Management Unit
|  | 1 | Project Management Staff
|  | a | Project Director | 500000 | 84 | 6 | 2.1 | 0.9 | 0 | 3 | IFAD Share 70 percent and GoKP Share 30 percent
|  | b | Project Coodinator | 400000 | 84 | 12 | 3.36 | 1.44 | 0 | 4.8
|  | c | Manager Agribusiness Development | 300000 | 84 | 6 | 1.26 | 0.54 | 0 | 1.8
|  | d | Managaer Skills and Employment | 300000 | 84 | 6 | 1.26 | 0.54 | 0 | 1.8
|  | e | Manager Finance | 300000 | 84 | 12 | 2.52 | 1.08 | 0 | 3.6
|  | f | Manager M&E, KM and Communication | 300000 | 84 | 6 | 1.26 | 0.54 | 0 | 1.8
|  | g | Social Inclusion and Youth Employment Specialist | 250000 | 84 | 6 | 1.05 | 0.45 | 0 | 1.5
|  | h | KM/Communication Specialists | 250000 | 84 | 6 | 1.05 | 0.45 | 0 | 1.5
|  | i | Environment and Climate Change Specialist | 250000 | 84 | 6 | 1.05 | 0.45 | 0 | 1.5
|  | j | Business Development Officer | 250000 | 84 | 6 | 1.05 | 0.45 | 0 | 1.5
|  | k | Agribusiness Policy Specialists/ Consultants | 250000 | 84 | 6 | 1.05 | 0.45 | 0 | 1.5
|  | l | Institutional Development Specialsits/ Consultants | 250000 | 84 | 6 | 1.05 | 0.45 | 0 | 1.5
|  | m | Labour Market Specialist(s) | 250000 | 84 | 6 | 1.05 | 0.45 | 0 | 1.5
|  | n | Skill Development Specilist(s)
|  | o | Employment Policy Specialsit(s) | 250000 | 84 | 6 | 1.05 | 0.45 | 0 | 1.5
|  | p | Accounts Officer | 150000 | 84 | 6 | 0.63 | 0.27 | 0 | 0.9
|  | q | Audit/Budget Officer | 150000 | 84 | 6 | 0.63 | 0.27 | 0 | 0.9
|  | r | Procurement Officer | 150000 | 84 | 6 | 0.63 | 0.27 | 0 | 0.9
|  | s | IT Officer | 150000 | 84 | 6 | 0.63 | 0.27 | 0 | 0.9
|  | t | Support Staff (PMU)
|  |  | Accounts Assistant | 70000 | 84 | 6 | 0.294 | 0.126 | 0 | 0.42 | IFAD Share 70 percent and GoKP Share 30 percent
|  |  | Administration Assistant | 70000 | 84 | 6 | 0.294 | 0.126 | 0 | 0.42
|  |  | HR Associate | 75000 | 84 | 6 | 0.315 | 0.135 | 0 | 0.45
|  |  | Contract and Grants Associate | 75000 | 84 | 6 | 0.315 | 0.135 | 0 | 0.45
|  |  | M&E Assistants (2) | 70000 | 168 | 6 | 0.294 | 0.126 | 0 | 0.42
|  |  | Office Assistant (2) | 70000 | 168 | 6 | 0.294 | 0.126 | 0 | 0.42
|  |  | Drivers (8) | 35000 | 672 | 6 | 0.21 |  | 0 | 0.21 | IFAD Share 100%
|  |  | Peon (4) | 30000 | 336 | 6 | 0.18 |  | 0 | 0.18
|  |  | Guards (4) | 30000 | 336 | 6 | 0.18 |  | 0 | 0.18
|  |  | Gardeners (2) | 30000 | 168 | 6 | 0.18 |  | 0 | 0.18
|  |  | Sweepers (2) | 25000 | 168 | 6 | 0.15 |  | 0 | 0.15
|  | Sub Total |  |  |  |  | 25.386 | 10.494 | 0 | 35.88
|  | 2 | Office Running Costs (PMU)
|  |  | Rent PMU | 450000 | 84 | 8 | 2.52 | 1.08 | 0 | 3.6 | IFAD Share 70% GoKP Share 30%
|  |  | Utilities | 80000 | 84 | 8 | 0.64 |  | 0 | 0.64
|  |  | Stationery and Supplies | 50000 | 84 | 12 | 0.462 | 0.138 | 0 | 0.6 | IFAD Share 77% GoKP Share 23%
|  |  | POL | 50000 | 672 | 48 | 2.4 |  | 0 | 2.4
|  |  | Vehicle O&M costs | 30000 | 672 | 48 | 1.1088 | 0.3312 | 0 | 1.44 | IFAD Share 77% GoKP Share 23%
|  |  | Communication, postage, email, internet | 50000 | 84 | 9 | 0.3465 | 0.1035 | 0 | 0.45
|  |  | Seminars, Workshops & Meetings | 70000 | 84 | 10 | 0.539 | 0.161 | 0 | 0.7
|  |  | Office maintenance | 30000 | 84 | 30 | 0.693 | 0.207 | 0 | 0.9
|  | Sub Total |  |  |  |  | 8.7093 | 2.0207 | 0 | 10.73
|  | 3 | Travel Cost
|  |  | TA/DA (day) | 1095000 | 84 | 6 | 5.0589 | 1.5111 | 0 | 6.57 | IFAD Share 77% GoKP Share 23%
|  |  | Rental Vehicles | 814050 | 84 | 9 | 5.6414 | 1.6851 | 0 | 7.3265
|  |  | Air Tickets | 23000 | 245 | 10 | 0.1771 | 0.0529 | 0 | 0.23
|  | Sub Total |  |  |  |  | 10.8774 | 3.2491 | 0 | 14.1265
| Sub Total (A) | [5 empty] | 44.9727 | 15.7638 | 0 | 60.7365
| B | Regional Coordination Units
|  | 1 | Regional Coordination Office Staff
|  | a | Regional Coordinator (5) | 300000 | 420 | 30 | 6.3 | 2.7 | 0 | 9 | IFAD Share 70 percent and GoKP Share 30 percent
|  | b | Regional M&E Officer (4 Agribusiness 4 Employment Total 8) | 150000 | 672 | 48 | 5.04 | 2.16 | 0 | 7.2
|  | c | Accountants (5) | 150000 | 420 | 30 | 3.15 | 1.35 | 0 | 4.5
|  | d | Support Staff
|  |  | Office Assistant (5) | 70000 | 420 | 30 | 1.47 | 0.63 | 0 | 2.1 | IFAD Share 70 percent and GoKP Share 30 percent
|  |  | Drivers (20) | 35000 | 1680 | 120 | 4.2 |  | 0 | 4.2
|  |  | Peon (10) | 30000 | 840 | 60 | 1.8 |  | 0 | 1.8
|  |  | Guards (10) | 25000 | 840 | 60 | 1.5 |  | 0 | 1.5
|  |  | Sweepers (5) | 25000 | 420 | 30 | 0.75 |  | 0 | 0.75
|  | Sub Total |  |  |  |  | 24.21 | 6.84 | 0 | 31.05
|  | e | Field Consultants | 20200000 | 7 | 1 | 14.14 | 6.06 | 0 | 20.2 | IFAD Share 70 percent and GoKP Share 30 percent
|  | Sub Total |  |  |  |  | 14.14 | 6.06 | 0 | 20.2
|  | 2 | Office Running Costs
|  |  | Rent RCU | 100000 | 336 | 30 | 2.1 | 0.9 | 0 | 3 | IFAD Share 70 percent and GoKP Share 30 percent
|  |  | Utilities | 50000 | 336 | 30 | 1.5 |  | 0 | 1.5
|  |  | Stationery and Supplies | 50000 | 336 | 30 | 1.155 | 0.345 | 0 | 1.5 | IFAD Share 77% GoKP Share 23%
|  |  | POL | 50000 | 1680 | 120 | 6 |  | 0 | 6
|  |  | Vehicle O&M costs | 35000 | 1680 | 120 | 3.234 | 0.966 | 0 | 4.2 | IFAD Share 77% GoKP Share 23%
|  |  | Communication, postage, email, internet | 30000 | 336 | 24 | 0.5544 | 0.1656 | 0 | 0.72
|  |  | Seminars, Workshops, Meetings | 50000 | 336 | 24 | 0.924 | 0.276 | 0 | 1.2
|  |  | Office maintenance | 15000 | 336 | 24 | 0.2772 | 0.0828 | 0 | 0.36
|  |  | Travelling and Daily Allowance | 2000000 | 7 | 1 | 1.54 | 0.46 | 0 | 2
|  | Sub Total |  |  |  |  | 17.2846 | 3.1954 | 0 | 20.48
| Sub Total (B) | [5 empty] | 55.6346 | 16.0954 | 0 | 71.73
Total Recurrent Cost (A+B) | [6 empty] | 100.6073 | 31.8592 | 0 | 132.4665
Un-allocated |  |  |  | 2190.35 | 0 | 0 | 0 | 0 | 0 | 0
G. TOTAL (Project Management Unit Cost) (Investment + Recurrent) | [6 empty] | 260.515 | 82.1245 | 1.0619 | 343.7014