INCEPTION REPORT

OF

BASELINE STUDY

SEP-2024

## Table of Contents (TOC)

| S. No | Nam of Content | Page No. |
| --- | --- | --- |
| 0 | Title Page | i-ii |
| 00 | Table of Contents | iii-iv |
| 000 | ACRONYMS | v |
| 1.0 | Executive Summary | 01 |
| 2.0 | Introduction | 02 |
|  | Background |  |
|  | Project Overview |  |
|  | Project Goal and Development Objective |  |
|  | Project Area and Target Group |  |
|  | Project Components |  |
|  | Project Implementation Strategy |  |
|  | Agribusiness Development Component |  |
| 3.0 | Specific objective of the Assignment | 03 |
|  | Consulting Firm Engagement |  |
|  | Project Clusters |  |
|  | Specific Objectives of the Assignment |  |
| 4.0 | Scope of Work | 04 |
|  | Consultant's Responsibilities |  |
| 5.0 | Deliverables | 03 |
|  | Baseline Inception Report |  |
|  | Baseline Report |  |
|  | Data and Reports: |  |
| 6.0 | Consultations with Stakeholders | 5 |
|  | Meetings |  |
| 7.0 | Conducting the Baseline Study | 5-13 |
|  | Objective of the Baseline Study |  |
|  | Study Design |  |
|  | Sampling and Sampling Technique |  |
|  | Data Collection Hierarchy for Agribusiness |  |
|  | Data Collection Methodology |  |
|  | Data Collection Modes |  |
|  | Team Composition for Conducting Baseline Study |  |
|  | Enumerator Training |  |

|  | Data Management and Quality Assurance |  |
| --- | --- | --- |
|  | Data Analysis |  |
|  | Ethical Considerations |  |
|  | Timeline |  |
| 8.0 | Limitations and Risks | 13-15 |
| 9.0 | Work Plan of the Baseline Study | 16 |
|  | Annexures | 17-36 |
|  | Annex-I: Questionnaire for Interviewing Individuals (HHs) |  |
|  | Annex-II: Questionnaire for Conducting Key Informants (KII) |  |

ACRONYMS

| Abbreviation | Description |
| --- | --- |
| BISP | Benazir Income Support Program |
| FSC | Farm Services Centre |
| GIS | Geographic Information System |
| HH | House Hold |
| IFAD | International Fund for Agriculture Development |
| KII | Key Informant Interview |
| KP | Khyber Pakhtunkhwa |
| NGO | Non-Governmental Organization |
| 4Ps | Public Private Producers Partnership |
| PFO | Professional Farmers Organization |
| PMU | Project Management Unit |
| PSC | Poverty Score Card |
| REPID | Rural Empowerment and Institutional Development |
| RETP | Rural Economic Transformation Project |
| TEVTA | Technical Education, Vocational Training Authority |

- Executive Summary:

Rural Empowerment and Institutional Development (REPID) is a National NGO engaged by PMU KP-RETP as consultant for conducting baseline for the Khyber Pakhtunkhwa Rural Economic Transformation Project (KP-RETP) in targeted project districts. REPID singed agreed with PMU KP-RETP on 6th September 2024, and will play a crucial role in fostering effective evidence creation and bench marking for the project interventions. The engagement of REPID was based on the experienced as a consulting firm for the will be engaged for provision of services for Baseline Study of the project following the Khyber Pakhtunkhwa Public Procurement Regulatory Authority (KP-PPRA) Rules, to the extent of their consistency with IFAD's Project Handbook & Procurement Guidelines, Financing Agreement and Letter to the Borrower (LTB),

The Objective of the bassline is to Conduct comprehensive surveys, focus group discussions and assessments to gather baseline data on agribusiness market system, farm business skills, employment status of rural youth and women in farm sector and non-farm sector, income level of households, landholdings/ownership status, prevailing cropping patterns, status of village-based Farmers Organizations (FOs) / cooperatives, cost of crop production and sources of investments undertaken by 220,000 small-scale farmers/ producers. comprehensive assessment regarding the prevalence of the different forms of malnutrition, causes of malnutrition and estimation of dietary gaps among women, adolescent girls and children in the project area. Situation analysis of market linkages for each PFO including both the demand and supply side, conduct market survey to identify gaps and shortcomings of the market linkages and provide a strategy to improve PFOs access to market.

The Final product of the survey report will be information regarding improvements in potentials of existing nutrition sensitive production system, possibility of inclusion of new nutrition sensitive value chain commodities and product lines based on area suitability. Identification of commodities whose development would create significant numbers of jobs either on- or off-farm. Assess the ongoing agribusiness of the different market actors, their present situation, role, and finally figure out the areas of interventions in the identified value chains for the actors including youth and rural women. Consultant will provide a detailed analysis of the value chains and provide recommendations on how the farmers/producers and their associations in selected agribusiness zones can be engaged in value chains in different roles (Supplier of inputs, producer, processor, transporter, traders and so on).

REPID will Make a profile of the value chains/mapping in the respective agribusiness zones. Assess the agribusiness market system, supporting environment (services, policies and rules regulations, infrastructure) and point out the market constraints. Provide skills Training Needs Assessment (TNA) related to potential roles in the nutrition sensitive value chains development. Evaluating existing capacities and knowledge levels of farmers and institutions regarding climate/environmental risk assessment and identifying climate adaptation/mitigation measures. Analyzing the job market challenges and opportunities for integrating 110,000 individuals (50% Women & 50 % youth) trained in the areas of skills for agribusiness, vocational/technical skills and jobs placement of fresh university graduates.

#### Introduction

  - Background: This brief report provides a detailed framework for the baseline study required for the KP-RETP, highlighting the key objectives, scope of work, and expected deliverables. It also elaborates on data collection sampling and methodology for collecting and analyzing data from about 1500 HHs in the Project Area. The consulting firm will play a crucial role in evaluating the project's impact and ensuring its alignment with the overarching goal of poverty reduction and rural development in Khyber Pakhtunkhwa.

  - Project Overview: The Islamic Republic of Pakistan has secured a loan from the International Fund for Agricultural Development (IFAD) for the Khyber Pakhtunkhwa – Rural Economic Transformation Project (KP-RETP). This initiative aims to tackle the primary causes of rural poverty and food insecurity in the Khyber Pakhtunkhwa province.

  - Project Goal and Development Objective: The primary goal of KP-RETP is to reduce poverty, enhance food and nutrition security, and strengthen the resilience of rural households. The development objective focuses on sustainably improving the incomes of rural households through climate-resilient, high-value agriculture and off-farm/non-farm employment opportunities.

  - Project Area and Target Group: KP-RETP will be implemented across all districts of Khyber Pakhtunkhwa, benefitting approximately 785,000 households. The project targets smallholder farmers, families within the Benazir Income Support Program - Poverty Score Card (BISP-PSC) category 0-40, food-insecure households, and rural women and youth.

#### Project Components:

    - Agribusiness Development: Formation of Professional Farmers Organizations (PFOs), development of public-private-producers partnerships (4Ps), Farm Service Companies, and Institutional Services.

    - Skills and Employment Promotion: Skills development for agribusiness, productive employment, start-up capital for self-employment, public-private internship programs for young graduates, and support to KP-TEVTA.

    - Project Management and Policy Support: Establishment of a dedicated Project Management Unit (PMU) for management, implementation coordination, policy support, and provision of technical assistance for institutional/capacity building.

  - Project Implementation Strategy: The project will follow an integrated approach, where agribusiness development will complement and support skills development and employment promotion. The Project Management Component will ensure smooth implementation, policy reform support, and sustainability of KP-RETP activities.

  - Agribusiness Development Component: The agribusiness development component will leverage the province's unique agro-climatic conditions to maximize income for small farmers.  This  will  be  achieved  through  institutional,  technological,  and  financial

interventions. The component includes the development of PFOs, 4Ps, Farm Services Companies, and institutional support services.

#### Objective of the Assignment

- Consulting Firm Engagement: An experienced consulting firm REPID has been engaged to conduct the Baseline Study, adhering to KP-PPRA rules and IFAD's guidelines, to assess the project's impact and identify areas of improvement. The Contract Agreement was signed on September 06, 2024 valid till December 05, 2024. Letter of Validity seeking extension of 45 days beyond December 05, 2024 has been submitted to the PMU.

#### Project Clusters:

Central

Agribusiness Cluster

Chitral

Agribusiness Cluster

Northern

Agribusiness Cluster

Project

Clusters

Southern

Agribusiness Cluster

Eastern

Agribusiness Cluster

  - Central Agribusiness Cluster: Peshawar, Charsada, Mardan, Swabi, Nowshera, Khyber, Mohmand

  - Northern Agribusiness Cluster: Lower Dir, Upper Dir, Malakand, Buner, Swat, Bajaur, Shangla

  - Eastern Agribusiness Cluster: Haripur, Abbottabad, Mansehra, Torghar, Batagram, Kolai Pallas, Upper Kohistan, Lower Kohistan

  - Southern Agribusiness Cluster: Kohat, Hangu, Kurram, Orakzai, Karak, Bannu, Lakki Marwat, D.I. Khan, South Waziristan Lower, South Waziristan Upper, North Waziristan, Tank

  - Chitral Agribusiness Cluster: Chitral Lower, Chitral Upper

#### Specific Objectives of the Assignment:

  - Assess the current status of 220,000 small-scale farmers.

  - Evaluate the capacities of farmers and institutions in assessing climate/environmental risks.

  - Analyze job market integration challenges for 110,000 individuals, focusing on skills development and self-employment readiness.

  - Set targets against indicators based on the gap between current and potential situations.

#### Scope of Work

The consultant will be responsible for the following tasks:

- Conducting comprehensive surveys, focus group discussions and assessments to gather baseline data on agribusiness market system, farm business skills, employment status of rural youth and women in farm sector and non-farm sector, income level of households, landholdings/ownership status, prevailing cropping patterns, status of village-based Farmers Organizations (FOs) / cooperatives, cost of crop production and sources of investments undertaken by 220,000 small-scale farmers/ producers.

- A comprehensive assessment regarding the prevalence of the different forms of malnutrition, causes of malnutrition and estimation of dietary gaps among women, adolescent girls and children in the project area.

- Situational analysis of market linkages for each PFO including both the demand and supply side, conduct market survey to identify gaps and shortcomings of the market linkages and provide a strategy to improve PFOs access to market.

- The survey report shall provide information regarding improvements in potentials of existing nutrition sensitive production system, possibility of inclusion of new nutrition sensitive value chain commodities and product lines based on area suitability.

- Identification of commodities whose development would create significant numbers of jobs either on- or off-farm.

- Assess the ongoing agribusiness of the different market actors, their present situation, role, and finally figure out the areas of interventions in the identified value chains for the actors including youth and rural women.

- Consultant will provide a detailed analysis of the value chains and provide recommendations on how the farmers/producers and their associations in selected agribusiness zones can be engaged in value chains in different roles (Supplier of inputs, producer, processor, transporter, traders and so on).

- Make a profile of the value chains/mapping in the respective agribusiness zones.

- Assess the agribusiness market system, supporting environment (services, policies and rules regulations, infrastructure) and point out the market constraints.

- Provide skills Training Needs Assessment (TNA) related to potential roles in the nutrition sensitive value chains development.

- Evaluating existing capacities and knowledge levels of farmers and institutions regarding climate/environmental risk assessment and identifying climate adaptation/mitigation measures.

- Analyzing the job market challenges and opportunities for integrating 110,000 individuals (50% Women & 50 % youth) trained in the areas of skills for agribusiness, vocational/technical skills and jobs placement of fresh university graduates.

#### Deliverables

- Expected Deliverables:

- Baseline Inception Report: will cover the baseline objectives, approach, methodology, team composition for the various Project Agribusiness Clusters, and detailed work plan for conducting the study and data analysis.

- Baseline Report: Comprehensive report covering ongoing agribusiness, farm business skills, employment status, income levels, value chain analysis, and recommendations for improvement.

- Data and Reports: All primary data collected, along with summaries of key meetings and discussions, are to be submitted in electronic format.

#### Consultation with Stakeholders:

- Meetings:

A series of consultative meetings under the Chairmanship of the Project Director KP-RETP was held to discuss arrangements for conducting the study, facilitation, data collection, Sampling, Data Analysis, and then reporting before and after the signing of the Contract Agreement. The 3 months Contract Agreement was signed between the Consulting firm and the Project (KP-RETP) on September 6, 2024. At the same time, the study design including Questionnaires both for interviewing the Individual households (HHs) and Key Informant Interviews from the Stakeholders was shared and approved by the Project Authorities.

## Conducting Baseline Study

#### . Objective of the Baseline Study:

The objective of this baseline study is to assess the socio-economic conditions of households in the Khyber Pakhtunkhwa (KP) province before the implementation of the Economic Transformation Project (KP-RETP). This study will focus on 1500 households, distributed across 05 Clusters of the Project, with a gender distribution of 75% male and 25% female respondents. The results will establish a benchmark for evaluating the impact of the project.

#### Study Design:

Sampling Framework:

  - Sample Size: 1500 households

#### Geographic Coverage:

    - All 05 Clusters of the Project in KP, ensuring proportional distribution of households across districts based on population size and relevance to the KP-RETP.

#### Gender Distribution:

    - Male Respondents: 75% (1125 respondents)

    - Female Respondents: 25% (375 respondents)

    - Youth Respondents: The above sampling of both Male and Female will also cover a certain number of Youth aged 15-29 representing the Youth in the community (50% youth and 25% female).

#### Sampling and Sampling Technique:

  - Stratified Random Sampling: The sample will be divided based on the following strata:

    - Geographical stratum: 05 Clusters

    - Gender stratum: 75% male, 25% female.

#### Multi-Stage Sampling Approach:

    - Stage 1: Selection of House Holds or villages within each Cluster

    - Stage 3: Random selection of households within these clusters, ensuring gender balance and stratification between target and control groups.

Pretesting:

A pilot survey will be conducted as part of the preparatory phase to test the feasibility and effectiveness of the survey methodology. This pretest will involve the completion of 10 survey forms per cluster to identify any potential issues or gaps in the questionnaire and data collection process. The data gathered from this pilot survey will be analyzed, and a detailed analysis report will be prepared to provide an overview of findings, ensuring the main survey can be executed smoothly and effectively.

#### Sampling size calculation:

The sample size for each region and district is determined based on the total population of each district, proportional to the overall sample size of 1500 households. This approach ensures that the sample distribution reflects the relative population sizes of the districts within each region. Below is the detailed methodology for calculating the sample size:

Sample Size Formula:

The calculation follows a proportional allocation method, which is based on the formula:

Where:

- Population of District is the population count for each district as per the latest census or projection.

- Total Population of Region is the sum of the populations of all districts within that region.

- Total Sample Size for Region is the target sample size for each region, based on the total sample size of 1500 households, distributed by population proportion.

Steps to Calculate Sample Size for Each District:

- Determine the proportion of each district’s population relative to the total population of the region.

- Multiply the region’s total sample size by the district’s population proportion to get the sample size for each district.

This ensures that larger districts with a higher population get a larger share of the sample, while smaller districts with a lower population get a smaller share.

Consolidated Sample Size region wise:

| Region | Percentage of Total | Target group Group | Male | Female | Youth (Male 15-29 years) | Youth (Female 15-29 years) | 30-45 years | 45-60 years |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Central | 37.33% | Total: 560 | 419 | 141 | 169 | 56 | 113 | 112 |
| 2. Northern | 23.53% | Total: 353 | 265 | 88 | 113 | 38 | 75 | 75 |
| 3. Eastern | 15.40% | Total: 231 | 173 | 58 | 113 | 38 | 75 | 75 |
| 4. Southern | 22.47% | Total: 337 | 253 | 84 | 113 | 38 | 75 | 75 |
| 5. Chitral | 1.27% | Total: 19 | 14 | 5 | 6 | 2 | 4 | 4 |

- Selection of Beneficiaries for the Interviews:

The KP-REAP target groups will fall under the category of smallholders (as per the definition of the Government < 5 Ha or 12 Acres or landless HHs. All the target HHs will be randomly selected as per the above mentioned methodology with PSC 0 – 40 range. Women and youth will be particularly targeted with specific interventions aiming at economic empowerment. The target groups (small farmers, youth and gender target groups) will be pre-identified through the implementing partners.

#### 18.0 Data Collection Methodology:

Data Collection Tools:

The data collection methodology for this study is designed to gather comprehensive, actionable insights through a structured and methodical approach. The methodology employs a detailed questionnaire complemented by rigorous pre-testing and ethical data collection practices to ensure validity, reliability, and cultural relevance.

Key Themes and Their Significance in Program Design

A comprehensive questionnaire will be designed for the baseline study, serving as a foundational tool to collect critical information across ten thematic areas. These themes are intended to provide insights into the current conditions and will also be used to inform the development of effective programmatic interventions. The following narrative outlines each theme, its significance at the baseline stage, and its role in shaping future interventions:

1. Demographic Information

Baseline Requirements:

Collecting demographic data such as age, gender, education, household size, and occupation is vital to understanding the socio-economic composition of the target population. Details about the respondent's relationship with the household head and geographic specifics (village, UC, tehsil, district) are essential for identifying community needs and contextualizing interventions.

Programmatic Interventions:

Demographic analysis will inform the equitable allocation of resources and helps design inclusive strategies that address the unique needs of different groups, particularly vulnerable populations like women, youth, and the elderly. For instance, literacy programs or vocational training may target less-educated segments, while livelihood support could be customized based on predominant occupations.

2. Agribusiness Development

Baseline Requirements:

Baseline data on services received, project awareness, and current needs will allow for assessing the reach and relevance of previous agribusiness initiatives. Understanding beneficiaries' perceptions of past services will help evaluate their effectiveness and areas for improvement.

Programmatic Interventions:

Interventions can be designed to enhance agribusiness productivity, such as access to modern farming techniques, input subsidies, and market linkages. Tailored support services can address the unmet needs of farmers and agribusiness operators, ensuring sustainable growth in the sector.

Formula for Confidence Interval & Standard Deviation:

REPID will conduct a survey of 1,500 households to analyze key metrics such as income, energy usage, or satisfaction levels by calculating the standard deviation and confidence intervals. The survey will begin with clear objectives and a well-designed questionnaire to capture relevant data points which ahs already been developed.  Once responses are collected, the data will be organized in statistical tools like Excel, SPSS Nova1. To calculate the standard deviation, the mean will be determined, deviations from the mean will be squared and summed, and the result will be divided by n−1n-1n−1 for a sample or nnn for a population, with the square root providing the standard deviation. For the confidence interval, REPID will select a confidence level (e.g., 95%), determine the Z-score (e.g., 1.96 for 95%), calculate the standard error of the mean (SE=snSE = \frac{s}{\sqrt{n}}SE=n​s​), compute the margin of error (ME=z⋅SEME = z \cdot SEME=z⋅SE), and construct the interval (CI=xˉ±MECI = \bar{x} \pm MECI=xˉ±ME). The findings will be reported using visualizations like histograms and bar graphs, with error bars representing confidence intervals. Results will be interpreted to provide insights into data variability and reliability, such as stating the average income and its variability or the confidence interval. This comprehensive analysis will ensure accurate and actionable insights for decision-making.

3. Project Goal

Baseline Requirements:

Determining the baseline household income, particularly from agricultural sales, establishes a starting point for measuring project impact. Challenges faced in generating income prior to the project highlight systemic issues that need addressing.

Programmatic Interventions:

Income-generation programs, such as training in value addition and entrepreneurship, can be introduced to maximize agricultural returns. Policy advocacy for fair market access or price stabilization mechanisms could address pre-existing barriers to income growth.

4. Development Objective

Baseline Requirements:

Understanding factors that influence income levels and decision-making at the household and community levels is crucial. Insights into the role of Producer Farmer Organizations (PFOs) will help evaluate their effectiveness and identify areas needing reinforcement.

Programmatic Interventions:

Strengthening PFOs through governance training, capacity building, and financial support ensures they can play a pivotal role in improving members’ livelihoods. Programs focusing on cooperative marketing and resource pooling could further enhance income stability.

5. Food Security and Nutrition

Baseline Requirements:

Women’s dietary diversity, access to food, and associated constraints will provide a clear picture of household nutritional security. Food group diversity serves as an indicator of dietary adequacy.

Programmatic Interventions:

Nutrition-focused interventions, such as promoting kitchen gardens, providing fortified food supplies, and conducting awareness campaigns on balanced diets, will address food insecurity. Special emphasis on women ensures that nutritional improvements benefit all family members.

6. Enterprise Profitability and Sustainability

Baseline Requirements:

Capturing baseline enterprise revenue, costs, and profit will provide insights into the economic viability of small businesses. Identifying challenges and strategies for profitability highlights areas requiring intervention.

Programmatic Interventions:

interventions that provide access to microcredit, technical assistance, and business mentoring will help enterprises scale sustainably. Initiatives focusing on market access and cost-efficient production methods can improve profitability and long-term sustainability.

7. Capacity Building for Organizations

Baseline Requirements:

Baseline data on governance, leadership, and decision-making within organizations will indicate their operational strength. Revenue and production volume data help gauge their economic contribution.

Programmatic Interventions:

Capacity-building programs, including leadership development, organizational governance training, and technical assistance, strengthen organizational effectiveness. Promoting sustainability practices and diversifying revenue streams can enhance organizational resilience.

8. Training and Technology Adoption

Baseline Requirements:

Assessing prior knowledge, barriers to adoption, and attitudes towards training will provide critical insights into the readiness of individuals and organizations to embrace change.

Programmatic Interventions:

Introducing targeted training programs that address specific barriers and incorporating incentives for technology adoption can foster innovation. Peer learning platforms and follow-up support can ensure sustained adoption of new practices.

9. Natural Resource and Climate Risk Management

Baseline Requirements:

Baseline data on participation in sustainable practices and knowledge of climate risk reduction measures will highlight the community’s capacity to manage natural resources.

Programmatic Interventions:

Programs promoting sustainable practices, such as afforestation, soil conservation, and water management, can mitigate climate risks. Community-level capacity-building workshops on disaster preparedness and resource management can enhance resilience.

10. Producer-Public-Private Partnerships (4Ps)

Baseline Requirements:

Economic indicators such as income, costs, and profit will provide insights into the financial impact of 4Ps. Perceptions of collaboration effectiveness will help evaluate the potential for scaling such models.

Programmatic Interventions:

Strengthening 4Ps through policy advocacy, facilitating multi-stakeholder dialogues, and enhancing coordination mechanisms ensures their success. Incentivizing private sector participation and promoting public policies supportive of collaborative models can drive innovation and growth.

Integration into Baseline Design and Program Development

By analyzing data across these themes, programmatic interventions can be designed to:

- Address identified gaps in access, awareness, and resource availability.

- Build resilience through capacity building and sustainable practices.

- Enhance inclusivity, particularly for marginalized groups.

- Monitor and evaluate progress using clearly defined indicators linked to the baseline findings.

These insights ensure that the program not only meets its immediate objectives but also fosters long-term, sustainable development in the target communities.

Pre-Testing: Objectives, Process, and Importance

Pre-testing plays a pivotal role in ensuring the readiness and effectiveness of the questionnaire. It validate the relevance of questions to project objectives, enhanced data quality through structural refinements, and equipped enumerators with the skills and tools required for successful field implementation. By incorporating the findings from pre-testing, the baseline survey tool will be optimized to provide reliable, actionable insights, enabling evidence-based programmatic interventions.

Objectives of Pre-Testing

The pre-test of the baseline questionnaire will be an essential step to validate its effectiveness, usability, and alignment with project objectives. The specific objectives will be:

- To assess and analyze respondents' knowledge levels and their understanding of the questions framed around the key objectives of the project.

- To evaluate the questionnaire's structure and test the enumerators’ preparedness for field data collection.

- To identify potential challenges during the data collection process, such as uncooperative respondents, language barriers, and other technical difficulties, through brainstorming sessions conducted during enumerator training.

- To equip enumerators with strategies to address anticipated challenges, enabling them to become comfortable with the questionnaire and data collection tools.

- To ensure a thorough testing of all components of the data collection process, including the Kobo Toolbox platform, hard copy forms, informed consent procedures, and logistical arrangements.

- To incorporate modifications to the questionnaire based on findings from the pre-test, improving its clarity, relevance, and functionality.

Sampling Technique and Sample Size

The pre-test will utilize a purposive sampling method to conduct pretesting with with a small, representative group 7-10% (150 HH) in 5 districts (Haripur, Swabi, Peshawar, Chitral and Shangla).

The selection of respondents will be based on their ability to provide meaningful insights into the key project objectives and thematic areas. The pre-test will help to evaluate the reliability of the instruments and to refine any unclear or ambiguous items.

How Pre-Testing will be Conducted

Pre-testing will follow a systematic approach to trial the baseline questionnaire in a controlled, real-world setting. This included:

- Field Simulation: Conducting the pre-test with the selected sample groups to replicate actual field conditions and identify practical challenges faced by enumerators and respondents.

- Enumerator Training: Providing detailed training sessions to enumerators, focusing on the questionnaire structure, skip logic navigation in Kobo Toolbox, and strategies to overcome challenges such as language barriers or respondent reluctance.

- Feedback Collection: Gathering insights from enumerators and respondents on question clarity, cultural relevance, and tool usability.

- Data Analysis: Analyzing pre-test data to identify gaps in the questionnaire structure, response inconsistencies, and other areas requiring refinement.

Importance of Pre-Testing Before full Baseline Deployment

Pre-testing will serve as a critical validation step, ensuring that the baseline questionnaire and associated processes are robust and aligned with project objectives. Its importance includes:

- Ensuring Relevance and Clarity: Testing the phrasing and cultural appropriateness of questions ensures respondents understand them as intended, avoiding misinterpretation.

- Improving Data Quality: Modifications based on pre-test findings enhance the tool's reliability and ability to capture actionable data.

- Enhancing Enumerator Competence: Training and hands-on practice during pre-testing prepare enumerators for efficient and accurate data collection.

- Optimizing Questionnaire Design: Streamlining the questionnaire by removing redundant or irrelevant questions and enhancing logical sequencing makes the survey concise and effective.

- Validating Data Collection Frameworks: Testing all operational aspects, including technological platforms and procedural requirements, ensures readiness for full-scale implementation.

The pretest report will be shared with the Project Management Unit (PMU) for their feedback and approval.

Data Collection Process

The data collection process for this study will employ a combination of traditional and digital methods to ensure inclusivity and comprehensive participation from diverse geographic and socio-economic backgrounds. The methodology will include:

- Digital Data Collection Tools Using Kobo Toolbox:

Kobo Toolbox will be the primary platform for data collection. This robust and user-friendly digital tool is specifically designed for data collection in challenging environments. Kobo Toolbox will allow for the creation and deployment of dynamic questionnaires that can include various question types, such as multiple-choice, open-ended, and scaled responses.

Importance and Features of Kobo Toolbox:

  - Offline Data Collection: Kobo Toolbox can operate offline, which is particularly valuable in areas with intermittent or no internet connectivity. Data is securely stored on the device and synced to a central database when a connection becomes available.

  - Ease of Use: The platform is intuitive and user-friendly, enabling data collectors to quickly adapt to its interface, minimizing training requirements.

  - Customizable Forms: Kobo Toolbox supports customizable and logic-based forms, ensuring that questionnaires are tailored to the specific needs of the study.

  - Real-Time Data Monitoring: It allows for real-time monitoring and analysis, capturing coordinate (exact location) and enabling timely adjustments to the data collection process if needed.

  - Reliability and Security: Data collected through Kobo Toolbox is encrypted and stored securely, ensuring confidentiality and compliance with ethical standards.

  - Cost-Effective Solution: Being an open-source tool, Kobo Toolbox reduces operational costs while maintaining high functionality, making it an ideal choice for this study.

By leveraging Kobo Toolbox, the study ensures efficient and accurate data collection, particularly in urban and semi-urban areas where participants are more likely to engage with digital technologies. The platform's adaptability and reliability make it a valuable asset in capturing high-quality data while enhancing the overall efficiency of the process.

Ethical Considerations

Ethical compliance remains central to the data collection process, ensuring that the study respects participants' rights and builds trust with the communities involved. The study adheres to the following principles:

- Informed Consent:

All participants will provide informed consent before data collection begins. Using Kobo Toolbox, consent forms can be embedded directly into the digital questionnaire, allowing respondents to review and acknowledge the study's objectives and their rights before proceeding. For face-to-face interviews, written or verbal consent will be obtained. This ensures transparency and fosters participants' confidence in the process.

- Confidentiality and Anonymity:

Confidentiality is a key priority, with measures in place to protect the privacy of all respondents. Kobo Toolbox's secure data storage features ensure that personal identifiers are encrypted, and access to raw data is restricted to authorized personnel only. Data will be anonymized before analysis, further safeguarding participants' identities. This approach not only complies with data protection laws but also reinforces trust and willingness to participate.

- Voluntary Participation:

Participation in the study is entirely voluntary. Participants will be informed of their right to withdraw at any time without penalty. The digital forms on Kobo Toolbox can be designed to include reminders about voluntary participation, while face-to-face interviewers will verbally communicate this to respondents. This ensures that all participation is genuinely consensual, respecting the autonomy of individuals.

#### . Data Collection Modes:

  - Face-to-face Interviews: This will be the primary mode of data collection to ensure a higher response rate, especially in rural and semi-urban areas where literacy may be low. As mentioned earlier total of 1500 individual HHs will be interviewed which will include a minimum of 25% female.

#### Key Informant Interviews:

- Purpose: The main purpose of conducting Key Informant Interviews (KII) for the Rural Economic Transformation Project is to gain deep insights and qualitative data on the socio- economic dynamics, opportunities, challenges, and community perspectives that impact rural development and transformation (Questionnaire Attached as Annex-B). Specifically, the goals may include:

- Understanding Local Context: Gather in-depth knowledge about local economic conditions, agricultural practices, infrastructure, access to services, and socio-cultural factors affecting rural communities.

- Identifying Opportunities and Challenges: Identify the opportunities for economic growth and the barriers that limit progress, such as market access, education, financial inclusion, etc.

- Mapping Stakeholder Perspectives: Learn from key stakeholders (community leaders, local officials, entrepreneurs, NGOs, etc.) about their experiences, priorities, and visions for economic transformation.

- Validating Secondary Data: Cross-check the information gathered from surveys, reports, and statistical data with real-world experiences of local leaders and experts.

- Guiding Program Design and Implementation: Utilize insights to design and implement development projects tailored to the needs of rural communities, ensuring sustainability and inclusiveness.

- Methodology for Conducting Key Informant Interviews: To effectively conduct a KII, the following methodology will be adopted:

#### Selection of Key Informants

  - Identify Participants: Choose informants based on their knowledge, experience, and influence in areas like agriculture, education, health, local governance, business, and development. Common informants include:

Officials from Agriculture and Livestock Departments,

Representative Local governments officials and Community leaders

Business owners and entrepreneurs

Representatives from NGOs and cooperatives

Farmers, including Women Farmers, traders, and local producers

  - Diversity: Ensure a mix of participants from different socio-economic backgrounds, genders, and age groups to capture diverse perspectives.

#### 20.0. Development of an Interview Guide

  - Define Objectives: Create a set of open-ended questions aligned with the project's objectives, focusing on themes like:

Economic activities (agriculture, trade, services)

Challenges in infrastructure, education, and healthcare  Employment and income generation

Market access and value chains  Gender roles in the economy

Environmental concerns and climate resilience

  - Tailored Questions: Adapt the questions to each informant’s role and expertise.

#### 21.0. Conducting the Interviews

One-on-One or Small Group Format: KIIs are typically conducted in a one-on-one setting to allow for focused and in-depth discussions. In some cases, small groups (with similar profiles) may be interviewed.

Structured but Flexible: Follow the prepared guide but allow flexibility for the informant to elaborate on important topics.

Recording and Note-Taking: With permission, record the conversation or take detailed notes to ensure accurate data collection.

Confidentiality: Ensure the informants that their identities and opinions will remain confidential, particularly on sensitive topics like governance or land use.

#### Data Analysis

The data collected for this study will undergo a comprehensive analysis to generate actionable and reliable insights. Given the nature of real-time data collection through KoboToolbox, this tool will be primarily used for initial analysis and reporting. KoboToolbox used frequently by INGOs, UN Agencies allows for real-time data collection, ensuring that data can be continuously assessed and monitored throughout the study. This capability enables timely interventions and immediate understanding of the emerging patterns. Excel will also be employed to handle simpler statistical tasks and data visualizations, particularly where detailed cross-tabulations and summary statistics are required. However, if an in-depth comparison of groups or detailed statistical testing is required, SPSS with the ANOVA1 (Analysis of Variance) tool will be used for more rigorous analysis.

The application of SPSS and ANOVA1 will be specifically employed if deeper statistical comparisons are needed during the analysis phase. This tool will allow for the examination of variances within and between different groups, such as geographical regions, income levels, or other demographic variables. ANOVA will provide a more precise and statistically significant comparison when the need arises to assess differences between groups, particularly in instances where complex relationships and interactions among variables are identified.

Data Preparation and Cleaning:

The data, initially gathered through KoboToolbox, will be exported into a format compatible with both Excel and SPSS (such as .csv or .sav). A systematic cleaning process will be conducted to ensure the data’s accuracy and consistency, addressing any missing values, outliers, or errors. Relevant variables will be categorized into thematic areas, such as household income, market access, and governance, to ensure the dataset is clean and organized for detailed analysis.

Descriptive Statistics and Data Summarization:

In the initial stages of analysis, Excel will be used for basic descriptive statistical analysis to provide an overview of the dataset. Key metrics like means, medians, and standard deviations will be calculated to summarize key variables, such as household income, product sales, and market access. Visual tools such as histograms and box plots will be employed in Excel to present the data distribution and highlight any outliers that could influence the analysis.

Application of Statistical Analysis Using ANOVA1:

Once the preliminary analysis is complete, ANOVA1 will be applied in SPSS if significant group comparisons are needed.

Validation Through Triangulation:

To further enhance the reliability and validity of the findings, a triangulation approach will be employed. The results from will be cross-referenced with data from other sources, such as household surveys, key informant interviews (KIIs), and focus group discussions (FGDs). This process will allow for consistency and corroboration of insights across different data collection methods.

Process of Data Triangulation:

- Data Integration: All data collected from household surveys, KIIs, FGDs, and secondary research will be consolidated into a unified framework to ensure comprehensive analysis.

- Cross-Referencing: Insights from different methods will be compared to identify consistencies and discrepancies.

- Validation of Outliers: Outliers or contradictory findings will be carefully reviewed by revisiting original data sources and consulting experts to validate their authenticity.

- Synthesis: The triangulated data will be synthesized into actionable insights, ensuring that the recommendations are grounded in robust and comprehensive evidence.

Application in the Current Study:

The triangulation approach will be applied across key thematic areas:

- Market Access Challenges: Quantitative data on market access issues will be compared with qualitative narratives about barriers such as lack of transport or infrastructure.

- Governance and Stakeholder Engagement: Survey data on local governance roles will be cross-referenced with insights from government officials through KIIs to ensure the consistency and accuracy of the information.

- Income Generation: Survey data on household income levels will be compared with qualitative accounts of economic challenges and opportunities to validate the results and generate holistic insights.

In summary, KoboToolbox will be the primary tool for real-time data collection, with Excel used for preliminary data summarization. SPSS and ANOVA1 will be deployed when in-depth statistical analysis or group comparisons are required, ensuring a scientifically rigorous and evidence-based analysis to inform programmatic interventions.

#### Reporting and Feedback

The Report Writing phase is a critical component of this study as it serves to synthesize all the data collected, analyzed, and interpreted throughout the project into a comprehensive document. This report will provide a clear, structured, and accessible overview of the study findings, challenges identified, opportunities for improvement, and actionable recommendations for the Rural Economic Transformation Project.

1. Structure of the Report:

The report will be systematically organized to ensure clarity and ease of navigation for all stakeholders, including decision-makers, donors, and project implementers. It will include the following sections:

- Executive Summary: A concise summary that captures the key findings, challenges, opportunities, and strategic recommendations. This section is particularly crucial for senior stakeholders and decision-makers who may only have time for a high-level overview of the report.

- Introduction: This section will provide background information on the Rural Economic Transformation Project, its goals, and the context within which the study was conducted. It will also include the study’s objectives, scope, and methodology to ensure transparency about the research process.

- Methodology: A detailed description of the research design, data collection methods (including KoboToolbox, surveys, key informant interviews (KIIs), etc.), and analysis techniques used, such as SPSS and ANOVA1. This will ensure that readers understand the rigor and reliability of the study.

- Findings:

  - Challenges: This section will discuss the barriers or constraints identified through the study, such as issues in market access, income generation, access to resources, governance inefficiencies, and climate-related risks. Each challenge will be supported by both quantitative data (e.g., statistics on household income, market access, etc.) and qualitative insights from interviews and focus group discussions (FGDs).

  - Opportunities: This will highlight potential areas for improvement and growth, such as access to new markets, increased capacity for local governance, and opportunities arising from climate adaptation strategies. It will focus on how leveraging these opportunities can enhance the economic resilience of rural populations through programmatic interventions.

- Key Recommendations: Based on the findings, this section will provide actionable recommendations for project implementation. The recommendations will be categorized by thematic areas and will be tailored to address the identified challenges and capitalize on the opportunities.

- Conclusion: A summary of the key findings and recommendations, emphasizing the importance of the proposed interventions for the success of the Rural Economic Transformation Project. This section will also reinforce the need for timely implementation to achieve sustainable outcomes for rural communities.

2. Key Insights:

The report will extract insights from the data, focusing on patterns that will help in refining the project’s strategy. For instance, if a significant portion of the rural population faces challenges related to market access due to poor infrastructure, this will be identified as a priority area for intervention. The report will emphasize actionable steps to overcome such barriers, such as advocating for improved transportation infrastructure or supporting local businesses to adapt to market demands.

3. Data Visualizations:

To enhance the readability and clarity of the findings, the report will include various data visualizations such as:

- Charts and Graphs: Visual representations of key statistics, such as household income distributions, market access percentages, or climate resilience levels.

- Tables: To present detailed quantitative comparisons, for example, income levels across different regions or demographic groups.

- Maps: If relevant, to show geographic disparities or the locations of key challenges and opportunities.

These visual elements will ensure that the findings are easily understandable and accessible to a wide range of audiences.

Feedback Loop: Engaging Stakeholders for Transparency and Continuous Improvement

The Feedback Loop is an essential part of the project’s learning and adaptation process. It ensures that the findings from the study are not only communicated to the relevant stakeholders but also that the insights are used to inform decision-making, refine strategies, and improve project implementation.

1. Sharing Key Insights with Stakeholders:

Once the report is drafted, it will be shared with all relevant stakeholders, including government representatives, donors, local authorities, and implementing partners. The aim is to ensure transparency in how the data was collected, analyzed, and interpreted, and to provide them with a clear understanding of the challenges and opportunities identified for rural economic transformation.

- debriefings: To facilitate deeper engagement, stakeholders will be invited to participate in debriefing workshop or presentation where key findings will be discussed. This interactive format will allow stakeholders to ask questions, raise concerns, and contribute their perspectives, ensuring that their voices are heard in the process.

- Regular Updates: The feedback loop will be continuous, with regular updates on progress and emerging insights. These updates will be shared through, email, or project meetings, ensuring that stakeholders are kept informed and involved throughout the project’s lifecycle.

2. Refining Strategies for Project Implementation:

The insights gathered from stakeholders during the feedback sessions will be used to refine the project’s strategies.

- Iterative Feedback: Based on stakeholder feedback, the project will refine its approach in an iterative manner.

- Adapting Interventions: As feedback is received and analyzed, the project will adjust its interventions to better meet the needs of the target population. This might include modifying the design of capacity-building programs, improving livelihood support mechanisms, or aligning the project’s objectives more closely with local governance priorities.

3. Ensuring Accountability and Ownership:

A transparent feedback loop fosters accountability, as stakeholders will have the opportunity to review the findings and ensure that the project remains aligned with the broader goals of economic transformation and sustainable development. In turn, this fosters a sense of ownership among stakeholders, who will feel invested in the project’s success and be more likely to actively participate in its implementation.

- Stakeholder Empowerment: Engaging stakeholders in a transparent and responsive feedback process empowers them to take ownership of the project’s outcomes. For instance, local governance bodies can use the findings to guide policy and practice changes in line with the identified opportunities.

- Feedback Documentation: All feedback provided by stakeholders will be documented and integrated into the study findings and recommendation, as well as it’s potential use for project’s ongoing monitoring and evaluation processes.

Team Composition (Enumerators)-for conducting Baseline Study:

|  |  | Male | Female |
| --- | --- | --- | --- |
| 1 | Central | Mohammad-Ishfaq | Sadia |
|  |  | Shah Muhammad | Kanwal Afridi |
|  |  | Zafar Khan | Bushra |
| 2 | Northern | Mubashir | Kanwal |
|  |  | Altaf | Irum |
|  |  | Arshad Iqbal | Mishi Khan |
| 3 | Eastern | Haris | Nanjeel |
|  |  | Jamal | Raheela |
|  |  | Kamal | Bushra Khan |
| 4 | Southern | Ibrar Ul Haq | Madiha |
|  |  | Muhammad Wali | Hajra Bibi |
|  |  | Fida Khan | Mahnnor |
| 5 | Chitral | Afzal Hayat | Rabia |
|  |  | Shahid | Karima |

- Enumerator Training:

Enumerators will be trained in survey methodology, interviewing techniques, ethical considerations, and gender sensitivity.

Special focus will be given to ensuring the accurate collection of data from female respondents, considering the cultural context of KP.

#### Data Management and Quality Assurance: Data Entry and Management:

- Real-time Data Capture: GPS_ Enabled: KOBO Software will be used, for uploading data in real-time.

Data Cleaning: Post-collection, data will be cleaned and validated through consistency checks and cross-verification with enumerators.

#### Quality Control Mechanisms:

Field Monitoring: Supervisors will be deployed to monitor data collection teams and ensure adherence to the study protocols.

- Back-checks: A portion of respondents (10%) will be revisited to verify the accuracy of the data.

Preparation Phase

Data Collection Phase

Monitoring & Quality Assurance

Data Submission

Reporting & Feedback

Resolution of Challenges

Final review & Handover

#### Data Analysis: Statistical Methods:

Descriptive	Statistics:	To	summarize	the	socio-economic	and	demographic characteristics of the sample (mean, median, standard deviation, frequencies).Descriptive statistics provide a concise summary of the socio-economic and demographic  characteristics of a sample, offering key insights into central tendencies, dispersion, and distributions. Metrics such as the mean and median highlight the central values of variables like income, age, or education level, while the standard deviation measures the variability or spread of the data. Frequencies are used to analyze categorical variables, showing the proportion of individuals within specific groups (e.g., gender, occupation, or marital status). Together, these statistics enable a clear understanding of the sample's overall profile, facilitating comparisons and guiding further analysis.

- Cross-tabulation: By gender, district, and other relevant variables. Cross-tabulation is a statistical tool used to examine the relationship between two or more categorical variables, such as gender, district, and other relevant factors. By creating a matrix of frequencies or percentages, it reveals patterns, trends, or associations within the data. For instance, cross-tabulating gender and district can show differences in socio-economic indicators or access to services across regions and sexes. This approach provides valuable insights into how specific characteristics interact, enabling researchers to identify disparities or correlations within the sample.

- Consent: Ethical considerations, including consent for photographs, respect for religious sensitivities, and adherence to plagiarism-free reporting, are integral to ensuring the credibility and ethical integrity of the analysis.

#### Software Tools:

- KOBO-Toolbox: Used for real-time data collection and instant analysis.

- Excel: Utilized for preliminary data summarization.

- SPSS ANOVA1: Employed for in-depth statistical analysis, wherever required.

#### Ethical Considerations:

Informed Consent: All respondents will be informed about the study’s purpose, their right to withdraw, and confidentiality.

Anonymity and Confidentiality: Data will be anonymized to protect the identity of respondents.

- Gender Sensitivity: Ensuring that female enumerators are available for female respondents, and interviews are conducted in culturally appropriate settings.

#### Timeline:

| - Phase | Duration | Activities | Additional Notes |
| --- | --- | --- | --- |
| Phase 1: Preparation | 2 Days | - Literature review and stakeholder engagement - Finalization of the sampling strategy and questionnaire design - Recruitment and training of enumerators | Ensure alignment with project goals; enumerators to be well-trained for accuracy |
| Phase 2: Data Collection | 7 Days | - Full-scale fieldwork across 15 districts | Fieldwork requires travel, logistics planning, and resource allocation across districts |
| Phase 3: Data Cleaning and Analysis | 7 Days | - Data entry, cleaning, and validation - Statistical analysis and report writing | Use software tools for efficient data management (e.g., SPSS, Excel, or R) |
| Phase 4: Reporting | 7 Days | - Presentation of preliminary findings to stakeholders - Finalization of the baseline report | Stakeholder feedback will refine the final report before submission |

#### 8. Expected Deliverables:

Cleaned and validated dataset

Baseline report with key socio-economic indicators for the control and target groups  Recommendations for monitoring and evaluation of the KP RETP

#### Limitations and Risks:

The below table outlines Risks, Mitigation Strategies, and Assumptions for conducting a baseline study of the Rural Economic Transformation Project in Khyber Pakhtunkhwa Province:

| Risks Mitigation Strategy/ Concrete Steps Assumptions |  |  |  |  |
| --- | --- | --- | --- | --- |
| Security Concerns | - Identify high-risk areas using real-time updates from local authorities. - Establish partnerships with local police for safe routes and emergency response. - Hire experienced local field staff to act as guides and security liaisons. - Create a secure schedule for fieldwork—operate during daylight hours and avoid conflict-prone times. - Conduct a pre-assessment of each region before mobilizing teams to ensure safety. |  |  | - The security situation in selected areas will be manageable, and local law enforcement will cooperate. |
| Access to remote Areas | - Hire reliable local guides familiar with difficult terrains. - Procure or rent suitable alternative transportation like motorbikes, jeeps, or boats. - Conduct reconnaissance visits to map out routes and estimate travel times. - Equip teams with proper gear (e.g., trekking boots, portable navigation devices) for walking long distances. |  |  | - Remote villages will be reachable with available transport options, even if challenging. |
| Cultural Sensitivity and Gender Issues | - Organize cultural sensitivity and gender-awareness training for all field staff. - Recruit gender-balanced teams with female enumerators for interviews involving women. - Meet with community leaders before fieldwork to gain approval and ensure cooperation. - Create a culturally appropriate dress code and behavior guide for staff. |  |  | - Community leaders and locals will be open to outside researchers, and gender sensitivity will be respected. |
| Language Barrier |  | - Recruit field staff fluent in regional dialects and languages. - Translate all survey tools and training materials into local languages (e.g., Urdu, Pashto). - Conduct language assessments to ensure enumerators’ proficiency. - Test the translated surveys during pilot studies for clarity and cultural relevance. | - Respondents will be able to communicate effectively with trained enumerators in local languages. |  |  |
| Poor Data Quality |  | - Conduct a pilot survey to test tools and identify potential issues. - Train data collectors extensively on survey protocols, tools, and ethical guidelines. - Establish field supervisors to perform regular spot checks and back-checks to verify data accuracy. - Implement digital data validation tools (if possible) to flag inconsistencies in real-time. | Enumerators will follow the methodology and data collection protocols strictly, ensuring high-quality data. |  |  |
| Weather Conditions |  | - Use seasonal weather data to plan fieldwork for optimal periods. - Create contingency schedules to allow for delays due to unforeseen weather conditions. - Equip teams with weatherproof clothing, transportation, and shelter where needed. - Monitor short-term weather forecasts and adjust plans accordingly. | - The weather will not cause significant disruptions, and alternative plans will be feasible. |  |  |
| Limited Technological Access |  | - Provide paper-based alternatives for surveys where digital tools cannot function. - Equip teams with solar-powered chargers or backup batteries for devices. - Test digital tools before deployment to identify technological limitations. - Develop a protocol for manual data recording and entry into digital systems post-fieldwork. | - Technological infrastructure will be insufficient in some areas, requiring flexibility in data collection methods. |  |  |
| Community Resistance to data collection |  | - Engage community leaders and influencers early to explain project objectives and gain support. - Conduct community orientation sessions to communicate project benefits and address concerns. - Use visual aids (flyers, videos) to simplify communication. - Design surveys to be brief and culturally appropriate to minimize resistance. | - Communities will be cooperative once adequately informed about the project’s objectives. |  |  |
| Sampling Bias |  | - Develop and implement a randomized sampling methodology to ensure representation. - Validate household lists and census data to identify gaps before sampling begins. - Conduct periodic audits to ensure the sample remains unbiased. - Use GPS tracking to confirm geographic coverage and prevent clustering in specific areas. | The population will be adequately represented by available lists and records. |  |  |

| 9.0 Work Plan for Conducting Baseline Study under the KP-Rural Economic Transformation Project (KP-RETP) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S.No | Stept/ Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 |
| 1 | Preparation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Collection of Data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Analysis of Data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Reporting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Submission of Final report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

#### Annexures:

Khyber Pakhtunkhwa Rural Economic Transformation Project (KP-RETP)

Baseline Household Questionnaire

INFORMED CONSENT: My name is ______________________________, and I am working with REPID. We are conducting a baseline study for the Khyber Pakhtunkhwa – Rural Economic Transformation Project (KP-RETP), funded by IFAD, to address rural poverty and food insecurity across KP. The project focuses on agribusiness development, employment promotion, and capacity building, aiming to enhance livelihoods, food security, and resilience among rural households. This survey seeks to assess the current state of agribusiness, employment opportunities for youth and women, household income levels, farming skills, production costs, and value chains, as well as identify training needs for small-scale farmers. Your participation is vital, and all information shared will be kept strictly confidential and reported in aggregate to protect your identity. - Are you willing to participate in the interview?  Yes  No

| Section 1: Demographic Information |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| GENERAL INFORMATION |  |  |  |  |  |  |
| Date of Interview |  |  |  |  |  | District: |
| Village council |  |  |  |  |  | Union Council |
| Data collected by |  |  |  |  |  | Designation: |
| RESPONDENT INFORMATION |  |  |  |  |  |  |
| Respondent’s name |  |  |  |  |  | Respondents contact number (optional) |
| Relationship with head of household |  |  Head of Household  Spouse  Son  Daughter  Father/Mother  any other (specify)._____________ |  |  |  |  |
| Gender |  |  Male  Female  other _________________ |  |  |  | Age |
| Any Disability |  |  Yes  No |  |  |  | If Yes (specify): _________________________ |
| Household size |  | Age group; Male; Female; Girls; Boy; Persons With Disabilities; Total. 0–5 years. 6–17 years. 18–29 years. 30–40 years. 41–60 years. 60 years and above. |
| Level of Education: |  |  Primary  Middle  High  Higher Secondary  University/Degree  No formal education |  |  |  |  |
| Section 2: Outreach - Services (awareness, communication, utilization, barriers to access). |  |  |  |  |  |  |
| 1 | Are you aware of any development programs or services currently available in your area? Hint: Ask this question to all respondents. Look for awareness among both men and women. |  |  |  |  | ⃞ Yes. ⃞ No |
| 2 | If yes, which services are you aware of in your community? |  |  |  |  | ⃞ Health ⃞ Education ⃞ Agribusiness support ⃞ Livelihood support ⃞ Other (specify) |
| 3 | How did you first learn about these services? (Select all that apply) |  |  |  |  | ⃞ Community meetings ⃞ Word of mouth ⃞ Media (TV, Radio, Newspapers) ⃞ Local leader/representatives ⃞ NGOs/Community Organizations ⃞ Other: ________________ |
| 4 | Do you feel that information about available services is shared adequately in your community? Hint: Assess the perceived adequacy of communication, especially for marginalized groups. |  |  |  |  | ⃞ Yes. ⃞ No |
| 5 | Have you ever participated in community meetings about available services? Hint: Understand the community engagement level for both men and women. |  |  |  |  | ⃞ Yes. ⃞ No |
| 6 | Which communication channels do you prefer to receive information about services? Hint: Look for preferences across gender, especially for women. |  |  |  |  | ⃞ Community meetings ⃞ Word of mouth ⃞ Media (TV, Radio, Newspapers) ⃞ Flyers or posters ⃞ Other: ________________ |
| 7 | How would you rate the effectiveness of these channels in informing you about services? Hint: Evaluate the effectiveness of each method, especially among women. |  |  |  |  | ⃞ Very effective ⃞ Somewhat effective ⃞ Not effective |
| 8 | Are there any communication channels that you believe are missing in your community? Hint: Identify gaps in communication, particularly for underserved groups. |  |  |  |  |  Yes  No |
| 9 | Has anyone in your household accessed any services in the past year? Hint: Ask about the entire household to get a complete picture. |  |  |  |  |  Yes  No |
| 10 | Which specific services did you or your household use in the last year? Hint: Identify the key services accessed, focusing on gender participation. |  |  |  |  | ⃞ Health ⃞ Education ⃞ Agribusiness support ⃞ Livelihood support ⃞ Other (specify) |
| 11 | Were there any barriers that prevented you from accessing these services? Hint: Assess potential barriers to access, especially for women or persons with disabilities. |  |  |  |  |  Yes  No |
| 12 | If you faced barriers, which ones were the most significant? Hint: Focus on identifying the most common obstacles. |  |  |  |  | ⃞ Lack of information ⃞ Financial constraints ⃞ Physical distance ⃞ Cultural barriers ⃞ other (specify).___________________ |
| 13 | Are there any services you would like to access, but currently cannot? Hint: Capture gaps in service access, especially for marginalized groups. |  |  |  |  | ⃞ Health ⃞ Education ⃞ Agribusiness support ⃞ Livelihood support ⃞ Other (specify) |
| 14 | Do you feel that the services in your community are equally accessible to both men and women? Hint: Look for gender-based barriers in access. |  |  |  |  |  Yes  No  Don’t’ Know |
| 15 | Are there any services that are not available to you due to your geographical location? Hint: Assess access based on geographical limitations. |  |  |  |  |  Yes  No  Don’t’ Know |
| 16 | If yes, please specify those services? |  |  |  |  | ⃞ Health ⃞ Education ⃞ Agribusiness support ⃞ Livelihood support ⃞ Other (specify) |
| 17 | Are services accessible to people with disabilities in your community? Hint: Ensure to focus on accessibility for persons with disabilities. |  |  |  |  |  Yes  No  Don’t’ Know |
| 18 | Is transportation a barrier to accessing services for you? Hint: Focus on transportation issues, especially for rural areas. |  |  |  |  |  Yes  No |
| 19 | Do you think there are cultural or social barriers that prevent people from accessing services? Hint: Investigate cultural and social barriers, especially for women and minorities. |  |  |  |  |  Yes  No  Don’t’ Know |
| 20 | If yes, what are those barriers? |  |  |  |  |  |
| Section 3: Poverty Reduction and Income Improvement: |  |  |  |  |  |  |
| 21 | What are the primary sources of income for your household? (Select all that apply) |  |  |  |  |  Agriculture  Livestock  Small business  Daily wage labor  Other (please specify) |
| 22 | If agriculture, How much land you owned? Please response in acres |  |  | Own; Agriculture land; Uncultivated agricultural land. Rented; Agriculture land; Uncultivated agricultural land. |
| 23 | What is the monthly/annual income of your household? |  |  |  |  |  |
| 24 | What proportion of your household's income came from agriculture or related products? |  |  |  |  |  |
| 25 | Are there other sources of income, such as remittances, jobs or support from relatives etc.? |  |  |  |  |  Yes  No |
| 26 | If Yes, please specify what are the other sources. |  |  |  |  |  |
| 27 | What proportion of your household’s income came from other sources. Hint: Identify any external financial support, including for women-headed households. |  |  |  |  |  |
| 28 | How do you sell your agricultural products. |  |  |  |  |  Directly  Middleman  Farmer Organization  other (specify). _________________ |
| 29 | What are the barriers in selling your products? |  |  |  |  |  lack of market awareness  transportation  market fluctuation  high inputs cost  lack of govt: regulations  other (specify). _________________ |
| 30 | How stable is your household income throughout the year? Hint: Understand income stability, focusing on seasonal or irregular income sources. |  |  |  |  |  Very stable  Somewhat stable  Not stable |
| 31 | If somewhat or not stable what are the reasons/primary challenges? |  |  |  |  |  |
| 32 | Do you rely on external sources of income (e.g., loans, support from relatives)? Hint: Determine if external financial support is common in the community. |  |  |  |  |  Yes  No |
| 33 | If yes, what are these external sources of income. |  |  |  |  |  |
| 34 | Are there sufficient income opportunities in your area? Hint: Understand the availability of opportunities for both men and women in the community. |  |  |  |  |  Yes  No |
| 35 | If yes, what are these opportunities? |  |  |  |  |  |
| 36 | What skills do men or women of your household possess? |  |  |  |  |  Farming  Food processing  Masonry  Shop keeping  Construction/ contracting  Transportation  Home-based activity tailoring  Home-based activity (handicraft)  Home-based activity (embroidery )  Other (Specify)_________ |
| 37 | Are you able to use these skills to generate income |  |  |  |  |  Yes  No |
| 38 | If yes, mention the skill and per month/year income generated from it? |  |  Farming  Food processing  Masonry  Shop keeping  Construction/ contracting  Transportation  Home-based activity tailoring  Home-based activity (handicraft)  Home-based activity (embroidery )  Other (Specify)_________ |  |  | Farming: Rs: Food processing: Rs: Masonry: Rs: Shop keeping: : Rs: Construction/ contracting: : Rs: Transportation(driving): : Rs: Home-based activity tailoring: Rs: Home-based activity (handicraft): Rs: Home-based activity (embroidery ):Rs: Other (Specify)_________ |
| 39 | Are there any vocational training programs available in your area? Hint: Explore available training programs, especially for women and marginalized groups. |  |  |  |  |  Yes  No |
| 40 | If yes, please specify/list the available programs? |  |  |  |  |  |
| 41 | Have you or anyone in your household ever attended a vocational training program? Hint: Focus on training participation by both men and women. |  |  |  |  |  Yes  No |
| 42 | Do you think vocational training programs are useful for improving your household's income? Hint: Assess the perceived value of training for economic empowerment. |  |  |  |  |  Yes  No |
| 43 | What types of vocational training would be most beneficial to you? Hint: Understand what types of training are in demand in the community. |  |  |  |  |  Tailoring  embroidery  mobile repair  auto works (cycle, bike, car)  Digital skills  other (specify). _________________ |
| 44 | What barriers prevent people from attending vocational training programs in your area? Hint: Look for barriers that might affect participation, especially for women. |  |  |  |  |  |
| Section 4: Community Participation and Governance: |  |  |  |  |  |  |
| 45 | Are you involved in any community or local decision-making processes? Hint for enumerators: Pay attention to whether women or marginalized groups have a voice in local decision-making. |  |  |  |  |  Yes  No |
| 46 | If yes, how you are engaged? |  |  |  |  |  community meeting  member of community structure  events  other (specify). _________________ |
| 47 | Are you aware of any formal community structures that exist in your community (CBO, Farmers Committee, PFO etc.)? |  |  |  |  |  Yes  No |
| 48 | If yes, please specify what type of community structure exist? |  |  |  |  |  CBO  Farmers Committee  PFO  other (specify). _________________ |
| 49 | How often do you participate in community meetings or discussions? Hint: Look for patterns in participation, particularly any barriers preventing women from engaging. |  |  |  |  |  regularly  occasionally  Never |
| 50 | Do you feel that your voice is heard in community decision-making? Hint for enumerators: Determine if women or minority groups feel excluded from decision-making processes. |  |  |  |  |  Yes  No |
| 51 | Do you think community leaders or local authorities consider your needs in decision-making processes? Hint for enumerators: Explore if marginalized groups, especially women and children, are considered in decisions. |  |  |  |  |  Yes  No |
| 52 | How satisfied are you with the level of participation allowed in local decision-making processes? Hint for enumerators: Focus on how different groups feel about their participation, particularly women or other marginalized populations. |  |  |  |  |  Very satisfied  Somewhat satisfied  Not satisfied |
| 53 | What challenges or barriers prevent you from engaging with local authorities or service providers to express your opinions or needs? |  |  |  |  |  Lack of access  Lack of awareness  distance  Transportation cost  No action of previous meetings  other (specify). _________________ |
| 54 | Do you agree that community participation is important in influencing local decisions? Hint: Understand the influence level in local decision making and their willingness |  |  |  |  |  Yes  No |
| Section 5: Food Security and Nutrition: |  |  |  |  |  |  |
| 55 | How many meals does your household consume daily on average? Hint: Assess the basic food security of the household, paying special attention to vulnerable groups like children and elderly. |  |  |  |  |  One  Two  Three or more |
| 56 | Can you list all the foods or food groups you consumed yesterday from morning until night (24 hours recall)?" (Purpose: This helps categorize the foods consumed into standard food groups used for MDDW, e.g., grains, fruits, vegetables, dairy, protein, etc.) |  |  |  |  |  Grains, white roots, tubers (maize, rice, potatoes, bread)  Pulses (beans, lentils, peas, chickpeas)  Vegetables (including dark leafy greens)  Fruits (oranges, mangoes, bananas)  Meat, poultry, or fish (including organ meats like liver  Dairy products (milk, yogurt, cheese)?  Eggs  Nuts and seeds  Oils and fats (vegetable oils, butter)  Sweets (sugar, honey, sugary foods) |
| 57 | How often does your household consume the above food groups? |  |  |  |  |  Daily  Weekly  Rarely |
| 58 | What percentage of your household's income is consumed in purchasing nutritious food? |  |  |  |  |  10 to 20%  30 to 40%  50 to 60%  other (specify) __________________ |
| 59 | In the last week, were there days when you did not have access to a variety of foods |  |  |  |  |  Yes  No |
| 60 | Are there any community programs focused on improving nutrition or food security? Hint: Identify existing programs that target nutrition and food security, especially for women and children. |  |  |  |  |  Yes  No |
| 61 | If yes, please list the programs |  |  |  |  |  |
| 62 | Have you or your household received any support, awareness sessions or training on food and nutrition security? |  |  |  |  |  Yes  No |
| 63 | If yes, What changes have you noticed in your household's food choices and eating habits after receiving the training? |  |  |  |  Reduction in Processed and Sugary Foods  Healthier Meal Planning and Portion Control  Increased Consumption of Fruits and Vegetables  Support not received |  |
| 64 | What are the challenges in accessing nutritious food at the household level? Hint: Check if there are barriers to accessing healthy food, particularly for vulnerable groups. |  |  |  |  |  Lack of awareness  Price hikes  Distance from market  Weather constraints  Dairy |
| Section 6: Public Private Producer Partnership: |  |  |  |  |  |  |
| 65 | Are you aware of any partnerships between public, private, and producer entities in your community? |  |  |  |  |  Yes  No |
| 66 | Are you aware of any government programs or initiatives supporting producers in your area? Hint: Assess awareness of public sector involvement. |  |  |  |  |  Yes  No |
| 67 | If yes, Have you received support or services from public sector organizations in the past year? Hint: Evaluate access to public sector resources. |  |  |  |  |  Yes, frequently  Occasionally  Never |
| 68 | How effective do you find the government’s support in addressing producer needs? Measure satisfaction with public sector interventions. |  |  |  |  |  Very effective,  Effective,  Neutral,  Ineffective |
| 69 | Have you participated in any training or capacity-building sessions organized by the government? |  |  |  |  |  Yes  No |
| 70 | If yes, please list down training names? |  |  |  |  |  |
| 71 | What additional support would you like to receive from the government? |  |  |  |  |  |
| 72 | Are you aware of any partnerships between producers and private companies in your area? |  |  |  |  |  Yes  No |
| 73 | Have you received any financial or technical support from private sector organizations? |  |  |  |  |  Yes, frequently  Occasionally  Never |
| 74 | Do private companies help market your products or services? |  |  |  |  |  Yes  No |
| 75 | Do you feel private sector organizations provide fair terms in partnerships? |  |  |  |  |  Yes  No |
| 76 | How can private companies better support producers like you? |  |  |  |  |  |
| 77 | Are you part of any producer organization (e.g., cooperatives, associations, PFO, etc.)? |  |  |  |  |  Yes  No |
| 78 | Do producers in your community share resources (e.g., equipment, market spaces)? |  |  |  |  |  Yes  No |
| 79 | What are the key skills or knowledge areas producers lack in your community? |  |  |  |  |  |
| 80 | Do you feel producers are adequately represented in partnerships with the public and private sectors? |  |  |  |  |  Yes  No |
| 81 | What additional support or opportunities do you think producers need to thrive? |  |  |  |  |  |
| 82 | Do you think collaborations between public, private, and producer organizations benefit your community? |  |  |  |  |  Yes, greatly,  Somewhat,  Not at all  |
| 83 | What challenges do you see in establishing or maintaining partnerships among public, private, and producer entities? |  |  |  |  |  |
| 84 | What would make partnerships between public, private, and producer entities more effective? |  |  |  |  |  |
| Section 7: Climate Change & Environment: |  |  |  |  |  |  |
| 85 | Do you use any climate-resilient farming techniques (e.g., crop rotation, drought-resistant seeds, irrigation systems)? |  |  |  |  |  Yes  No |
| 86 | If Yes, Please specify |  |  |  |  |  Crop rotation  Use of drought-resistant seeds  Irrigation systems (e.g., drip irrigation, sprinkler systems)  Soil management practices (e.g., mulching, cover cropping)  Agroforestry  Integrated pest management  Others (please specify): |
| 87 | Are you aware of climate/environmental risks affecting your farming practices? |  |  |  |  |  Yes  No |
| 88 | If Yes, which of the following risks are you aware of? |  |  |  |  |  Drought  Flooding  Erratic rainfall  Soil degradation  Pests and diseases  Rising temperatures  Water scarcity  Others (please specify): |
| 89 | What steps do you take to mitigate climate risks (e.g., soil management, water conservation)? |  |  |  |  |  Crop rotation  Use of drought-resistant seeds  Water conservation techniques (e.g., rainwater harvesting, drip irrigation)  Soil management practices (e.g., mulching, cover cropping)  Diversifying crops  Agroforestry  Building or maintaining flood protection measures  Integrated pest management  Others (please specify):  None |
| 90 | Do you have access to information or services related to climate risk management? |  |  |  |  |  Yes  No |
| 91 | If Yes, what is the source of the information or services? (Select all that apply): |  |  |  |  |  Government agencies  NGOs/Development organizations  Private sector  Farmer groups or cooperatives  Research institutions  Media (e.g., TV, radio, newspapers)  Digital platforms (e.g., apps, websites, social media)  Community meetings or local leaders  Others (please specify): |
| 92 | If Yes, what type of services do you access? (Select all that apply): |  |  |  |  |  Weather forecasts  Climate risk advisory  Early warning systems  Training programs  Financial services (e.g., climate insurance, loans)  Agricultural inputs (e.g., seeds, fertilizers)  Technology or equipment for climate resilience  Others (please specify): |
| 93 | Do you face any barriers in adopting climate-resilient practices? |  |  |  |  |  Yes  No |
| 94 | If Yes, which of the following barriers do you face? (Select all that apply): |  |  |  |  |  Lack of financial resources  Limited access to information or training  Unavailability of climate-resilient inputs (e.g., seeds, equipment)  Lack of access to credit or loans  Insufficient government support  Limited access to technology or infrastructure  Social or cultural constraints  Lack of awareness about climate-resilient practices  Uncertainty about the effectiveness of these practices  Others (please specify): |
| 95 | Are you part of any farmer group or institution? |  |  |  |  |  Yes  No |
| 96 | If yes, does your group provide support for managing climate-related risks? |  |  |  |  |  Yes  No |
| 97 | If Yes, what type of support does your group provide? (Select all that apply): |  |  |  |  |  Training and capacity-building programs  Financial support (e.g., grants, loans)  Provision of climate-resilient seeds and inputs  Access to technology or equipment  Dissemination of climate risk information or advisories  Development of early warning systems  Community-level planning and resource mobilization  Policy advocacy and lobbying for climate action  Others (please specify): |
| 98 | Have you received any institutional support for climate adaptation measures? |  |  |  |  |  Yes  No |
| 99 | If Yes, which institution provided the support? (Select all that apply): |  |  |  |  |  Government agencies  NGOs/Development organizations  Private sector  Research institutions  Farmer groups or cooperatives  International organizations  Others (please specify): |
| 100 | What type of support did you received? (Select all that apply): |  |  |  |  |  Financial support (e.g., grants, subsidies, loans)  Training and capacity-building  Provision of climate-resilient seeds or inputs  Access to technology or equipment  Climate risk advisories or information  Infrastructure development (e.g., irrigation systems, flood protection)  Others (please specify): |
| 101 | What gaps do you observe in institutional support for managing climate/environment risks? |  |  |  |  |  Lack of funding  Insufficient technical expertise  Weak policy enforcement  Limited inter-agency coordination  Inadequate data collection and monitoring  Lack of community involvement  Other (please specify) |
| 102 | Did you or anyone in the household receive any training or advice on the management of climate-related risks from any project? |  |  |  |  |  Yes  No |
| 103 | if yes, which of the following sources provided the training or advice? (Select all that apply) |  |  |  |  |  Government agencies  NGOs/Development organizations  Private sector  Farmer groups or cooperatives  Research institutions  Others (please specify): |
| 104 | please specify the types of training or advice you or anyone in your household received. |  |  |  |  |  Crop diversification  Water management techniques  Soil health and conservation  Pest and disease management  Climate-smart agriculture practices  Financial planning and risk management  Early warning systems  Other (please specify): __________ |
| 105 | What skills or training do you think would help improve your climate resilient farming? |  |  |  |  |  Crop diversification  Water management techniques  Soil health and conservation  Pest and disease management  Climate-smart agriculture practices  Financial planning and risk management  Early warning systems  Other (please specify) |
| 106 | What gaps do you perceive in current efforts to support farmers in managing climate risks? |  |  |  |  |  Lack of access to climate information and forecasts  Inadequate financial support and insurance options  Insufficient training and capacity-building programs  Limited access to resilient seeds and technologies  Poor infrastructure for water management  Limited government policies or incentives  Other (please specify) |

`

Signature of the Interviewer: ___________________________________

#### Annex-B:

Key-Informative-Interviews (KIIs)

Targeted Respondents: Officials from Agriculture and Livestock Departments, Local Government Representatives, Community Leaders, Business Owners, Entrepreneurs, Representatives from NGOs and Cooperatives, Farmers (including Women Farmers), Traders, Local Producers, Youth, Social Welfare Department, Chamber of Commerce, Business Entities, Institutes, TEVET, and other relevant stakeholders.

Interviewee Name: ____________________________

Date: ____________________

| Guiding questions | Responses |
| --- | --- |
| Agribusiness Development: |  |
| - Professional Farmer Organizations (PFOs): |  |
| - What are the main challenges in forming and sustaining Professional Farmer Organizations? |  |
| - How effective have PFOs been in increasing market access for smallholder farmers? |  |
| - What support do PFOs need to improve their operations? |  |
| - Public-Private-Producers Partnerships (4Ps): |  |
| - How agribusiness personals facilitated linkages between farmers and the private sector? |  |
| - What challenges exist in developing and sustaining these partnerships? |  |
| - What measures can be taken to enhance the effectiveness of 4Ps? |  |
| - Farm Services Companies (FSCs): |  |
| - How responsive have Farm Services Companies been to the needs of small farmers? |  |
| - What are the key barriers to accessing services provided by FSCs? |  |
| - How can FSCs be improved to better serve smallholder farmers? |  |
| - Institutional Support Services: |  |
| - What role do institutional support services play in the success of PFOs, 4Ps, and FSCs? |  |
| - What additional institutional support is needed to meet market demands? |  |
| Skills and Employment Promotion: |  |
| - Skills Development and Vocational Training: |  |
| - How well are the existing skills development programs aligning with the needs of the agribusiness sector? |  |
| - What gaps exist in the current vocational training programs? |  |
| - How can these programs be improved to better prepare participants for the job market? |  |
| - Public-Private Internship Programs: |  |
| - How effective has the internship program been in providing practical experience to young graduates? |  |
| - What challenges have been encountered in implementing the internship program? |  |
| - What recommendations would you make to enhance the impact of the internship program? |  |
| - Policy Reform: |  |
| - What policies have been identified as crucial for improving rural livelihoods? |  |
| - How effective has the project been in advocating for policy reforms? |  |
| - What additional policy support is needed to ensure the sustainability of the project’s outcomes? |  |
| Current agribusiness activities of different market actors in Khyber Pakhtunkhwa, with a focus on identifying areas of intervention for youth and rural women |  |
| - What are the roles and contributions of different market actors in the existing agribusiness value chains in KP? |  |
| - What challenges and opportunities do youth and rural women face within the agribusiness value chains? |  |
| - What resources, skills, and support systems are currently available to agribusiness actors, particularly youth and rural women, in KP? |  |
| - Which value chains have the most potential for high-impact interventions that could benefit agribusiness actors, especially youth and rural women. |  |
| Training needs for potential roles in developing nutrition-sensitive value chains in Khyber Pakhtunkhwa |  |
| - What specific skills and knowledge gaps exist among individuals currently involved in or interested in roles within nutrition-sensitive value chains? |  |
| - What are the priority skills required to enhance the nutritional outcomes within each segment of the value chain (production, processing, distribution, retail)? |  |
| - What barriers do individuals, including youth and rural women, face in accessing skills training for roles in nutrition-sensitive value chains? |  |

Name and Signature of the Interviewer: ____________________________________________